1

Moretele Local Municipality

_____________________________________________________

2026/2027

Service Delivery and Budget Implementation Plan

(SDBIP DRAFT)

___________________________________

1

Revision Control 2026/27 Planning

May 2026    ____________________________________________________________________________________________________

____________________________________________________________________________________________________

Strategic Services

IDP/PMS Unit

Enquiries:012716 1321 / 1433

nyakale.lale@moretele.gov.za

| Item | Topic | Page Number |
| --- | --- | --- |
| 1. | Mayor Foreword and Overview by Accounting Officer | 5 |
| 2. | SDBIP Approval | 7 |
| 3. | Key Performance Areas | 8 |
| 4. | SDBIP Contents | 9 |
|  | 4.1 Budget processes and related matters | 9 |
|  | 4.2 Components of the SDBIP | 10 |
| 5. | Municipal vision and Demographics | 11 |
|  | 5.1 Municipal Vision | 11 |
|  | 5.2 Demographics | 12 |
| 6. | Municipal Mandate, Powers, and Functions | 21 |
|  | 6.1 Municipal Mandate | 21 |
|  | 6.2 Powers and Functions | 22 |
| 7. | Financial Plan | 23 |
| 8 | Service Delivery, Indicators and Targets | 57 |
|  | 8.1.1 Infrastructure Development Services | 58 |
|  | 8.1.2 Community Development Services | 63 |

|  | 8.2 Budget and Treasury | 66 |
| --- | --- | --- |
|  | 8.3 Human Resources | 72 |
|  | 8.4 Local Economic Development | 77 |
|  | 8.5 Good Governance | 85 |
| 9 | Consolidated Planned Indicators | 100 |
| 10 | Implementing, Monitoring and Reporting of the 2026-2027 SDBIP | 101 |
| 11 | Projections of each month of revenue to be collected by source. Operational and Capital expenditure by Vote (Attached as Annexure A) | 101 |

- Mayor Foreword and Overview by the Accounting Officer

1.1 Mayor’s foreword

The preparation of the SDBIP represents one of the most important responsibilities entrusted to the leadership of the Moretele Local Municipality.

As we present this SDBIP, we do so mindful of the expectations of our residents who look to the municipality for improved living conditions, reliable services, and sustainable socio-economic opportunities. This SDBIP reflects our collective commitment as Council to respond to these expectations through careful planning, implementation, responsible governance, and inclusive development.

Over the past months, the municipality has undertaken extensive consultations with communities, ward committees, traditional leaders, business stakeholders, and civil society organisations. These engagements ensured that the voices and aspirations of our people remain at the centre of our planning processes. The priorities raised during community consultations have informed the programmes and projects outlined in the Draft IDP.

Our focus remains on addressing critical service delivery needs such as water provision, road infrastructure, sanitation, local economic development, and community services. At the same time, we continue to strengthen institutional capacity, financial sustainability, and governance systems to ensure that the municipality is better positioned to deliver on its developmental mandate.

The Draft IDP is aligned with national and provincial development priorities, including the objectives of the National Development Plan 2030, which seeks to eliminate poverty and reduce inequality through sustainable development and economic growth.

As we table the IDP, I wish to extend my appreciation to the Speaker of Council, Members of the Executive Committee, Honourable Councillors, the Municipal Manager, Directors, officials, and all stakeholders who contributed to the development of this strategic document. Your dedication and commitment to improving the lives of our people are highly appreciated.

I also encourage members of the community and all stakeholders to carefully review the Draft IDP and provide meaningful inputs during the public participation process. Your contributions will assist Council in refining the plan to ensure that it truly reflects the needs and aspirations of the people of Moretele.

Together, through cooperation, transparency, and accountability, we will continue working towards building a responsive, developmental municipality that improves the quality of life for all residents.

Cllr Masango George Manyike
Mayor
Moretele Local Municipality

_________________________

  - Overview by the Accounting officer

It is with great pleasure that I present the Service Delivery and Budget Implementation Plan (SDBIP) for Moretele Local Municipality for the 2026/2027 financial year. As we navigate an election year, we are acutely aware of the importance of aligning our plans with national priorities and the needs of our community.

Our commitment to good governance and financial stewardship remains unwavering, and I am proud to report that we have maintained our unqualified audit opinion, a testament to our dedication to transparency and accountability.

We have made significant strides in addressing our audit findings, having investigated over 60% of our UIFWE, with only unauthorized expenditure remaining, which will be processed by June 2026. This demonstrates our resolve to attain a clean audit.

Our council is functional, with all committees established, providing effective oversight and strategic direction. We have prioritized essential services, focusing on water provision, roads, and stormwater management, critical to improving the quality of life for our residents.

Our 2026/2027 budget is fully funded, reflecting our prudent financial management and commitment to sustainability. I am confident that our stable administration, with all key positions filled, is well-equipped to deliver on our mandate and drive development in our municipality.

As we move forward, we remain committed to aligning our efforts with national plans and priorities, ensuring that our services meet the needs of our community and contribute to the country's growth and development.

Mr. S.Ngwenya

Municipal Manager

Moretele Local Municipality

____________________________

- Final SDBIP Approval

Draft 2026/2027 Service Delivery and Budget Implementation Plan

is hereby approved in terms of section 53(1)(c)(ii) of the

Municipal Finance Management Act of 2003.

____________________________

Cllr G Manyike

Hon Mayor

3. Key Performance Areas

| Key Performance Area | Directorates / Units | Strategic Objective |
| --- | --- | --- |
| Basic Services and Infrastructure Development | Infrastructure Development Services | To ensure access to sustainable services and infrastructure to all households |
|  | Community Development Services | To ensure access to public amenities and to promote community safety, development and sustainable livelihoods |
| Financial Management and Viability | Budget and Treasury Office | To promote and ensure prudent financial management to enhance institutional viability and access to basic services |
| Institutional Development and Transformation | Human Resources and Corporate Services | To promote and enhance professional institutional development and transformation through improved human resources systems and technology |
| Local Economic Development | Local Economic Development and Planning | To promote and enhance economic development, growth and economic access |
| Good Governance and Public Participation | Strategic Services and Governance - Internal Audit - Communications - IDP/PMS - Special Projects - Public Participation - MPAC | - To promote and enhance effective governance systems for improved service delivery - To enhance and promote effective governance through credible communication systems - To promote and enhance integrated municipal planning - To promote Institutional development, transformation and good governance |

- SDBIP Context

The Municipal Finance Management Act (MFMA) No. 56 of 2003 defines the “service delivery and budget implementation plan” as the detailed plan approved by the mayor of the municipality in terms of Section 53 (1) (c) (ii) for implementing the municipality’s delivery of municipal services and its annual budget and which must include the following: -

a) Projections of each month of-

      - revenue to be collected, by source; and

      - operational and capital expenditure, by vote.

    - Service delivery targets and performance indicators for each quarter; and

    - Any other matters that may be prescribed and includes any revisions of such plan by the mayor in terms of section 54(1)(c).

In terms of Section 53 (i) (c)(ii) of the MFMA, the SDBIP must be approved by the mayor of a municipality within 28 days of the approval of the budget

  - Budget processes and related matters

Section 53 (4) requires that the mayor of a municipality must—

    - provide general political guidance over the budget process and the priorities that must guide the preparation of a budget.

    - co-ordinate the annual revision of the integrated development plan in terms of section 34 of the Municipal Systems Act and the preparation of the annual budget, and determine how the integrated development plan is to be considered or revised for the purposes of the budget; and (c) take all reasonable steps to ensure—

      - that the municipality approves its annual budget before the start of the budget year.

      - that the municipality’s service delivery and budget implementation plan is approved by the mayor within 28 days after the approval of the budget: and

      - that the annual performance agreements as required in terms of section 57(1)(b) of the Municipal Systems Act for the municipal manager and all senior managers-

(aa) comply with this Act to promote sound financial management.

(bb)are linked to the measurable performance objectives approved with the budget and to the service delivery and budget implementation plan; and

(cc) are concluded in accordance with section 57(2) of the Municipal Systems Act

  - Components of the SDBIP

Municipal Finance Management Act Circular 13 provides that the Service Delivery and Budget Implementation Plan should comprise of the following:

Component Description

| Monthly Projections of Revenue to be Collected for each Source | o | The Municipality must institute measures to achieve its monthly revenue targets for each source These measures will enable the Municipality to assess its cash flow monthly with a view to undertaking contingency plans should there be a cash flow shortage or other challenges and positives |
| --- | --- | --- |
| Monthly Projections of Expenditure and Revenue for each Vote | o | The monthly projection of revenue and expenditure per vote relate to the cash paid and reconciles with the cash flow statement adopted with the budget |
|  | o | The focus under this component is a monthly projection per vote in addition to projections by source |
| Quarterly Projections of Service Delivery Targets and Performance Indicators for each Vote | o o o | This component of the SDBIP requires non-financial measurable performance objectives in the form of service delivery targets and other indicators of performance The focus is on outputs rather than inputs Service delivery targets relate to the level and standard of service being provided to the community and include the addressing of backlogs in basic services |

- Municipality’s Vision and Demographics

  - Municipal Vision

Vision

A Developing Moretele for Growth and Prosperity for All

Mission

To provide and enhance equitable, cost effective, efficient and quality

service delivery and exploit resources for sustainable development,

growth and prosperity for all

Values

Service to stakeholders

Excellence

Transparency

Responsiveness

Value for diversity

Value for partnerships

Ethical standards

  - Demographics (Summary)

Population

South African Population as at census 2022 is at 62,027,503 and Northwest population is at 3,804,548 , Bojanala is at 1,624,428 and Moretele at 186 499.

| Male | Female |
| --- | --- |
| 85353 | 101146 |
| Total | 186499 |

| Local | age | Male | Female | Male(%) | Female(%) |
| --- | --- | --- | --- | --- | --- |
| NW371 : Moretele | 0-4 | 8266 | 8686 | -4.4% | 4.7% |
| NW371 : Moretele | 5-9 | 11035 | 11243 | -5.9% | 6.0% |
| NW371 : Moretele | 10-14 | 10492 | 9945 | -5.6% | 5.3% |
| NW371 : Moretele | 15-19 | 9939 | 9221 | -5.3% | 4.9% |
| NW371 : Moretele | 20-24 | 3767 | 5068 | -2.0% | 2.7% |
| NW371 : Moretele | 25-29 | 3994 | 6160 | -2.1% | 3.3% |
| NW371 : Moretele | 30-34 | 5763 | 7300 | -3.1% | 3.9% |
| NW371 : Moretele | 35-39 | 6581 | 7267 | -3.5% | 3.9% |
| NW371 : Moretele | 40-44 | 3945 | 5044 | -2.1% | 2.7% |
| NW371 : Moretele | 45-49 | 1789 | 3577 | -1.0% | 1.9% |
| NW371 : Moretele | 50-54 | 1770 | 4313 | -0.9% | 2.3% |
| NW371 : Moretele | 55-59 | 3141 | 5166 | -1.7% | 2.8% |
| NW371 : Moretele | 60-64 | 5048 | 4731 | -2.7% | 2.5% |
| NW371 : Moretele | 65-69 | 4034 | 4243 | -2.2% | 2.3% |
| NW371 : Moretele | 70-74 | 2868 | 3361 | -1.5% | 1.8% |
| NW371 : Moretele | 75+ | 2922 | 5823 | -1.6% | 3.1% |
|  | Total | 85353 | 101146 |  |  |
|  | Grand total |  | 186499 |  |  |

| Functional age groups | Number |
| --- | --- |
| 0-14 (children) | 59667 |
| 15 -34 (youth) | 51212 |
| 34-64 (adults) | 52371 |
| Elderly ( 65+) | 23250 |

| Coloured | 297 | 259 | 556 |
| --- | --- | --- | --- |
| Indian or Asian | 69 | 23 | 91 |
| White | 202 | 127 | 330 |
| Other | 169 | 39 | 208 |
| Unspecified | 6 | 3 | 9 |

| Table 2.3: Labour force characteristics by province and metro |  |
| --- | --- |
|  | Oct-Dec 2024 |
|  | Thousand |
| Northwest |  |
| Population 15-64 yrs | 2,817 |
| Labour Force | 1,593 |
| Employed | 935 |
| Unemployed | 658 |
| Not economically active | 1,224 |
| Discouraged work-seekers | 339 |
| Other | 885 |
| Rates (%) |  |
| Unemployment rate | 41.3 |
| Employed / population ratio (Absorption) | 33.2 |
| Labour force participation rate | 56.6 |

| Home/community play group | 1355 |  |  |
| --- | --- | --- | --- |
| Other (Specify) | 83 |  |  |
| None | 9344 |  |  |
| Space-Time Research |  |  |  |
| Census 2022 Version 1.1 |  |  |  |
| Table 1 |  |  |  |
| Highest level of education |  |  |  |
| for Person weight, 20 +, Moretele Local Municipality |  |  |  |
| No schooling | 8747 |  |  |
| Some primary | 12848 |  |  |
| Completed primary | 5216 |  |  |
| Some secondary | 43470 |  |  |
| Completed Grade 12/ Standard 10 | 49903 |  |  |
| Higher education | 5839 |  |  |
| Other | 742 |  |  |

| Formal dwelling | 88.4 |  |
| --- | --- | --- |
| Informal dwelling/ | 7.2 |  |
| Other | 0.4 |  |
| Not applicable | 3.5 |  |
| Caravan/tent | 0.0 |  |
| Traditional dwelling/hut/structure made of traditional materials | 0.4 |  |
| Total | 100.0 |  |

| Census 2022 |  |  |
| --- | --- | --- |
| Summation Options and Refuse or Rubbish |  |  |
| for Moretele Local Municipality |  |  |
|  | Percentage (%) |  |
| Own refuse dump | 46.0 |  |
| Removed by local authority/private company/community members at least once a week | 33.8 |  |
| Communal container/central collection point | 11.4 |  |
| Dump or leave rubbish anywhere (no rubbish disposal) | 4.9 |  |
| Removed by local authority/private company/community members less often | 1.9 |  |
| Communal refuse dump | 0.8 |  |
| Other | 1.1 |  |
| Total | 100.0 |  |

| Functional age groups | Number |
| --- | --- |
| 0-14 (children) | 59667 |
| 15 -34 (youth) | 51212 |
| 34-64 (adults) | 52371 |
| Elderly ( 65+) | 23250 |
| Sex ratio |  |
| 0.84 |  |

| Mid-year population estimates - 2024 |  |  |
| --- | --- | --- |
| Population by sex: |  |  |
| Male | Female |  |
| 85353 | 101146 |  |
| Total | 186499 |  |

Access to electricity lighting

Number of Households

Average household in size in a district

Internet Services

The figure below indicates 95% have no access to internet services.

Development Implications

The figure clearly points to the fact that there is a strong need for action to maximize internet access throughout the municipal area. The municipality should in partnership with other sectors explore available means of improving internet and cell phone network access.

Tenure Status

The figure below indicates that 72% of the households own and fully paid off and with about 23, 7% households occupied rent free. It should be noted that very few areas have been proclaimed and there is a larger percentage of households found in traditional council’s areas, which means that security of tenure is not guaranteed for 72% as indicated.

Census 2022

5.3. Economic Analysis

The spatial development framework of the municipality is shaped by the rich agricultural history characterizing large pieces of land in the area. It is against this backdrop that agriculture has become a focal point in all economic development prospects for the municipality constituency.

The municipality has vast tracts of land which can be used to harness economic development opportunities. It is believed that livestock farming is the main type of farming activity that is carried out in the local municipality. The tourism sector in the Moretele Local Municipality is not well established.

Trading Services are key economic drivers of the local economy. The district economy is largely driven by mining primarily around Rustenburg and Brits.  The weakness for the local economy is that there are no industries to boost the economy and create jobs to cushion poverty for the more than 25 000 people who are unemployed.

The real economic growth rate for the Northwest province in 2007 was 2.7% with the poverty gap standing at 8.8%. the contribution of Gauteng province into the South African Economy in 2011 was 34.5% whereas that of the Northwest Province at the same period was 6.5%, this implies that chances of finding employment in the province and the municipality in are very slim.

- Municipal Mandate and Powers and Functions

  - Mandate

Section 152 of the Constitution of the Republic Mandates local government to perform the following functions as depicted by the figure below:

To provide democratic and

accountable government for

local communities

To ensure the provision of services

to communities in a sustainable

manner

To promote social and economic

development

To promote safe and healthy environment

To encourage the involvement of

communities and community

organisations in the matters of

local government

  - Powers and Functions

The table below provides a list of allocated powers and functions of the municipality in accordance with Schedule 4 B and 5 B of the Constitution (1996) and Sections 83, 84, 85 and 86 of the Municipal Structures Act.

| Authorized Functions |  |  | Non-Authorized |  |
| --- | --- | --- | --- | --- |
| - Air Pollution | - Municipal Public Transport | - Childcare Facilities | - Electricity |
| - Local tourism | - Trading Regulations | - Municipal planning | - Fire fighting |
| - Municipal Airport | - Beaches and Amusement | - Pontoons and Ferries | - Municipal Health Services |
| - Storm Water | - Facilities | - Water (potable) |  |
| - Sanitation | - Cemeteries, Funeral | - Billboards and the |  |
| - Billboards and the Display of Advertisement in Public Places | - Parlours and Crematoria | - Display of |  |
| - Control of Public Nuisance | - Control of Undertaking that Sell Liquor to the public | - Advertisement in Public |  |
| - Fencing and Fences | - Licensing of dogs | - Places |  |
| - Local Amenities | - Markets | - Cleansing |  |
| - Local Sports Facilities | - Noise Pollution | - Facilities for the accommodation, care, and burial of animals Licensing of undertakings that sell food to the Public |  |
| - Municipal Parks and Recreation | - Refuse Removal, refuse Dumps and solid waste disposal | - Municipal Abattoirs Pounds |  |
| - Public Places | - Traffic and Parking | - Street Trading |  |
| - Street Lighting |  |  |  |
| - Building Regulation |  |  |  |
| - Municipal airport |  |  |  |

- Financial Plan

2026/2027 Final Summary Budget

Executive Summary

This budget is the application of sound financial management principles for the compilation of the Municipality’s financial plan which is essential and critical to ensure that the Municipality remains financially viable and that municipal services are provided sustainably, economically, and equitably to all communities.

The Municipality’s business and service delivery priorities were reviewed as part of this year’s planning and budget process. The appropriate funds were transferred from low- to high priority programmes to maintain sound financial stewardship.

The Municipality is embarking on implementing a range of revenue collection strategies to optimize the collection of debt owed by consumers, mainly state owned. Some of these revenue collection strategies are through the new valuation roll which is implemented from FY 2024/2025 financial year and is valid until 2028/2029.

BUDGET 2026/2027 MTREF.

The main challenges experienced during the compilation of the Budget 2026/2027 MTREF can be summarized as follows:

- Based on the programs that the service delivery department must undertake, we had to ensure that they do not drive the budget to be in deficit, which means that certain programs have to wait or stop to have a funded budget.

- Aging and poorly maintained roads, wastewater and water infrastructure.

- Reprioritizing capital projects and expenditure within the existing resource envelope given cash flow realities and ensuring the non-declining cash position of the municipality.

- The need to reprioritize projects and expenditure within the existing resource envelope given the cash flow realities and with also ensuring the non-declining cash position of the municipality.

- Affordability of capital projects – MIG allocation for 2025/2026 was R139.5 million, it has been increased to R159.9-million in 2026/2027.The municipality has prioritized water and sanitation on new projects and completion of MIG registered projects and R9.3 million is ring-fenced for refurbishment of Maubane sport complex.

- WSIG allocation for 2025/2026 was R42.5-million, it has been reduced to R8.4 -million in 2026/2027 financial year. The grant is allocated for Sanitation project.

The following budget principles and guidelines directly informed the compilation of the Draft Budget 2026/2027:

- The 2026/2027 Draft Budget priorities and targets, as well as the base line allocations contained in the Draft Budget were adopted as the upper limits for the new baselines.

- Intermediate service level standards were used to inform measurable objectives, targets, and backlog eradication goals; In view of the following table is a consolidated overview of the proposed 2026/2027 Medium-term Revenue and Expenditure.

- The total revenue budget for 2025/2026 was R859.9 million including capital budget revenue when compared with 2026/2027 budget of R887.9-million which represents an increase budget income estimates of R28 -million.

- The 2025/2026 Financial Year (FY) operating expenditure was R 725.5 million, compared to the budget of R794.8 million for 2026/2027 which indicates an increase of R69.3 million. This reflects a surplus of R 93.1 million.

Operating Revenue framework

Moretele Local Municipality continues to improve the quality of services for its citizens; it needs to generate the required revenue. In these tough economic times strong revenue management is fundamental to the financial sustainability of every municipality. The reality is that we are facing serious financial difficulties because of our low revenue generation capacity. This will further delay the reduction of backlogs and poverty. The expenditure required to address these challenges will inevitably always exceed available funding; hence difficult choices must be made in prioritizing projects to be implemented and balancing expenditures against realistically anticipated revenues. The municipality grants reliance and seeks various methods to augment the financial incapacity.

Some of the mechanisms explored are the grant funds sought from different departments and the alignment of the municipality’s strategic objectives to the main conditions of the grants being provided by sister departments.

Moretele Municipality is still dependent on grants as a major contributor of revenue. The Gazetted Division of Revenue bill has confirmed the following transfers to the municipality

Grants

The total allocation for operational grants for 2026/2027 is R503.2-million funded by transfers from National Department and other departments. The Capital grant allocation is R160.8 million funded by transfers from National Departments.

Service charges

In line with the formats prescribed by the Municipal Budget and Reporting Regulations, capital transfers and contributions are excluded from the operating statement, as inclusion of these revenue sources would distort the calculation of the operating surplus/deficit. Revenue generated from rates and services charges forms a signficant percentage of the revenue basket for the Municipality. The total revenue projections for Property rates and service charges for 2026/2027 are R163.2 million, the municipality currently applies a flat-rate tariff for unmetered water consumers, which is not fully cost reflective. In light of the approved bulk water tariff increase by Magalies Water and rising operational costs, a cost-reflective analysis was undertaken.

The analysis considered the unit cost of bulk water, estimated average household consumption, and associated distribution and operational costs. The findings indicate that the current flat-rate tariff is under-recovering the actual cost of service provision.

To address the issue, the municipality proposes a phased adjustment of the flat-rate tariff over the MTREF period to gradually align it with the cost of supply, while mitigating the impact on indigent households. This approach supports financial sustainability while ensuring affordability and compliance with tariff-setting principles. This reflects 22% of the total revenue budget excluding capital transfers of R727.09million.

Other Operational Revenue

Operating Expenditure Framework

The Municipality’s expenditure framework for the 2026/2027 budget is informed by the funding of the budget over the medium-term as informed by Section 18 and 19 of the MFMA and should there be operational gains and efficiencies will be directed to funding the capital budget and other core services. Based on the financial constraints that we have as a municipality, the expenditure to be incurred must be budgeted within the revenue we anticipate receiving, it is therefore difficult to propose a new delivery project without the outside of the current expenditure we have.

EMPLOYEES’ COSTS

The allocation for employee related costs for the 2026/2027 financial year is R201,7 million, which equals 25 per cent of the total operating expenditure. The increase of (4.75%) is in line with the Salary and Wage Collective Agreement for the period 01 July 2024 to 30 June 2029 dated 6 September 2024 through the agreement that was approved by the Bargaining Committee of the Central Council in terms of Clause 17.3 of the Constitution.

COUNCILLORS COSTS

The budget allocation for Councilor’s costs for the financial year is R25.07 million. The cost associated with the remuneration of councilors is determined by the Minister of Cooperative Governance and Traditional Affairs in accordance with the Remuneration of Public Office Bearers Act, 1998 (Act 20 of 1998).

DEBT IMPAIRMENT/WRITE-OFF

The provision of debt impairment was determined based on a non-collection rate of 90 per cent and the Debt Write-off Policy of the Municipality. The current situation is that the municipality has been impairing 90% of its debtors every year. 10% is mainly the government and business institution who we try every month to collect the amount owed to the municipality. The Debt impairment projection for 2026/2027 is R146 million.

BULK PURCHASES

The 2025/2026 budget for bulk purchase was R59.1 million and the budget for 2026/2027 has increased to R59.9 million, this indicates an increase of R800 thousand.

REPAIRS AND MAINTENANCE

The repairs and maintenance budget are supposed to be aligned to the needs required to preserve and maintain the Municipality’s current infrastructure. In terms of the Municipal Budget and Reporting Regulations, operational repairs and maintenance are not considered a direct expenditure drive but an outcome of certain other expenditures, such as remuneration, purchases of materials and contracted services. The total budget for Repairs and maintenance is R26.1 million.

GENERAL EXPENDITURE

The general expenditure budget for 2025/2026 amounts to R84.7 million, when compared to R83.9 million for 2026/2027 financial year this reflects R800 thousand decrease.

CONTRACTED SERVICES

The contracted services budget for the year 2025/2026 was R216.3 million and for the financial year 2026/2027 the budget is R208.1 million, this reflects a decrease of R8.2 million. Repairs and maintenance were budgeted under contracted services for the value of R26.9 million, Professional Services for R64.5 million and other outsourced services for R117.5 million.

DEPRECIATION

The Depreciation budget allocation for 2025/2026 was R68.3 million, it has increased by R627 thousand when compared to 2026/2027 budget of R68.9 million, the indicator to increase the depreciation, is due to the additional of assets added to the assets register.

Budget Table

- Table A1 is a budget summary and provides a concise overview of the Municipality’s budget

- from all the major financial perspectives (operating, capital expenditure, financial position, cash flow, and MFMA funding compliance).

- The table provides an overview of the amounts approved by Council for operating performance, resources deployed to capital expenditure, financial position, cash and funding compliance, as well as the municipality’s commitment to eliminating basic service delivery backlogs.

- Financial management reforms emphasize the importance of the municipal budget being funded. This requires simultaneous assessment of the Financial Performance, Financial Position and Cash Flow Budgets, along with the Capital Budget. The Budget Summary provides the key information in this regard:

- The operating surplus/deficit (after Total Expenditure) is positive over the MTREF

- Capital expenditure is balanced by capital funding sources, of which

- Transfers recognized is reflected on the Financial Performance Budget;

- Borrowing is incorporated in the net cash from financing on the Cash Flow budget

- Internally generated funds are financed from a combination of the current generating surplus and accumulated cash-backed surpluses from previous years. The amount is incorporated in the Net cash from investing on the Cash Flow Budget. The fact that the municipality’s cash flow remains positive and is improving indicates that the necessary cash resources are available to fund the Capital Budget.

- Total operating revenue (excluding capital transfer) is R727.3 million in 2026/2027 and Revenue to be generated from property rates is R23.9 million in 2026/2027.

- The original budget for services charges for water is R108.4 million and for refuse is R30.8 million.

- Transfers recognized – operational transfers include the local government equitable share and other operating grants from national and provincial government is R503 million and the capital transfer is R160 million.

- Bulk purchases (Inventory Water) for 2026/2027 budget are R59.9-million.

- The original budgeted allocation for employee related costs for the 2026/2027 financial year is R201.7 million, which equals 25 per cent of the total operating expenditure.

- Professional Services- Budget for professional services for 2026/2027 is R64 million.

- Repairs and maintenance- The budget for 2025/2026 R26.4 million and for 2026/2027 is R26.1 million, which indicate an increase of R280 thousand.

Overview of Annual Budget Process

Section 53 of the MFMA requires the mayor of the municipality to provide general political guidance in the budget process and the setting of priorities that must guide the preparation of the budget.  In addition, Chapter 2 of the Municipal Budget, and Reporting Regulations states that the mayor of the municipality must establish a Budget Steering Committee to provide technical assistance to the mayor in discharging the responsibilities set out in section 53 of the Act.

The Budget Steering Committee consists of the Municipal Manager and senior officials of the municipality meeting under the chairpersonship of the Portfolio Committee for Budget and Treasury.

The primary aims of the Budget Steering Committee is to ensure:

- that the process followed to compile the budget complies with legislation and good budget practices;

- that there is proper alignment between the policy and service delivery priorities set out in the municipality’s IDP and the budget, considering the need to protect the financial sustainability of municipality;

- that the municipality’s revenue and tariff setting strategies ensure that the cash resources needed to deliver services are available; and

- that the various spending priorities of the different municipal departments are properly evaluated and prioritised in the allocation of resources.

In terms of section 21 of the MFMA the Mayor is required to table in Council ten months before the start of the new financial year (i.e. in August 2025) a time schedule that sets out the process to revise the IDP and prepare the budget.

Intergrated development plan and Service delivery and budget implementation plan

The Council’s IDP is its principal strategic planning instrument, which directly guides and informs its planning, budget, management, and development actions.  This framework is rolled out into objectives, key performance indicators and targets for implementation which directly inform the Service Delivery and Budget Implementation Plan.  The Process Plan applicable to this cycle included the following key IDP processes and deliverables:

- Registration of community needs;

- Compilation of departmental business plans including key performance indicators and targets;

- Financial planning and budgeting process;

- Public participation process;

- Compilation of the SDBIP, and

The IDP has been taken into a business and financial planning process leading up to the 2026/2027 MTREF, Mid-year Review and adjustments budget.  The business planning process has subsequently been refined in the light of current economic circumstances and the resulting revenue projections.

With the compilation of the 2026/2027 MTREF, each department/function had to review the business planning process, including the setting of priorities and targets after reviewing the mid-year and third quarter performance against the 2026/2027 Departmental Service Delivery and Budget Implementation Plan.  Business planning links back to priority needs and master planning and essentially informed the detail operating budget appropriations and three-year capital programme.

Financial Modelling and Key Planning Drivers

As part of the compilation of the 2026/2027 MTREF, extensive financial modelling was undertaken to ensure affordability and long-term financial sustainability.  The following key factors and planning strategies have informed the compilation of the 2026/2027 MTREF:

- Council’s growth

- Policy priorities and strategic objectives

- Asset maintenance

- Economic climate and trends (i.e. inflation, Eskom increases, and household debt)

- Performance trends

- Cash Flow Management

- Debtor payment levels

- The need for tariff increases versus the ability of the community to pay for services

- Improved and sustainable service delivery

Overview of alignment of annual budget with IDP

The Constitution mandates local government with the responsibility to exercise local developmental and cooperative governance.  The eradication of imbalances in South African society can only be realized through a credible integrated developmental planning process.

Municipalities in South Africa need to utilise integrated development planning as a method to plan future development in their areas and so find the best solutions to achieve sound long-term development goals.  A municipal IDP provides a five-year strategic programme of action aimed at setting short, medium, and long term strategic and budget priorities to create a development platform, which correlates with the term of office of the political incumbents.  The plan aligns the resources and the capacity of a municipality to its overall development aims and guides the municipal budget.  An IDP is therefore a key instrument which municipalities use to provide vision, leadership, and direction to all those that have a role to play in the development of a municipal area.  The IDP enables municipalities to make the best use of scarce resources and speed up service delivery.

Integrated developmental planning in the South African context is amongst others, an approach to planning aimed at involving the municipality and the community to jointly find the best solutions towards sustainable development.  Furthermore, integrated development planning provides a strategic environment for managing and guiding all planning, development and decision making in the municipality.

It is important that the IDP developed by municipalities correlate with National and Provincial intent. It must aim to co-ordinate the work of local and other spheres of government in a coherent plan to improve the quality of life for all the people living in that area. Applied to Moretele, issues of national and provincial importance should be reflected in the IDP of the municipality.  A clear understanding of such intent is therefore imperative to ensure that the municipality strategically complies with the key national and provincial priorities.

The aim of this revision cycle was to develop and coordinate a coherent plan to improve the quality of life for all the people living in the area, also reflecting issues of national and provincial importance.  One of the key objectives is therefore to ensure that there exists alignment between national and provincial priorities, policies and strategies and the municipality’s response to these requirements.

The national and provincial priorities, policies and strategies of importance include amongst others:

- Green Paper on National Strategic Planning of 2009.

- Government Programme of Action;

- Development Facilitation Act of 1995;

- Provincial Growth and Development Strategy (GGDS);

- National and Provincial spatial development perspectives;

- Relevant sector plans such as transportation, legislation and policy;

- National Key Performance Indicators (NKPIs);

- Accelerated and Shared Growth Initiative (ASGISA);

- National 2014 Vision;

- National Spatial Development Perspective (NSDP) and

- The National Priority Outcomes.

The Constitution requires local government to relate its management, budgeting and planning functions to its objectives.  This gives a clear indication of the intended purposes of municipal integrated development planning.  Legislation stipulates clearly that a municipality must not only give effect to its IDP but must also conduct its affairs in a manner which is consistent with its IDP.  The following table highlights the IDP’s five strategic objectives for the 2026/2027 MTREF and further planning refinements that have directly informed the compilation of the budget.

- Service Delivery Objectives, Indicators and Targets

Municipal objectives by Directorate

Infrastructure Development Services

>

To ensure access to sustainable services and infrastructure to all households

Community Development Services

>

To ensure access to public amenities and to promote community safety, development and sustainable livelihoods

Budget and Treasury Office

>

To promote and ensure prudent financial management to enhance institutional viability and access to basic services

Human Resources and Corporate Services

>

To promote and enhance professional institutional development and transformation through improved human resources systems and

technology

Local Economic Development and Planning

>

To promote and enhance economic development, growth and economic access

Strategic Services and Governance

>

To promote and enhance effective governance systems for improved service delivery

>

To enhance and promote effective governance through credible communication systems

>

To promote and enhance integrated municipal planning

>

To promote Institutional development and transformation and good governance

Moretele Local Municipality

_____________________________________________________

2026/2027

Draft SDBIP

BTO

| National Outcome |  |  | National Outcome Responsive, Accountable, Effective And Efficient Local Government System |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NDP Chapters |  |  | Chapter 4: Economic Infrastructure Chapter 8: Human Settlements Chapter 12: Building Safer Communities Chapter 13: Building a capable state Chapter 14: Promoting accountability and fighting corruption |  |  |  |  |  |  |  |  |  |  |  |
| Municipal Strategic Objectives |  |  | To promote and enhance effective governance systems for improved service delivery, To enhance and promote effective governance through credible communication systems, to promote and enhance integrated municipal planning, To promote Institutional development and transformation and good governance |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Goals |  |  | SG BTO: Ensuring Prudent Financial Management through improved sustainable revenue generation measures |  |  |  |  |  |  |  |  |  |  |  |
| Key Performance Area |  |  | Financial Management and Viability |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 7. Ensure Financial Sustainability & revenue enhancement |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |
| 7.1 | Output | 7.1 Improve municipal revenue collection and maintain financial sustainability | % (50) of billed revenue collected by June 2027 | Debtors Age analysis | Target | Percentage | 50% | 50% | 50% | 50% | 50% | 50% | Budget and Treasury Office | Chief Financial Officer |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
|  |  |  |  |  | 50% | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |
| 7.2 | Output | 7. 2. Improve municipal revenue collection and maintain financial sustainability | Number(1) of Annual completions of supplementary valuation rolls with legislated timeframes by March 2027 | 1. supplementary valuation rolls | Target | Number | 1 | 1 |  |  | 1 |  | Budget and Treasury Office | Chief Financial Officer |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
|  |  |  |  |  | Operating | N/A |  | 3000000 | 0 | 0 | 0 | 0 |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |
| 7.3 | Output | 7.3. Improve municipal revenue collection and maintain financial sustainability | %(5) increase in revenue base after tariff schedule approval by September 2027 | Tariff schedule | Target | Percentage | 5% | 5% | 5% |  |  |  | Budget and Treasury Office | Chief Financial Officer |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
|  |  |  |  |  | Operating | N/A |  | 8000000 | 0 | 0 | 0 | 0 |  |  |

| National Outcome |  |  | National Outcome Responsive, Accountable, Effective And Efficient Local Government System |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NDP Chapters |  |  | Chapter 4: Economic Infrastructure Chapter 8: Human Settlements Chapter 12: Building Safer Communities Chapter 13: Building a capable state Chapter 14: Promoting accountability and fighting corruption |  |  |  |  |  |  |  |  |  |  |  |
| Municipal Strategic Objectives |  |  | To promote and enhance effective governance systems for improved service delivery, To enhance and promote effective governance through credible communication systems, to promote and enhance integrated municipal planning, To promote Institutional development and transformation and good governance |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Goals |  |  | SG BTO: Ensuring Prudent Financial Management through improved sustainable revenue generation measures |  |  |  |  |  |  |  |  |  |  |  |
| Key Performance Area |  |  | Financial Management and Viability |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 8. Strengthen budget planning and financial management |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |
| 7.4 | Output | 8.1. Prepare a credible, funded and sustainable municipal budget aligned with the IDP | Number (1) preparation and submission of the Draft MTREF budget By March 2027 | Draft MTREF budget | Target | Number | 1 | 1 |  |  | 1 |  | Budget and Treasury Office | Chief Financial Officer |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
|  |  |  |  |  | 50% | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |
| 7.5 | Output | 8. 2. Prepare a credible, funded and sustainable municipal budget aligned with the IDP | Number( 4)Quarterly submission of budget performance by June 2027 | Sec 52 | Target | Number | 4 | 4 | 1 | 1 | 1 | 1 | Budget and Treasury Office | Chief Financial Officer |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
|  |  |  |  |  | Operating | N/A |  | 3000000 | 0 | 0 | 0 | 0 |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |
| 7.6. | Output | 8.3 Prepare a credible, funded and sustainable municipal budget aligned with the IDP to maintain financial sustainability | Number (4) Quarterly savings on cost containment by June 2027 | Sec 52 | Target | Number | 4 | 4 | 1 | 1 | 1 | 1 | Budget and Treasury Office | Chief Financial Officer |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
|  |  |  |  |  | Operating | N/A |  | 8000000 | 0 | 0 | 0 | 0 |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |
| 7.7 | Output | 8.4. Prepare a credible, funded and sustainable municipal budget aligned with the IDP to maintain financial sustainability | Number (12) Monthly submission of in-year reports by June 2027 | Sec 71 | Target | Number | 12 | 12 | 3 | 3 | 3 | 3 | Budget and Treasury Office | Chief Financial Officer |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
|  |  |  |  |  | Operating | N/A |  | 8000000 | 0 | 0 | 0 | 0 |  |  |

| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |
| 7.8 | Output | 8. 2. Prepare a credible, funded and sustainable municipal budget aligned with the IDP | Number(1)Annually table funded budget by June 2027 | 1 | Target | Number | 1 | 1 |  |  |  | 1 | Budget and Treasury Office | Chief Financial Officer |

| National Outcome |  |  | National Outcome Responsive, Accountable, Effective And Efficient Local Government System |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NDP Chapters |  |  | Chapter 4: Economic Infrastructure Chapter 8: Human Settlements Chapter 12: Building Safer Communities Chapter 13: Building a capable state Chapter 14: Promoting accountability and fighting corruption |  |  |  |  |  |  |  |  |  |  |  |
| Municipal Strategic Objectives |  |  | To promote and enhance effective governance systems for improved service delivery, To enhance and promote effective governance through credible communication systems, to promote and enhance integrated municipal planning, To promote Institutional development and transformation and good governance |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Goals |  |  | SG BTO: Ensuring Prudent Financial Management through improved sustainable revenue generation measures |  |  |  |  |  |  |  |  |  |  |  |
| Key Performance Area |  |  | Financial Management and Viability |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 9. Improve supply chain management compliance : Ensure transparent, fair and compliant procurement |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |
| 7.9 | Output | 9.1. Ensure transparent, fair and compliant procurement | Number (4) Quarterly submission of SCM implementation reports by June 2027 | SCM implementation report | Target | Number | 4 | 4 | 1 | 1 | 1 | 1 | Budget and Treasury Office | Chief Financial Officer |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
|  |  |  |  |  | 50% | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |
| 7.10 | Output | 9. 2. Ensure transparent, fair and compliant procurement | %(80) Reduction in Irregular expenditure by June 2027 | 1. Register of Irregular expenditure 2. Council resolution | Target | Percentage | 80% | 80% | 20% | 20% | 20% | 20% | Budget and Treasury Office | Chief Financial Officer |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |
| 7.11 | Output | 9. 3. Ensure transparent, fair and compliant procurement | Number( 4)Quarterly submission of contract management report to Audit committee by June 2027 | contract management report | Target | Number | 4 | 4 | 1 | 1 | 1 | 1 | Budget and Treasury Office | Chief Financial Officer |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |

| National Outcome |  |  | National Outcome Responsive, Accountable, Effective And Efficient Local Government System |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NDP Chapters |  |  | Chapter 4: Economic Infrastructure Chapter 8: Human Settlements Chapter 12: Building Safer Communities Chapter 13: Building a capable state Chapter 14: Promoting accountability and fighting corruption |  |  |  |  |  |  |  |  |  |  |  |
| Municipal Strategic Objectives |  |  | To promote and enhance effective governance systems for improved service delivery, To enhance and promote effective governance through credible communication systems, to promote and enhance integrated municipal planning, To promote Institutional development and transformation and good governance |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Goals |  |  | SG BTO: Ensuring Prudent Financial Management through improved sustainable revenue generation measures |  |  |  |  |  |  |  |  |  |  |  |
| Key Performance Area |  |  | Financial Management and Viability |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 10. Strengthening financial reporting and audit outcome: Enhance quality of financial reporting and achieve improved audit outcomes. |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |
| 7.12 | Output | 10.1. Enhance quality of financial reporting and achieve improved audit outcomes. | Number(1)Timely submission of Annual Financial Statements by June 2027 | SCM implementation report | Target | Number | 1 | 1 |  |  |  | 1 | Budget and Treasury Office | Chief Financial Officer |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
|  |  |  |  |  | Operational | R |  | R4000 000 | 0 | 0 | 0 | 0 |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |
| 7.13 | Output | 10. 2. Ensure transparent, fair and compliant procurement | %(100) reduction in audit findings by June 2027 | PAAP progress | Target | Percentage | 100% | 100% |  |  | 50% | 50% | Budget and Treasury Office | Chief Financial Officer |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |
| 7.14. | Output | 10. 3. Ensure transparent, fair and compliant procurement | %(100) of implementation of Audit Action plans by June 2027 | PAAP progress | Target | Number | 100% | 100% |  |  | 50% | 50% | Budget and Treasury Office | Chief Financial Officer |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |
| 7.15. | Output | 10. 4. Ensure transparent, fair and compliant procurement | Percentage(100) Improved Audit opinion: unqualified without findings by June 2027 | Audit report | Target | Number | 100% | 100% |  |  | 50% | 50% | Budget and Treasury Office | Chief Financial Officer |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |

| National Outcome |  |  | National Outcome Responsive, Accountable, Effective And Efficient Local Government System |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NDP Chapters |  |  | Chapter 4: Economic Infrastructure Chapter 8: Human Settlements Chapter 12: Building Safer Communities Chapter 13: Building a capable state Chapter 14: Promoting accountability and fighting corruption |  |  |  |  |  |  |  |  |  |  |  |
| Municipal Strategic Objectives |  |  | To promote and enhance effective governance systems for improved service delivery, To enhance and promote effective governance through credible communication systems, to promote and enhance integrated municipal planning, To promote Institutional development and transformation and good governance |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Goals |  |  | SG BTO: Ensuring Prudent Financial Management through improved sustainable revenue generation measures |  |  |  |  |  |  |  |  |  |  |  |
| Key Performance Area |  |  | Financial Management and Viability |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 11. Improve asset and insurance management: Ensure effective management of municipal assets and claims |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |
| 7.16 | Output | 11.1. Ensure effective management of municipal assets and claims | Number (1) Submission of accurate GRAP Fixed Assets register by June 2027 | SCM implementation report | Target | Number | 1 | 1 |  |  |  | 1 | Budget and Treasury Office | Chief Financial Officer |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
|  |  |  |  |  | Operational | R |  | R7 000 000 | 0 | 0 | 0 | 0 |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |
| 7.17 | Output | 11. 2. Ensure transparent, fair and compliant procurement | Number (4)Quarterly reporting of insurance claims successfully processed by June 2027 | PAAP progress | Target | Number | 4 | 4 | 1 | 1 | 1 | 1 | Budget and Treasury Office | Chief Financial Officer |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |
| 7.18. | Output | 11. 3. Ensure transparent, fair and compliant procurement | Number (1)Annual risk assessment for insurable Municipal assets by December 2027 | Assessment Report from Broker | Target | Number | 1 | 1 |  | 1 |  |  | Budget and Treasury Office | Chief Financial Officer |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
|  |  |  |  |  | Operating | N/A |  | R2000 000 | 0 | 0 | 0 | 0 |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |
| 7.19 | Output | 11. 4. Ensure transparent, fair and compliant procurement | %(100) of annual insured assets by June 2027 | Insurance portfolio | Target | Number | 100% | 100% |  |  | 50% | 50% | Budget and Treasury Office | Chief Financial Officer |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
|  |  |  |  |  | Operating | R |  | R7000 000 | 0 | 0 | 0 | 0 |  |  |

| National Outcome |  |  | National Outcome Responsive, Accountable, Effective And Efficient Local Government System |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NDP Chapters |  |  | Chapter 4: Economic Infrastructure Chapter 8: Human Settlements Chapter 12: Building Safer Communities Chapter 13: Building a capable state Chapter 14: Promoting accountability and fighting corruption |  |  |  |  |  |  |  |  |  |  |  |
| Municipal Strategic Objectives |  |  | To promote and enhance effective governance systems for improved service delivery, To enhance and promote effective governance through credible communication systems, to promote and enhance integrated municipal planning, To promote Institutional development and transformation and good governance |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Goals |  |  | SG BTO: Ensuring Prudent Financial Management through improved sustainable revenue generation measures |  |  |  |  |  |  |  |  |  |  |  |
| Key Performance Area |  |  | Financial Management and Viability |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 12. Improve cash flow and working capital management: Maintain adequate cash flow to support service delivery |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |
| 7.20 | Output | 12.1. Maintain adequate cash flow to support service delivery | % (100) compliance with 30 days payment to suppliers by June 2027 | Creditors Age analysis | Target | Percentage | 100% | 100% | 100% | 100% | 100% | 100% | Budget and Treasury Office | Chief Financial Officer |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
|  |  |  |  |  | Operational | R |  | R7 000 000 | 0 | 0 | 0 | 0 |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |
| 7.21 | Output | 12. 2. Maintain adequate cash flow to support service delivery | Number (4)Quarterly submission of section 11 reports Withdrawals by June 2027 | section 11 reports Withdrawals | Target | Number | 4 | 4 | 1 | 1 | 1 | 1 | Budget and Treasury Office | Chief Financial Officer |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |
| 7.22. | Output | 12.3. Maintain adequate cash flow to support service delivery | Number (4) Quarterly submission of section 66 reports Staff Benefits by June 2027 | section 66 reports Staff Benefits | Target | Number | 4 | 4 | 1 | 1 | 1 | 1 | Budget and Treasury Office | Chief Financial Officer |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
|  |  |  |  |  | Operating | N/A |  | 0 | 0 | 0 | 0 | 0 |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |
| 7.23 | Output | 12. 4. Maintain adequate cash flow to support service delivery | %(100) Reduction of fruitless and wasteful expenditure by June 2027 | 1.Register of Fruitless & wasteful expenditure 2. Council resolution | Target | Number | 100% | 100% |  |  | 50% | 50% | Budget and Treasury Office | Chief Financial Officer |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
|  |  |  |  |  | Operating | R |  | R7000 000 | 0 | 0 | 0 | 0 |  |  |
| National Outcome |  |  | National Outcome Responsive, Accountable, Effective And Efficient Local Government System |  |  |  |  |  |  |  |  |  |  |  |
| NDP Chapters |  |  | Chapter 4: Economic Infrastructure Chapter 8: Human Settlements Chapter 12: Building Safer Communities Chapter 13: Building a capable state Chapter 14: Promoting accountability and fighting corruption |  |  |  |  |  |  |  |  |  |  |  |
| Municipal Strategic Objectives |  |  | To promote and enhance effective governance systems for improved service delivery, To enhance and promote effective governance through credible communication systems, to promote and enhance integrated municipal planning, To promote Institutional development and transformation and good governance |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Goals |  |  | SG BTO: Ensuring Prudent Financial Management through improved sustainable revenue generation measures |  |  |  |  |  |  |  |  |  |  |  |
| Key Performance Area |  |  | Financial Management and Viability |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 13. Strengthening Risk management and internal control: Enhance internal financial controls and compliance |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |
| 7.24 | Output | 13.1. Enhance internal financial controls and compliance | %(100) implementation of internal audit recommendations by June 2027 | Internal audit report | Target | Percentage | 100% | 100% | 100% | 100% | 100% | 100% | Budget and Treasury Office | Chief Financial Officer |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
|  |  |  |  |  | Operational | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |
| 7.25 | Output | 13. 2. Enhance internal financial controls and compliance | Number (4) implementation of risk mitigation treatment by June 2027 | section 11 reports Withdrawals | Target | Number | 4 | 4 | 1 | 1 | 1 | 1 | Budget and Treasury Office | Chief Financial Officer |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
|  |  |  |  |  | Operating | R |  |  | 0 | 0 | 0 | 0 |  |  |

Moretele Local Municipality

_____________________________________________________

2026/2027

Draft SDBIP

CDS

| National Outcome |  |  | National Outcome Responsive, Accountable, Effective And Efficient Local Government System |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NDP Chapters |  |  | Chapter 4: Economic Infrastructure Chapter 8: Human Settlements Chapter 12: Building Safer Communities Chapter 13: Building a capable state Chapter 14: Promoting accountability and fighting corruption |  |  |  |  |  |  |  |  |  |  |  |  |
| Municipal Strategic Objectives |  |  | To ensure access to public amenities and to promote community safety, development and sustainable livelihoods |  |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Goals |  |  | SG CDS: To ensure access to safe and habitable public facilities, To promote and maximize participation in sports, To promote and maximize participation in sports and recreation |  |  |  |  |  |  |  |  |  |  |  |  |
| Key Performance Area |  |  | Basic Services and Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 5. Access to safe and habitable public facilities (CDS) |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |
| 5.10 | Output | 5.10 Community Resilience promoted through effective disaster management activities | Percentage (100) implementation of planned disaster management activities conducted by June 2027 | Q1-Q4: Attendance Register | Target | Percentage |  | 100 | 25 | 50 | 75 | 100 | Community Development Services | Community Development Services Director |
|  |  |  |  |  | Capital | N/A |  | 500000 | 0 | 0 | 0 | 0 |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |
| 5.11 | Output | 5.11 Health Awareness programs designed and implemented in collaboration with other Dept of Health and health agencies | Number of (08) community health awareness campaigns held by June 2027 | Programs & Attendance Registers | Target | Number | 12 | 8 | 2 | 2 | 2 | 2 | Community Development Services | Community Development Services Director |
|  |  |  |  |  | Capital | N/A |  | 200000 | 0 | 0 | 0 | 0 |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |
| 5.2 | Output | 5.2 To provide accessible and adequate cemeteries and protect from damage | Number (3) of cemeteries fenced in W6, W21 & W14 by June 2027 | Completion certificate for cemetery fencing signed by 30 Jun 2026 | Target | Number | 2 | 3 | 0 | 1 | 1 | 1 | Community Development Services | Community Development Services Director |
|  |  |  |  |  | Capital | N/A |  | 1350000 | 0 | 0 | 0 | 0 |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |
| 5.3 | Output | 5.3 To improve access to safe and habitable public facilities through upgrading and maintaining community facilities | Number (4) Municipal Public facilities developed and maintained at Municipal DLTC Offices , Municipal hall, One- Ten Com Hall & Moss Mary hall by June 2027 | Completion certificate and delivery note signed off by 30 Jun 2026 | Target | Number | 2 | 4 | 1 | 1 | 1 | 1 | Community Development Services | Community Development Services Director |
|  |  |  |  |  | Capital | N/A |  | 2000000 | 0 | 0 | 0 | 0 |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |
| 5.4 | Output | 5.4 Development of disaster management plan | Number of (1) development of disaster management Plan by June 2027 | Final copy Reviewed Disaster Management Plan | Target | Number | 1 | 1 | 0 | 1 | 0 | 0 | Community Development Services | Community Development Services Director |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |
| 5.5 | Output | 5.5 Community support for victims of disaster provided through various relief Materials | Percentage (100) cumulative of Disaster Relief Materials for disaster victims by June 2027 | Proof of Purchase materials and Delivery notes | Target | Percentage | 1 | 100 | 25 | 50 | 75 | 100 | Community Development Services | Community Development Services Director |
|  |  |  |  |  | Capital | N/A |  | 500000 | 0 | 0 | 0 | 0 |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |
| 5.6 | Output | 5.6 To create an environment focused on lifting the vulnerable society through social sector meetings and awareness programs | Number of 20 Social Sector Meeting and Awareness Programs {Disability Forum, Woman &amp; Children, Older Person, LDAC &amp; NPO’s Forums} by June 2027 | Attendance Registers and Programmes | Target | Number | 14 | 20 | 5 | 5 | 5 | 5 | Community Development Services | Community Development Services Director |
|  |  |  |  |  | Capital | N/A |  | 500000 | 0 | 0 | 0 | 0 |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |
| 5.7 | Output | 5.7 Improvement of sports facilities | Number of Sports Complex (1) building ablution and change rooms Motla Sports Complex by 30 June 2027 | Completion certificate and delivery note signed off by 30 Jun 2026 | Target | Number | 1 | 1 | 0 | 0 | 1 | 0 | Community Development Services | Community Development Services Director |
|  |  |  |  |  | Capital | N/A |  | 900000 | 0 | 0 | 0 | 0 |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |
| 5.8 | Output | 5.8 Revitalization of community libraries to encourage a culture of learning | Percentages of Community libraries (100-cumulative) revitalized and maintained by June 2027 | Quarterly reports on library grant spending | Target | Percentage |  | 100 | 25 | 50 | 75 | 100 | Community Development Services | Community Development Services Director |
|  |  |  |  |  | Capital | N/A |  | 1400000 | 0 | 0 | 0 | 0 |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |
| 5.9 | Output | 5.9 Community Safety programs designed and implemented in collaboration with other security cluster agencies | Number (12) of security cluster initiatives to fight crime implemented by June 2027 | Attendance Registers and Programs | Target | Number | 7 | 12 | 2 | 6 | 3 | 1 | Community Development Services | Community Development Services Director |
|  |  |  |  |  | Capital | N/A |  | 500000 | 0 | 0 | 0 | 0 |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |
| Outcome |  |  | 6. Participation in sports and recreation maximized |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |
| 6.1 | Output | 6.1: Sports and Recreational activities undertaken | Percentage (100), quarterly of Sports &amp; Recreational activities undertaken by June 2027 | Attendance Register and Programs | Target | Percentage |  | 100 | 25 | 50 | 75 | 100 | Community Development Services | Community Development Services Director |

Moretele Local Municipality

_____________________________________________________

2026/2027

Draft SDBIP

HR

| National Outcome |  |  | National Outcome Responsive, Accountable, Effective And Efficient Local Government System |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NDP Chapters |  |  | Chapter 4: Economic Infrastructure Chapter 8: Human Settlements Chapter 12: Building Safer Communities Chapter 13: Building a capable state Chapter 14: Promoting accountability and fighting corruption |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Municipal Strategic Objectives |  |  | To promote and enhance professional institutional development and transformation through improved human resources systems and technology |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Goals |  |  | SG HR & CS: To promote and enhance professional institutional development and transformation through improved human resources systems and technology |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Key Performance Area |  |  | Institutional Development and Transformation |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 14. Professional institutional development and transformation through improved human resources systems and technology promoted and enhanced |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.1 | Output | 14.1 Develop, review and approval of HR Policies and Unit based policies | Percentage (100) of HR related Policies and units based policies developed, reviewed and approved by June 2027 | Q2-Q4: Council Resolution on Approved Policies | Target | Percentage |  | 100 | 0 | 100 | 100 | 100 | Human Resources and Corporate Services | Director Human Resource and Corporate Services |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.10 | Output | 14.10 Service and governance systems improved through the implementation of Information and communication technology and manage legal activities | Percentage (100) implementation of planned information and communication technology initiatives and legal activities by June 2027 | Q1-Q4: Compliance Certificates or copies of reports | Target | Percentage | 100 | 100 | 100 | 100 | 100 | 100 | Human Resources and Corporate Services | Director Human Resource and Corporate Services |  |  |
|  |  |  |  |  | Capital | N/A |  | 16.8 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.11 | Output | 14.11 Employee Wellness initiatives Promoted | Percentage (100) of Employee Wellness/Campaigns initiatives held June 2027 | Q1-Q4 Attendance Register and Reports | Target | Percentage | 4 | 100 | 100 | 100 | 0 | 100 | Human Resources and Corporate Services | Director Human Resource and Corporate Services |  |  |
|  |  |  |  |  | Capital | N/A |  | 62000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.12 | Output | 14.12 Good records keeping and access to information promoted for a better Audit Opinion through the implementation of Records Management legislative compliant systems | Percentage (100) implementation of planned records keeping and access to information initiatives (Records Management legislative compliant systems by June 2027 | Q1 - Q4 Reports | Target | Percentage | 100 | 100 | 100 | 100 | 100 | 100 | Human Resources and Corporate Services | Director Human Resource and Corporate Services |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.13 | Output | 14.13 Institutionalization of Risk Management | 100% of Risk Treatment Plans resolved by June 2027 | Q1-Q4: Risk Reports | Target | Percentage | 100 | 100 | 100 | 100 | 100 | 100 | Human Resources and Corporate Services | Director Human Resource and Corporate Services |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.14 | Output | 14.14 Post Audit Action Plan to address all the audit findings of AGSA and Internal Audit implemented | 100% of Findings resolved by June 2027 | Q3-Q4: Post Audit Action Plan | Target | Percentage | 100 | 100 | 0 | 0 | 100 | 100 | Human Resources and Corporate Services | Director Human Resource and Corporate Services |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.15 | Output | 14.15 Harmonious Employer Employee Relations | Number (04) of LLF Meetings held by June 2027 | Q1-Q4: Attendance Register | Target | Number | 4 | 4 | 1 | 1 | 1 | 1 | Human Resources and Corporate Services | Director Human Resource and Corporate Services |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.16 | Output | 14.16 Submission of the Annual Employment Equity Report to Department of Employment & Labour | Number(1) of EE Report submitted to Department of Employment &amp; Labour by June 2027 | Q3: Submission/Acknowledgement Letter | Target | Number | 1 | 1 | 0 | 0 | 1 | 0 | Human Resources and Corporate Services | Director Human Resource and Corporate Services |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.17 | Output | 14.17 Promote conducive working environment | Percentage (100), of over grown grass cutting and reconciliation of overtime claims and the work output by June 2027 | Pictures and consolidated overtime claim reports | Target | Percentage |  | 100 | 100 | 100 | 100 | 100 | Human Resources and Corporate Services | Director Human Resource and Corporate Services |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.18 | Output | 14.18 Promote and support the maintenance and repairs of municipal fleet by June 2026 | Percentage (100) of maintenance and repairs of municipal fleet by June 2027 | Maintenance and repairs reports | Target | Percentage | 100 | 100 | 100 | 100 | 100 | 100 | Human Resources and Corporate Services | Director Human Resource and Corporate Services |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.2 | Output | 14.2 Review Staff Establishment | Number (1) of Reviewed and Approved Staff Establishment by June 2027 | Q4: Signed Copy of Approved Reviewed Staff Establishment | Target | Number | 1 | 1 | 0 | 0 | 0 | 1 | Human Resources and Corporate Services | Director Human Resource and Corporate Services |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.3 | Output | 14.3 Filling of Critical Vacant Senior Managers Position | Number (2) of Senior Managers appointed by June 2027 | Q4: Council Resolution on Appointment of Senior Managers | Target | Number | 5 | 2 | 0 | 0 | 0 | 2 | Human Resources and Corporate Services | Director Human Resource and Corporate Services |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.4 | Output | 14.4 Staff Appointments | Percentage (100) of staff Appointments by March 2027 | Q2- Q4: Signed Recruitment Files & Appointment Letters | Target | Percentage | 100 | 100 | 0 | 50 | 0 | 50 | Human Resources and Corporate Services | Director Human Resource and Corporate Services |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.5 | Output | 14.5 Enhanced measures and systems that create safe working conditions as prescribed for in OHSA/COIDA | Number (2) implementation of planned OHSA/COIDA-related initiatives by June 2027 | Q2 and Q4: Risk Assessment 0r Site Inspection or Medical Surveillance reports | Target | Number | 2 | 2 | 0 | 1 | 0 | 1 | Human Resources and Corporate Services | Director Human Resource and Corporate Services |  |  |
|  |  |  |  |  | Capital | N/A |  | 250000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.6 | Output | 14.6 Workplace Skills Plan implemented to promote employee development and professional growth | Percentage (100) implementation of Workplace Skills Plan initiatives by June 2027 | Q1-Q4: Attendance registers or results or academic records or Proof of payments | Target | Percentage |  | 100 | 100 | 100 | 100 | 100 | Human Resources and Corporate Services | Director Human Resource and Corporate Services |  |  |
|  |  |  |  |  | Capital | N/A |  | 2.6 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.7 | Output | 14.7 Maintenance of Municipal Offices | Percentage (100) implementation of Municipal Offices maintenance by June 2027 | Q1-Q3: Maintenance/Delivery Reports/Note | Target | Percentage | 1 | 100 | 100 | 0 | 100 | 0 | Human Resources and Corporate Services | Director Human Resource and Corporate Services |  |  |
|  |  |  |  |  | Capital | N/A |  | 400000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.8 | Output | 14.8 Communication of Council Resolutions to Senior Managers | Percentage (100%) of Council Resolution Register updated and circulated to Senior Managers by June 2026 | Q1-Q4: Signed Updated Council Resolution Register Acknowledgment of Receipt | Target | Percentage | 100 | 100 | 0 | 0 | 0 | 100 | Human Resources and Corporate Services | Director Human Resource and Corporate Services |  |  |
|  |  |  |  |  | Capital | N/A |  | 2000000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.9 | Output | 14.9 Security and access control | Percentage (100%) provision of security and access control services by June 2027 | Q1-Q4: Quarterly security, assessment reports and monthly OB entries | Target | Percentage | 100 | 100 | 100 | 100 | 100 | 100 | Human Resources and Corporate Services | Director Human Resource and Corporate Services |  |  |
|  |  |  |  |  | Capital | N/A |  | 35.6 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |

|  | Human Resources and Corporate Services MORETELE LOCAL MUNICIPALITY SDBIP Annual Plan: 2025/2026 Page of Human Resources and Corporate Services MORETELE LOCAL MUNICIPALITY SDBIP Annual Plan: 2025/2026 Page 1 of |
| --- | --- |

Moretele Local Municipality

_____________________________________________________

2026/2027

Final SDBIP

IDS

| National Outcome |  |  | National Outcome Responsive, Accountable, Effective And Efficient Local Government System |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NDP Chapters |  |  | Chapter 4: Economic Infrastructure Chapter 8: Human Settlements Chapter 12: Building Safer Communities Chapter 13: Building a capable state Chapter 14: Promoting accountability and fighting corruption |  |  |  |  |  |  |  |  |  |  |  |  |
| Municipal Strategic Objectives |  |  | To ensure access to sustainable services and infrastructure to all households |  |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Goals |  |  | SG IDS: To optimise access to water services, To enhance human dignity through adequate sanitation, To promote and to ensure integrated and safe road networks, To ensure access to safe and habitable public facilities |  |  |  |  |  |  |  |  |  |  |  |  |
| Key Performance Area |  |  | Basic Services and Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 1. Optimised access to water services |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 1.1 | Output | 1.1 Water supply through yard connection and bulk pipe in Ward 1 | Number (2500) yard connections and pipe line in Ward 1 (Ruigtesloot) by June 2027 | Progress reports & Completion certificate | Target | Number | 41856 | 2500 | 0 | 0 | 0 | 2500 | Infrastructure Development Services | Infrastructure Development Services Director |  |  |
|  |  |  |  |  | Capital | N/A |  | 32 903 895.79 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 1.2 | Output | 1.2 Water supply through Steel tanks and reservoir in Ward 12 | Number (300) water reticulation and 5km of pipeline in Ward 12 by June 2027 | Q4: Completion certificates | Target | KM | 41856 | 300 | 0 | 0 | 0 | 300 | Infrastructure Development Services | Infrastructure Development Services Director |  |  |
|  |  |  |  |  | Capital | N/A |  | 8 460 000.00 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 1.3 | Output | 1.3 Water supply through refurbishment of reservoirs with steel tank in ward 17, 19 and 20 | Number (3) refurbishment of reservoirs with (3) elevated steel tanks in Ward 17,19,20 by June 2027 | Progress reports and completion certificates | Target | Number | 41856 | 3 reservoirs and 3 Steel tanks | 0 | 0 | 3 steel tanks | 3 reservoirs | Infrastructure Development Services | Infrastructure Development Services Director |  |  |
|  |  |  |  |  | Capital | N/A |  | 20 099 450 00 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Outcome |  |  | 19. Community facilities constructed for improved public cohesion and interactions |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 19.1 | Output | 19.1 Completion of Community Hall in Ward 20 | Number (1)) completion of Community Hall in Ward 20 completed by June 2027 | Progress report and completion certificate | Target | Number |  | 1 | 0 | 0 | 0 | 1 | Infrastructure Development Services | Infrastructure Development Services Director |  |  |
|  |  |  |  |  | Capital | N/A |  | 4 886 244.11 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| 19.2 | Output | 19.2 Completion of Community Hall in Ward 18 | Number (1) completion of Community Hall in Ward 18 completed by June 2027 | Progress report and completion certificate | Target | Number |  | 1 | 0 | 0 | 0 | 1 |  |  |  |  |
|  |  |  |  |  | Capital | N/A |  | 4 209 860 01 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| 19.3 | output | 19.3 Completion of upgrading of maubane sports complex | Number (1) completion of upgrading of Maubane sports complex in Ward 15 by June 2027 | Progress report and completion certificate | Target | Number |  | 1 | 0 | 0 | 0 | 1 |  |  |  |  |
|  |  |  |  |  | Capital | N/A |  | 9 318 000 000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Outcome |  |  | 2. Human dignity enhanced through adequate sanitation |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 2.1 | Output | 2.1 Construction of Ablution facilities in in Kromkuil | Number (300) provision of VIP toilets in Kromkuil ward 23 by June 2027 | Progress report and completion certificate | Target | Number | 43571 | 300 | 0 | 100 | 100 | 100 | Infrastructure Development Services | Infrastructure Development Services Director |  |  |
|  |  |  |  |  | Capital | N/A |  | 10 000 000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Outcome |  |  | 3. Integrated and safe road networks promoted and ensured |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 3.1 | Output | 3.1: Paved roads & stormwater drainage constructed in ward 5 | Km (1) of road paved by June 2027 in ward 05 | Progress Report, Completion Certificate | Target | KM | 105 | 1km | 0 | 0 | 0 | 1km | Infrastructure Development Services | Infrastructure Development Services Director |  |  |
|  |  |  |  |  | Capital | N/A |  | 10 000 000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 3.2 | Output | 3.2 Paved roads & stormwater drainage constructed in ward18 | Km (1) of Pavement by June 2027 in swartdam ward 07 | Progress report and completion certificate | Target | KM | 105 | 1km | 0 | 0 | 0 | 1km | Infrastructure Development Services | Infrastructure Development Services Director |  |  |
|  |  |  |  |  | Capital | N/A |  | 10000000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 3.3 | Output | 3.3 Paved roads & stormwater drainage constructed in ward 17 | Km (1) of road paved by June 2027 in ward 10 | Progress report and completion certificate | Target | KM | 105 | 1km | 0 | 0 | 0 | 1km | Infrastructure Development Services | Infrastructure Development Services Director |  |  |
|  |  |  |  |  | Capital | N/A |  | 10000000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 3.4 | Output | 3.4 Paved roads & stormwater drainage constructed in ward 22 | Km (1) of road paved with stormwater by June 2027 in Ward 06 | Progress report and completion certificate | Target | KM | 105 | 1km | 0 | 0 | 0 | 1 | Infrastructure Development Services | Infrastructure Development Services Director |  |  |
|  |  |  |  |  | Capital | N/A |  | 10000000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 3.5 | Output | 3.5 Paved roads & stormwater drainage constructed in ward 21 | Km(1) of road paved in Ward 21 by June 2027 | Progress Reports and Completion Certificate | Target | Percentage |  | 1km | 0 | 0 | 0 | 1km | Infrastructure Development Services | Infrastructure Development Services Director |  |  |
|  |  |  |  |  | Capital |  |  | 10000 000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Infrastructure Development Services | Infrastructure Development Services Director |  |  |
| 3.6 | Output | 3.6 Paved roads & stormwater drainage constructed in ward 21 | Km(1) of road paved in Ward 3 phase 5 by June 2027 | Progress Reports and Completion Certificate | Target | Percentage |  | 1km | 0 | 0 | 0 | 1km |  |  |  |  |
|  |  |  |  |  | Capital |  |  | 10000 000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| 3.7 | Output | 3.7 Paved roads & stormwater drainage constructed in Mathibestad | Km(1) of road paved in Mathibestad by June 2027 | Progress Reports and Completion Certificate | Target | Percentage |  | 1km | 0 | 0 | 0 | 1km |  |  |  |  |
|  |  |  |  |  | Capital |  |  | 10000 000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Outcome |  |  | 4. Public safety enhanced through sustainable public lighting |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 4.1 | Output | 4.1 Community lighting erected for improved public safety in ward 02 | Number (6) of high mast-lights erected by March 2027 in Ward 02 | Progress report and completion certificate | Target | Number | 335 | 6 | 0 | 0 | 0 | 6 | Infrastructure Development Services | Infrastructure Development Services Director |  |  |
|  |  |  |  |  | Capital | N/A |  | 5500000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
| 4.2 | Output | 4.1 Community lighting erected for improved public safety in ward 21 | Number (6) of high mast-lights erected by March 2027 in Ward 21 | Progress report and completion certificate | Target | Number | 335 | 6 | 0 | 0 | 0 | 6 | Department | Person |  |  |
|  |  |  |  |  | Capital | N/A |  | 5500000 | 0 | 0 | 0 | 0 | Infrastructure Development Services | Infrastructure Development Services Director |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |

Moretele Local Municipality

_____________________________________________________

2026/2027

Draft SDBIP

LED

| National Outcome |  |  | National Outcome Responsive, Accountable, Effective and Efficient Local Government System |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NDP Chapters |  |  | Chapter 4: Economic Infrastructure Chapter 8: Human Settlements Chapter 12: Building Safer Communities Chapter 13: Building a capable state Chapter 14: Promoting accountability and fighting corruption |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Municipal Strategic Objectives |  |  | To promote and enhance economic development, growth and economic access |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Goals |  |  | SG LED: To maximize the economic potential and growth of the local economy through innovation and improved economic performance, To Maximize the economic potential and growth of Agriculture as a critical economic anchor in the local economy, To minimize the environmental damage through maximizing compliance to address the environmental issues that have a direct and indirect impacts on the natural environment, To maximize (should be minimize) environmental damage through temporary job creation, To maximize the economic potential development of Tourism in the area, Compliance with Town Planning Legislations/policies/regulations |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Key Performance Area |  |  | Local Economic Development |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 10. The economic potential development of Tourism in the area maximized |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 10.1 | Output | 10.1 Tourism Development and supported | Number 10 of Tourism projects supported by June 2027 | Appointment letter, final feasibility report, delivery Note and attendance registers and picture | Target | Number | 3 | 10 | 2 | 1 | 4 | 3 | Local Economic Development and Planning | Director Local Economic Development |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Outcome |  |  | 11. Compliance with Town Planning Legislations/policies/regulations |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 11.1 | Output | 11.1 Land-Use Scheme Review | Number (5) milestones land use scheme review by June 2027 | Inception report, status quo & situational analysis, draft land use scheme, final land use scheme and closure report | Target | Number |  | 5 | 1 | 1 | 1 | 2 | Local Economic Development and Planning | Director Local Economic Development |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 11.2 | Output | 11.2 Incomplete Land Tenure Upgrading in (3) settlements | Number (31) MLM incomplete land tenure projects for Carousel View, Motle and Syferskuil by June 2027June 2027 | Terms of reference, 3 appointment letters,3 inception reports, 3 status quo, 3 draft layout plans, proof of submission of applications to the Municipality, public participation proof, applications approval from the Municipality, final approved layout plans and closure reports | Target | Number |  | 31 | 4 | 9 | 9 | 9 | Local Economic Development and Planning | Director Local Economic Development |  |  |
|  |  |  |  |  | Capital | N/A |  | 480000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 11.3 | Output | 11.3 Delivery, supply, installation and commissioning of GIS | Number (12) of milestone for delivery, supply, installation and commissioning of GIS by June 2027 | Training session attendance register, training report, Report of Database maintenance and Database management | Target | Number | 5 | 12 | 3 | 3 | 3 | 3 | Local Economic Development and Planning | Director Local Economic Development |  |  |
|  |  |  |  |  | Capital | N/A |  | 1031000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 11.4 | Output | 11.4 Demarcation of sites | Number (9) of milestone for sites demarcation by June 2027 | Application for approval by the Municipality, final approved layout plans and closure report for Bahwaduba Traditional Council and Bakgatla-Ba-Mosetlha and Proof of application submission to the Municipality for Bakgatla Ba Mocha, approval of 2 applications by the Municipality, final layout plans approved by the Municipality and community resolution for Bakgatla Ba Mocha and closure report | Target | Number | 11 | 9 | 3 | 2 | 2 | 2 | Local Economic Development and Planning | Director Local Economic Development |  |  |
|  |  |  |  |  | Capital | N/A |  | 1270000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 11.5 | Output | 11.5 Land use and land development awareness workshops | Number (8) of land use awareness workshops conducted by June 2027 | Attendance registers and minutes | Target | Number | 4 | 8 | 2 | 2 | 2 | 2 | Local Economic Development and Planning | Director Local Economic Development |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 11.6 | Output | 13.7 Invasive Species Control Monitoring and Eradication Plan | Number (1) of Invasive Species Control Monitoring and Eradication Plan by June 2027 | Developed plan |  |  | 0 | 1 | 0 | 1 | 0 | 0 | Local Economic Development and Planning | Director Local Economic Development |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | 0 |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | 0 |  |  |  |  |
| Outcome |  |  | 12. Minimize environmental damage through temporary job creation |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 12.1 | Output | 12.1 Minimize the unemployment rate in Moretele through the EPWP initiatives | Number (390) of jobs created through Phepafatsa Moretele Project by June 2027 | Monthly reports and attendance registers | Target | Number | 390 | 390 | 390 | 390 | 390 | 390 | Local Economic Development and Planning | Director Local Economic Development |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Outcome |  |  | 13. Minimize the environmental damage through maximizing compliance to address environmental issues that have a direct and indirect impact on the natural environment |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 13.1 | Output | Construction and renovations of Environmental facilities | Number (3) of Environmental facilities constructed and renovated by June 2027 | Appointment and Completion certificate | Target | Number |  | 3 | 1 | 1 | 1 | 0 | Local Economic Development and Planning | Director Local Economic Development |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 13.2 | Output | 13.2 Cleaning of illegal dump hotspots | Number (26) Wards with weekly cleaning of illegal dump hotspots by June 2027 | Monthly signed cleaning of illegal dumps reports and pictures | Target | Number | 26 | 26 | 26 | 26 | 26 | 26 | Local Economic Development and Planning | Director Local Economic Development |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 13.3 | Output | 13.3 Wards with access to weekly waste removal services | Number (26) wards with access to weekly waste removal services by June 2027 | Monthly signed waste collection reports | Target | Number | 26 | 26 | 26 | 26 | 26 | 26 | Local Economic Development and Planning | Director Local Economic Development |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 13.4 | Output | 13.4 Wards with weekly skip bins maintenance | Number (26) Wards with weekly skip-bins maintenance by June 2027 | Monthly signed skip bins maintenance reports and pictures | Target | Number | 26 | 26 | 26 | 26 | 26 | 26 | Local Economic Development and Planning | Director Local Economic Development |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 13.5 | Output | 13.5 Waste Pickers Support | Number 4 of Waste Pickers supported by June 2027 | Appointment letter and completion certificate | Target | Number | 1 | 4 | 1 | 1 | 1 | 1 | Local Economic Development and Planning | Director Local Economic Development |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Outcome |  |  | 8. The economic potential and growth of the local economy through innovation and improved economic performance maximised |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 8.1 | Output | SMME Workshops | Number 4 of SMME workshop held by June 2027 | Attendance registers | Target | Number | 4 | 4 | 1 | 1 | 1 | 1 | Local Economic Development and Planning | Director Local Economic Development |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 8.2 | Output | 14.2 SMME Development and support | Number (13) of SMME projects developed and supported by June 2027 | Appointment and Completion certificate | Appointment and Completion certificate | Number | 5 | 13 | 3 | 4 | 3 | 3 | Local Economic Development and Planning | Director Local Economic Development |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 8.3 | Output | Agricultural Workshop | Number 4 of Agriculture workshop held by June 2027 | Attendance registers | Target | Number | 1 | 4 | 1 | 1 | 1 | 1 | Local Economic Development and Planning | Director Local Economic Development |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Outcome |  |  | 9. The economic potential and growth of Agriculture as a critical economic anchor in the local economy maximized |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 9.1 | Output | 9.1 Agriculture Development and support | Number 08 0f Agricultural Projects developed and supported by June 2027 | Appointment letter and completion certificate | Target | Number | 5 | 8 | 2 | 2 | 2 | 2 | Local Economic Development and Planning | Director Local Economic Development |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |

|  | Local Economic Development and Planning MORETELE LOCAL MUNICIPALITY SDBIP Annual Plan: 2025/2026 Page of Local Economic Development and Planning MORETELE LOCAL MUNICIPALITY SDBIP Annual Plan: 2025/2026 Page 1 of |
| --- | --- |

Moretele Local Municipality

_____________________________________________________

2026/2027

Draft SDBIP

OFFICE OF THE MAYOR

| National Outcome |  |  | National Outcome Responsive, Accountable, Effective And Efficient Local Government System |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NDP Chapters |  |  | Chapter 4: Economic Infrastructure Chapter 8: Human Settlements Chapter 12: Building Safer Communities Chapter 13: Building a capable state Chapter 14: Promoting accountability and fighting corruption |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Municipal Strategic Objectives |  |  | To promote and enhance effective governance systems for improved service delivery, To enhance and promote effective governance through credible communication systems, To promote and enhance integrated municipal planning, To promote Institutional development and transformation and good governance |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Goals |  |  | SG Governance: Efficient and effective Audit Management functions provided, Efficient and effective Risk Management functions provided, To ensure credible planning for improved outcomes,Achieve improved in institutional development, transformation, and good governance outcomes through implementation of Performance Management, Promote participatory development and local democracy through effective oversight |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Key Performance Area |  |  | Good Governance and Public Participation |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 15. Improved institutional development, transformation, and good governance outcomes through implementation of Performance Management |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 16. Efficient and effective Audit Management functions provided |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 17. Efficient and effective Risk Management functions provided |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 18. Promote participatory development and local democracy through effective oversight |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.11 | Output | 18.11 Promotion of Active Involvement, Good Governance and Public Participation | Percentage (100) of good government and public participation initiative held by June 2027 | Attendance Registers, Reports & Pictures | Target | Percentage | 100 | 100 | 100 | 100 | 100 | 100 | Office of the Mayor | Manager- Office of Mayor |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.11.1 | Activity | 18.11.1Promotion of Active Involvement, Good Governance and Public Participation | Number of (4) Imbizo’ s Held by June 2027 | Attendance Register & Pictures | Target | Number | 4 | 4 | 1 | 1 | 1 | 1 | Office of the Mayor | Manager- Office of Mayor |  |  |
|  |  |  |  |  | Capital | N/A |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 1.2 |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.11.2 | Activity | 18.11.2 Conduct Mayor Oversight visits | Number (4) of Mayors Oversights visits and Service Delivery Accelerated Programs (Netefatso Program) by June 2027 | Attendance Registers, Reports & Pictures | Target | Number | 4 | 4 | 1 | 1 | 1 | 1 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 100 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.11.3 | Activity | 18.11.3 Promotion of the rights of Senior Citizen by June 2027 | Number (2) of Senior Citizens support Programs by June 2027 | Attendance Registers, Reports & Pictures | Target | Number | 2 | 2 | 0 | 1 | 0 | 1 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 200 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.11.4 | Activity | 18.11.4 Provide vulnerable families with food parcels | Number (1040) of vulnerable households supported with food parcels by June 2027 | Beneficiary list per ward Q1-Q4 | Target | Number |  | 1040 | 260 | 260 | 260 | 260 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 2200000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.11.5 | Activity | 18.11.5 Promotion and support of destitute 02 families | Percentage (100) promotion and support of selected destitute 02 families by June 2027 | Pictures and confirmation of receipt by beneficiaries | Target | Percentage | 100 | 100 | 0 | 0 | 100 | 100 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 300 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.11.6 | Activity | 18.11.6 Hosting of local IGR Forums | Number (2) of Local IGR Forums held by June 2027 | Attendance Registers, Reports & Pictures | Target | Number |  | 2 | 0 | 1 | 0 | 1 | Office of the Mayor | Protocol & IGR Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 100 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.11.7 | Activity | 18.11.7 Promotion of National Calendar Events | Number (6) of Calendar Events held (1 x Mandela day Project, Festive Prayer Day, Women’s Day, 1 Pre-Easter, World Aids Day and Youth Day by June 2027 | Attendance Registers, Reports & Pictures | Target | Number | 6 | 6 | 2 | 2 | 1 | 1 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.5 | Output | 18.5 Implementation of IGR & Protocol Initiatives | Percentage (100) Implementation of IGR &amp; Protocol Initiatives by June 2027 | attendance registers or Pictures | Target | Percentage | 100 | 100 | 100 | 100 | 100 | 100 | Office of the Mayor | Protocol & IGR Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.5.1 | Activity | 18.5.1 Promotion of social cohesion and good governance | Number (3) Mayorâ€™s Stakeholders Outreach Engagements session held by June 2027 | Attendance Registers & Pictures | Target | Number |  | 3 | 0 | 1 | 1 | 1 | Office of the Mayor | Protocol & IGR Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 400000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.5.2 | Activity | 18.5.2 Strengthening the relationship between the Municipality and Magosi | Number (3) of Engagement Session with Magosi and Traditional Council held by June 2027 | Attendance Registers & Pictures | Target | Number | 3 | 3 | 0 | 1 | 1 | 1 | Office of the Mayor | Protocol & IGR Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 400000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.6 | Output | 18.6 Promotion and empowerment of Women | Percentage (100) of Women empowerment initiatives by June 2027 | Q1-Q4 Reports | Target | Percentage |  | 100 | 100 | 100 | 100 | 100 | Office of the Mayor | Manager- Office of Mayor |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.6.1 | Activity | 18.6.1 Hold Women’s Day Celebration | Number (1) Women Seminar held by June 2027 | Attendance registers and pictures | Target | Number | 1 | 1 | 1 | 0 | 0 | 0 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 200000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.6.2 | Activity | 18.6.2 Provide Support to Women Projects | Number (2) of Women Projects Supported by June 2027 | Attendance registers and pictures | Target | Number | 2 | 2 | 0 | 0 | 1 | 1 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 400000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.6.3 | Activity | 18.6.3 Hold Mothers â€˜s day Celebration | Number (1) of Motherâ€™s Day celebration by June 2027 | Attendance registers and pictures | Target | Number |  | 1 | 0 | 0 | 0 | 1 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 150000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.7 | Output | 18.7 Promotion and support of people living with disability | Percentage (100) of support of people living with disabilities by June 2027 | Q1-Q4 Reports | Target | Percentage |  | 100 | 100 | 100 | 100 | 100 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.7.1 | Activity | 18.7.1 Provide Disability Projects Support | Number (1) of Casual Day Celebration by June 2027 | Pictures and Attendance Register | Target | Number |  | 1 | 1 | 0 | 0 | 0 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 125000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.7.2 | Activity | 18.7.2 Engagement with People with Disability | Number (2) Disability Forum Meetings and Programs by June 2027 | Attendance registers and pictures | Target | Number |  | 2 | 0 | 1 | 0 | 1 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 125000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.7.3 | Activity | 18.7.3 Provide People with Disability Projects Support | Number (1) of Disability Projects Supported by June 2027 | Profile of projects, acknowledgement of receipt | Target | Number | 1 | 1 | 0 | 0 | 1 | 0 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 100000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.8 | Output | 18.8 Promotion of Social Cohesion through celebrating National Days | Percentage of Social Cohesion through celebrating National Days initiatives implemented by June 2027 | Attendance registers and pictures | Target | Percentage | 100 | 100 | 100 | 100 | 100 | 100 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.8.1 | Activity | 18.8.1 Promotion of Social Cohesion through celebrating National Days | Number (1) of Heritage Day Celebration September 2026 | Attendance registers and pictures | Target | Number | 1 | 1 | 1 | 0 | 0 | 0 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 200000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.8.2 | Activity | 18.8.2 Promotion of Social Cohesion through celebrating National Days | Number (1) of Women's Month Commemoration by June 2027 | Attendance registers and pictures | Target | Number | 1 | 1 | 1 | 0 | 0 | 0 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | Capex |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 200000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.8.3 | Activity | 18.8.3 Promotion of Social Cohesion through celebrating National Days | Number (1) of World Aids Days celebrated by July 2027 | Attendance registers and pictures | Target | Number | 1 | 1 | 0 | 1 | 0 | 0 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 15000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.8.4 | Activity | 18.8.4 Promotion of Social Cohesion through celebrating National Days | Number (1) of 16 Days of Activism of Abuse Against Women and Child Abuse celebrated by December 2026 | Attendance registers and pictures | Target | Number | 1 | 1 | 0 | 1 | 0 | 0 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.9 | Output | 18.9 Promotion and empowerment of the Youth | Percentage (100) of Youth empowerment initiatives by June 2027 | Q1-Q4 Reports | Target | Percentage | 100 | 100 | 100 | 100 | 100 | 100 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.9.1 | Activity | 18.9.1 Training and skills development of Youth | Number (20) of Youth to be trained and skilled by June 2027 | Q2-Q4 Attendance register & Reports | Target | Number | 20 | 20 | 0 | 20 | 20 | 20 | Office of the Mayor | Special Projects Manager \ |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 1300000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.9.2 | Activity | 18.9.2 Provide real-world application for classroom concepts for youth | Number (06) youth provided with work integrated learning program by June 2027 | Q1-Q4 Attendance register & Reports | Target | Number | 06 | 06 | 06 | 06 | 06 | 06 | Office of the Mayor | Special Projects Manager |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  | 300000 |  |  |  |  | Department | Person |  |  |
| 18.9.3 | Activity | Encourage participation in sports activities | Host (1) Mayors Cup Soccer & Netball Tournament by June 2027 | Pictures & Reports | Target | Number | 1 | 1 | 0 | 0 | 0 | 1 | Office of the Mayor | Special Projects Manager |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.9.4 | Activity | Youth Council Engagement Session | Host (1) Youth Council Engagement by June 2027 | Attendance register, report and pictures | Target | Percentage |  | 1 | 0 | 0 | 0 | 1 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 1 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 100000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.9.5 | Activity | Host Career Development Program | Number (1) Career Exhibition in partnership with Dept of Education) by June 2027 | Attendance registers and pictures | Target | Number |  | 1 | 0 | 0 | 1 | 0 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 200000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.9.6 | Activity | Provide Youth Projects Support | Number (2) of Youth Projects Supported by June 2027 | Profile of projects, acknowledgement of receipt | Target | Number |  | 2 | 0 | 0 | 1 | 1 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 400000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.9.7 | Activity | Conduct Back to School Campaign in partnership with Dept of Education | Number (1) of Back-to-School Campaigns conducted in partnership with Dept of Education (Distribution of 200 shoes, and 500 cares packs) by March 2027 | List of Schools and Pictures | Target | Number |  | 1 | 0 | 0 | 1 | 0 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 200000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.9.8 | Activity | Issuing, submission, capturing and awarding of 2027 academic year study grants | Percentage (100) completion of issuing, submitting and capturing of 2026 academic bursaries for 30 Youth by March 2027 | Registration letters, Report | Target | Number | 100 | 100 | 0 | 100 | 100 | 0 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 1200000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |

Moretele Local Municipality

_____________________________________________________

2026/2027

Draft SDBIP

OFFICE OF THE MUNICIPAL MANAGER

| National Outcome |  |  | National Outcome Responsive, Accountable, Effective And Efficient Local Government System |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NDP Chapters |  |  | Chapter 4: Economic Infrastructure Chapter 8: Human Settlements Chapter 12: Building Safer Communities Chapter 13: Building a capable state Chapter 14: Promoting accountability and fighting corruption |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Municipal Strategic Objectives |  |  | To promote and enhance effective governance systems for improved service delivery, To enhance and promote effective governance through credible communication systems, To promote and enhance integrated municipal planning, To promote Institutional development and transformation and good governance |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Goals |  |  | SG Governance: Efficient and effective Audit Management functions provided, Efficient and effective Risk Management functions provided, To ensure credible planning for improved outcomes,Achieve improved in institutional development, transformation, and good governance outcomes through implementation of Performance Management, Promote participatory development and local democracy through effective oversight |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Key Performance Area |  |  | Good Governance and Public Participation |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 15. Improved institutional development, transformation, and good governance outcomes through implementation of Performance Management |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 15.1 | Output | 15.1 Annual Report consistent with Circular 63 (National Treasury) prepared | Number (1) of 2025/2026 Annual Report approved by January 2027 | Q3 Report | Target | Number |  | 1 | 0 | 0 | 1 | 0 | Office of the Municipal Manager | PMS Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 15.1.1 | Activity | 15.1.1 2026 /2027 Performance agreements finalised and signed by Senior Managers | Number (6) of signed performance agreements for Senior Managers by September 2026 | Q1: Copies of signed Performance Agreements | Target | Number | 6 | 6 | 6 | 0 | 0 | 0 | Office of the Municipal Manager | PMS Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 15.1.10 | Activity | 15.1.10 PMS Strategic session | Number (1) of IDP Strategic sessions held by March 2027 | Q3 A attendance register | Target | Number | 1 | 1 | 0 | 0 | 1 | 0 | Office of the Municipal Manager | PMS Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 15.1.2 | Activity | 15.1.2 Preparation and approval of the Annual Report | Percentage (100) completion of the preparation and approval of 2024/2025 Annual Report approved by January 2027 | Q3: Copy of Annual Report | Target | Percentage | 100 | 100 | 0 | 0 | 100 | 0 | Office of the Municipal Manager | PMS Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 15.1.3 | Activity | 15.1.3 Implement initiatives performance management organisational wide through Performance Management System | Percentage (100) of Individual performance management cascading initiatives through performance management System implemented by June 2027 | Q4: Quarterly Reports | Target | Percentage | 100 | 100 | 0 | 0 | 0 | 100 | Office of the Municipal Manager | PMS Manager |  |  |
|  |  |  |  |  | Capital | N/A |  | 2.2 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 15.1.4 | Activity | 15.1.4 Conduct quarterly performance reviews for all section 56/57 employees | Number (4) of individual (section 54/56 managers) performance reviews conducted by June 2027 | Q3&Q4: Performance Review Report | Target | Number | 4 | 4 | 1 | 1 | 1 | 1 | Office of the Municipal Manager | PMS Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 15.1.5 | Activity | 15.1.5 Conduct PMS policy review | Percentage (100) completion of PMS policy review and approval by June 2027 | Q4: Council Approved Copy of the policy | Target | Percentage | 100 | 100 | 0 | 0 | 0 | 100 | Office of the Municipal Manager | PMS Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 15.1.6 | Activity | 15.1.6 Preparation and approval of the SDBIP | Percentage (100) completion of the preparation and approval of the 2025/2026 signed by the Mayor by June 2027 | Q4: Copy of the SDBIP | Target | Percentage | 100 | 100 | 0 | 0 | 0 | 100 | Office of the Municipal Manager | PMS Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 15.1.7 | Activity | 15.1.7 Prepare consolidated quarterly performance report | Number (4) of quarterly performance reports tabled and approved by June 2027 | Q1-Q4: Council Resolutions | Target | Number | 4 | 4 | 1 | 1 | 1 | 1 | Office of the Municipal Manager | PMS Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 15.1.8 | Activity | 15.1.8 IDP REP Forum Capacity Building | Number (1) of IDP Capacity Building by December 2026 | Q2 Attendance register | Target | Number | 1 | 1 | 0 | 1 | 0 | 0 | Office of the Municipal Manager | PMS Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 15.1.9 | Activity | 15.1.9 IDP/PMS Operations equipment procured | Number (1) Projector and Sound system procured by July 2027 | Q1 Delivery note | Target | Number | 1 | 1 | 1 | 0 | 0 | 0 | Office of the Municipal Manager | PMS Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Outcome |  |  | 16. Efficient and effective Audit Management functions provided |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 16.1 | Output | 16.1 Risk based internal Audit Plan developed and approved | Number of Internal Audit Plans developed and approved by September 2026 | Q1: Approved Internal Audit Plan by Audit Committee, minutes of the audit committee | Target | Number | 1 | 1 | 1 | 0 | 0 | 0 | Office of the Municipal Manager | Internal Audit Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 16.1.1 | Activity | 16.1.2 Preparation and Approval of the Internal Audit Plan | Number of Internal Audit Plans prepared and approved by September 2026 | Q1: Approved Internal Audit Plan by Audit Committee and minutes of the audit committee | Target | Number | 1 | 1 | 1 | 0 | 0 | 0 | Office of the Municipal Manager | Internal Audit Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 16.2 | Output | 16.2 Implementation of the approved Internal audit plan | Number (4) of Internal audit progress reports submitted to Audit Committee by June 2027 | Q1-Q4: internal audit progress reports to audit committee and minutes of the audit committee | Target | Number | 4 | 4 | 1 | 1 | 1 | 1 | Office of the Municipal Manager | Internal Audit Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 16.2.1 | Activity | 16.2.1 Implementation of the approved Internal audit plan | Number (4) of Internal audit progress reports submitted to Audit Committee by June 2027 | Q1-Q4: internal audit progress reports to audit committee and minutes of the audit committee | Target | Number | 4 | 4 | 1 | 1 | 1 | 1 | Office of the Municipal Manager | Internal Audit Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Outcome |  |  | 17. Efficient and effective Risk Management functions provided |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 17.1 | Output | 17.1 Fraud Management Plan developed and approved | Number (1) Fraud Management Plan developed by September 2026 | Approved Fraud Management Plan | Target | Number | 1 | 1 | 1 | 0 | 0 | 0 | Office of the Municipal Manager | Risk Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 17.1.1 | Activity | 17.1.1 Hold Anti-fraud and Corruption Awareness Training and Workshop | Number (1) of Anti-fraud and Corruption Awareness Training and Workshops held by December2026 | Presentations and attendance register | Target | Number | 1 | 1 | 0 | 1 | 0 | 0 | Office of the Municipal Manager | Risk Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 17.2 | Output | 17.2 Risk Management Plan developed and approved | Number (1) of Risk Management Plan developed by September 2026 | Approved Risk Management Plan | Target | Number | 1 | 1 | 1 | 0 | 0 | 0 | Office of the Municipal Manager | Risk Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 17.2.1 | Activity | 17.2.1 Hold Risk Management Committee meetings | Number (4) of Risk Management Committee meetings held by June 2027 | Minutes of the RMC meeting and attendance register | Target | Number | 4 | 4 | 1 | 1 | 1 | 1 | Office of the Municipal Manager | Risk Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Outcome |  |  | 18. Promote participatory development and local democracy through effective oversight |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.1 | Output | 18.1 IDP reviewed in accordance with approved Process Plan | Percentage (100) of 2027/2028 IDP Reviewed and approved by June 2027 | Q4: Copy of 2027/2028 IDP | Target | Percentage | 100 | 100 | 0 | 0 | 0 | 100 | Office of the Municipal Manager | IDP Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.1.1 | Activity | 18.1.1 Develop a credible IDP Process plan | Number (1) of 2027-2028 credible IDP Process plans developed by September 2026 | Copy of a 2027-2028 process plan | Target | Number | 1 | 1 | 1 | 0 | 0 | 0 | Office of the Municipal Manager | IDP Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.1.2 | Activity | 18.1.2 Hold 2026/2027 IDP Ward based consultations | Number (26) of 2027-2028 IDP Ward based consultations held by December 2026 | 2027-2028 Ward Based consultation report | Target | Number | 26 | 26 | 0 | 26 | 0 | 0 | Office of the Municipal Manager | IDP Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | Opex |  | 520000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.1.3 | Activity | 18.1.3 Hold IDP REP Forum meetings | Number (4) of IDP REP Forum meetings held by June 2027 | Minutes and attendance register | Target | Number | 4 | 4 | 1 | 1 | 1 | 1 | Office of the Municipal Manager | IDP Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | Opex |  | 100000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.1.4 | Activity | 18.1.4 Capacitate IDP REP Forums | Number (1) of IDP REP Forums capacitated by December 2026. | Report and Attendance register | Target | Number | 1 | 1 | 0 | 1 | 0 | 0 | Office of the Municipal Manager | IDP Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | Opex |  | 200000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.2 | Output | 18.2 Communication Strategy developed and implemented | Number (1) of Communication Strategy developed and implemented to improve communication and its credibility by June 2027 | Copy of communication strategy | Target | Number |  | 1 | 0 | 0 | 1 | 0 | Office of the Municipal Manager | Communications Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 100000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.2.1 | Activity | 18.2.1 Ensure professional coordination of municipal events | Percentage (100) of professional coordination of municipal events by June 2027 | Attendance register | Target | Number | 100 | 100 | 100 | 100 | 100 | 100 | Office of the Municipal Manager | Communications Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | Opex |  | 50000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.2.2 | Activity | 18.2.2 Develop Cooperate Identity Manuals | Number (1) of Cooperate Identity Manuals developed by December 2026 | Cooperate identity manual | Target | Percentage |  | 1 | 0 | 1 | 0 | 0 | Office of the Municipal Manager | Communications Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | Opex |  | 200000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.2.3 | Activity | 18.2.3 Develop Communications and Social Media Policies | Number (3) of Communications and Social Media Policies developed by June 2027 | Copies of media, communications, and social media policies | Target | Number |  | 3 | 0 | 1 | 1 | 1 | Office of the Municipal Manager | Communications Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.2.4 | Activity | 18.2.4 Procure Diaries, Promotion Materials, Digital billboards, five-year magazine and Calendars | Number (5) of Diaries, Promotion Materials, Digital billboards, five-year magazine and Calendars procured by June 2027 | Proof of purchase | Target | Number |  | 5 | 1 | 3 | 1 | 0 | Office of the Municipal Manager | Communications Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | Opex |  | 500 000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.2.5 | Activity | 18.2.5 Hold Media Communications and Coverage Promotions | Number (4) of Media Communications and campaigns held by June 2027 | Attendance register | Target | Number |  | 4 | 1 | 1 | 1 | 1 | Office of the Municipal Manager | Communications Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | Opex |  | 100000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.4 | Output | 18.4 Communities and interested stakeholders engaged on the 2024/2025 Annual Report | Percentage (100) of 2024/2025 Annual Oversight Report approved by June 2027 | Copy of an oversight report | Target | Percentage | 100 | 100 | 0 | 0 | 0 | 100 | Office of the Municipal Manager | MPAC Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.4.1 | Activity | 18.4.1 Workshop for all the members of MPAC on the role and responsibilities of MPAC. | Number (1) Workshop for all members of MPAC on the strengthening of capacity of MPAC by June 2027 | Q:1- Q3 Invitation, Attendance registers. | Target | Number | 1 | 3 | 1 | 1 | 1 | 0 | Office of the Municipal Manager | MPAC Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 180000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.4.2 | Activity | 18.4.2 Consolidation of the draft 2024/2025 Oversight Report by MPAC committee by end of March 2026 | Percentage (100) of engagements, consolidation, preparation on the draft Annual report by March 2027 | Invitations, Attendance registers and draft oversight report. | Target | Percentage | 100 | 100 | 0 | 0 | 100 | 0 | Office of the Municipal Manager | MPAC Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 240000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.4.3 | Activity | 18.4.3 Printing of the 2024/2025 Annual Oversight Report | Percentage (100) completion of the Printing of the 2024/2025 Annual Oversight Report by March 2027 | Final printed Oversight report adopted by council. | Target | Percentage | 100 | 100 | 0 | 0 | 100 | 0 | Office of the Municipal Manager | MPAC Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 200 000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.4.4 | Activity | 18.4.4 Engagement on the 2024/2025 Annual Report with community members by end of March 2026 | Number (4) of UIFW reports considered by MPAC by June 2027 | MPAC resolutions and reports to council | Target | Number | 1 | 4 | 1 | 1 | 1 | 1 | Office of the Municipal Manager | MPAC Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 160000 | 0 | 0 | 0 | 0 |  |  |  |  |

| National Outcome |  |  | National Outcome Responsive, Accountable, Effective And Efficient Local Government System |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NDP Chapters |  |  | Chapter 4: Economic Infrastructure Chapter 8: Human Settlements Chapter 12: Building Safer Communities Chapter 13: Building a capable state Chapter 14: Promoting accountability and fighting corruption |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Municipal Strategic Objectives |  |  | To promote and enhance professional institutional development and transformation through improved human resources systems and technology |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Goals |  |  | SG HR & CS: To promote and enhance professional institutional development and transformation through improved human resources systems and technology |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Key Performance Area |  |  | Institutional Development and Transformation |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 14. Professional institutional development and transformation through improved human resources systems and technology promoted and enhanced |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.10.5 | Activity | 14.10.5 Professional institutional development and transformation through provision of legal advice and guidance to the Municipality | Percentage (100) implementation of legal advice and guidance provided by June 2027 | Q3-Q4: Reports | Target | Percentage |  | 100 | 0 | 0 | 100 | 100 | Office of the Municipal Manager | Legal Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.10.6 | Activity | 14.10.6 Professional institutional development and transformation through conducting of legal research to identify potential risk associated with Municipality | Percentage (100) of legal research conducted by June 2027 | Q3-Q4: reports | Target | Percentage |  | 100 | 0 | 0 | 100 | 100 | Office of the Municipal Manager | Legal Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.10.7 | Activity | 14.10.7 Professional institutional development and transformation through engagement with stakeholders to develop strategies and policies to ensure compliance with law | Percentage (100 engagement with stakeholders by June 2027 | Q3-Q4 Reports | Target | Percentage |  | 100 | 0 | 0 | 100 | 100 | Office of the Municipal Manager | Legal Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.10.8 | Activity | 14.10.8 Professional institutional development and transformation through effective management of litigation cases | Percentage (100 of litigation cases managed by June 2027 | Q3-Q4 Report | Target | Percentage |  | 100 | 0 | 0 | 100 | 100 | Office of the Municipal Manager | Legal Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.10.9 | Activity | 14.10.9 Professional institutional development and transformation through working with internal departments to develop measures that align business practices with legal requirements | Percentage (100) of engagements with internal departments by June 2027 | Q3-Q4 Reports | Target | Percentage |  | 100 | 0 | 0 | 100 | 100 | Office of the Municipal Manager | Legal Manager |  |  |

Moretele Local Municipality

_____________________________________________________

2026/2027

Draft SDBIP

OFFICE OF THE CHIEFWHIP

| National Outcome |  |  | National Outcome Responsive, Accountable, Effective And Efficient Local Government System |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NDP Chapters |  |  | Chapter 4: Economic Infrastructure Chapter 8: Human Settlements Chapter 12: Building Safer Communities Chapter 13: Building a capable state Chapter 14: Promoting accountability and fighting corruption |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Municipal Strategic Objectives |  |  | To promote and enhance effective governance systems for improved service delivery, To enhance and promote effective governance through credible communication systems, To promote and enhance integrated municipal planning, To promote Institutional development and transformation and good governance |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Goals |  |  | SG Governance: Efficient and effective Audit Management functions provided, Efficient and effective Risk Management functions provided, To ensure credible planning for improved outcomes,Achieve improved in institutional development, transformation, and good governance outcomes through implementation of Performance Management, Promote participatory development and local democracy through effective oversight |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Key Performance Area |  |  | Good Governance and Public Participation |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 15. Improved institutional development, transformation, and good governance outcomes through implementation of Performance Management |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 16. Efficient and effective Audit Management functions provided |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 17. Efficient and effective Risk Management functions provided |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 18. Promote participatory development and local democracy through effective oversight |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.10 | Output | 18.10 Implementation of Whipery Initiatives | Percentage (100) Implementation of Whipery Initiatives by June 2027 | Report | Target | Percentage | 100 | 100 | 100 | 100 | 100 | 100 | Office of the Single Whip | Manager - Office of the Single Whip |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.10.1 | Activity | 18.10.1 Hold Information Sharing Session between Whips of all political affiliates and portfolio whips. | Number (4) of Whipery Forum held and 04 Portfolio Whip by June 2027 | Attendance Register and Minutes | Target | Percentage | 3 | 4 | 1 | 1 | 1 | 1 | Office of the Single Whip | Manager - Office of the Single Whip |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 30000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.10.2 | Activity | 18.10.2 Hold Direct Engagements with Stakeholders concerning good governance and service delivery issues | Number (4) of Governance Forum held by June 2027 | Attendance Register and Reports | Target | Number | 4 | 4 | 1 | 1 | 1 | 1 | Office of the Single Whip | Manager - Office of the Single Whip |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 250000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.10.3 | Activity | 18.10.3 Hold Political engagements in order to make our institution politically stable and avoid unnecessary tension within our institution. | Number (4) of Political Caucus Management (Multi-Party Caucus) held by June 2027 | Attendance Register and Reports | Target | Number | 4 | 4 | 1 | 1 | 1 | 1 | Office of the Single Whip | Manager - Office of the Single Whip |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 30000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.10.4 | Activity | 18.10.4 Capacitate Councilors as Custodian of the society in the implementation of service delivery. | Number (4) of Council Caucuses held by June 2027 | Attendance Register and Reports | Target | Number | 4 | 4 | 1 | 1 | 1 | 1 | Office of the Single Whip | Manager - Office of the Single Whip |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 40000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.10.5 | Activity | 18.10.5 Voter registration drives, hosting candidate forums or debates, and conducting outreach efforts to inform and mobilize the electorate Organized | Number (4) of Letsema Programmes by June 2027 | Programmes and Attendance Register | Target | Number | 4 | 4 | 1 | 1 | 1 | 1 | Office of the Single Whip | Manager - Office of the Single Whip |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 220000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.10.6 | Activity | 18.10.6 Bringing together representatives from different political parties, ensure they caucuses can work collaboratively in uniform approach | Number (130) of Multi-party Uniforms purchased by June 2027 | Delivery note, collection receipt register of Cllrs and pictures | Target | Number |  | 130 | 0 | 0 | 0 | 130 | Office of the Single Whip | Manager - Office of the Single Whip |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 150000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.10.7 | Activity | 18.10.7 Hold an induction workshops | Number (2) of Multiparty and whipery induction workshops held by June 2027 | Attendance Register and reports | Target | Number | 4 | 2 | 0 | 1 | 1 | 0 | Office of the Single Whip | Manager - Office of the Single Whip |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 3000000 | 0 | 0 | 0 | 0 |  |  |  |  |

|  | Office of the Single Whip MORETELE LOCAL MUNICIPALITY SDBIP Annual Plan: 2025/2026 Page of Office of the Single Whip MORETELE LOCAL MUNICIPALITY SDBIP Annual Plan: 2025/2026 Page 1 of |
| --- | --- |

Moretele Local Municipality

_____________________________________________________

2026/2027

DRAFT SDBIP

OFFICE OF THE SPEAKER

| National Outcome |  |  | National Outcome Responsive, Accountable, Effective And Efficient Local Government System |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NDP Chapters |  |  | Chapter 4: Economic Infrastructure Chapter 8: Human Settlements Chapter 12: Building Safer Communities Chapter 13: Building a capable state Chapter 14: Promoting accountability and fighting corruption |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Municipal Strategic Objectives |  |  | To promote and enhance effective governance systems for improved service delivery, To enhance and promote effective governance through credible communication systems, To promote and enhance integrated municipal planning, To promote Institutional development and transformation and good governance |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Goals |  |  | SG Governance: Efficient and effective Audit Management functions provided, Efficient and effective Risk Management functions provided, To ensure credible planning for improved outcomes,Achieve improved in institutional development, transformation, and good governance outcomes through implementation of Performance Management, Promote participatory development and local democracy through effective oversight |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Key Performance Area |  |  | Good Governance and Public Participation |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 15. Improved institutional development, transformation, and good governance outcomes through implementation of Performance Management |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 16. Efficient and effective Audit Management functions provided |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 17. Efficient and effective Risk Management functions provided |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 18. Promote participatory development and local democracy through effective oversight |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.3 | Output | 18.3 Participatory development and local democracy promoted through effective ward committee system | Percentage (100) of promotions in participatory development and effective award system by June 2027 | Q1-Q4: Copies of Ward Committee meeting attendance registers | Target | Percentage | 100 | 100 | 100 | 100 | 100 | 100 | Office of the Speaker | Manager- Office of the Speaker |  |  |
|  |  |  |  |  | Capital | Capex |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 150000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.3.1 | Activity | 18.3.1 Conduct Ward Committee meetings | Number (20) of Ward Committee meetings held by June 2027 | Q1-Q4: Copies of Ward Committee meeting attendance registers | Target | Number | 20 | 20 | 5 | 5 | 5 | 5 | Office of the Speaker | Manager- Office of the Speaker |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 4149600 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.3.2 | Activity | 18.3.2 Award Councillor's Bursary | Number (1) of Councillor's Bursary Awarded by March 2027 | Q1; list of Registered Councilor's | Target | Number | 1 | 1 | 0 | 0 | 1 | 0 | Office of the Speaker | Manager- Office of the Speaker |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 500000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.3.3 | Activity | 18.3.3 Purchase Ward Committee Uniforms and Identifications | Number (260) of Ward Committee Uniforms and Identifications purchased by March 2027 | Q2: Invoices and Receipts | Target | Number | 260 | 260 | 0 | 0 | 260 | 0 | Office of the Speaker | Manager- Office of the Speaker |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 230800 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.3.4 | Activity | 18.3.4 Hold Ward Councilors and Secretaries Forum | Number (4) of Ward Councilors and Secretaries Forum held by June 2027 | Q1-Q4: Copy of Attendance Registers | Target | Number | 4 | 4 | 1 | 1 | 1 | 1 | Office of the Speaker | Manager- Office of the Speaker |  |  |
|  |  |  |  |  | Capital | N/A |  | 50000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.3.5 | Activity | 18.3.5 Hold Ordinary Council meetings | Number (4) of Ordinary Council meetings held by June 2027 | Q1-Q4: Copy of Attendance Registers and Invites | Target | Number | 4 | 4 | 1 | 1 | 1 | 1 | Office of the Speaker | Manager- Office of the Speaker |  |  |
|  |  |  |  |  | Capital | N/A |  | 250000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |

| 9.Consolidated planned Indicators | 9.Consolidated planned Indicators |
| --- | --- |

9.Consolidated planned Indicators

| Directorate / Unit | Planned Annual indicators |
| --- | --- |
| Infrastructure Development Services | 15 |
| Community Development services | 11 |
| Budget and Treasury Office | 25 |
| Human Resources and Corporate Services | 18 |
| LED and Planning | 17 |
| Strategic Services |  |
| - IDP/PMS | 2 |
| - Communications | 1 |
| - Speaker’s Office | 6 |
| - Special Projects (Mayor’s Office) | 7 |
| - Internal Audit | 2 |
| - Risk | 2 |
| - Chief Whip | 8 |
| - MPAC | 1 |
| Totals | 115 |

10. Implementation, Monitoring and Reporting of the 2026/2027 SDBIP

- Directors are to submit monthly reports to the Municipal Manager by Directors, the Municipal Manager submits to the mayor in accordance with section 71 (g) (ii) of the MFMA

- The Mayor or the Budget and Treasury Chairperson as delegated convenes quarterly Budget Steering Committee

- The mayor submits quarterly reports to Council in accordance with section 52 (d) of MFMA indicating progress in the implementation of the SDBIP

- The revision of the SDBIP may be done as per section 54 (1) (c) of the MFMA as part of the adjustment budget.

- Section 121 of the MFMA requires a municipality to account in a form of an assessment of performance against the measurable objectives set in the IDP and SDBIP.

| Directorate: | Office of the Municipal Manager |
| --- | --- |
| Municipal Manager: | Name: |

11. Projections of each month of revenue to be collected by source. Operational and Capital expenditure by Vote (Attached as Annexure A)