1

Moretele Local Municipality

_____________________________________________________

2025/2026

Adjusted Service Delivery and Budget Implementation Plan

(ADJUSTED SDBIP )

___________________________________

1

Revision Control 2025/26 Planning

February  2026    ____________________________________________________________________________________________________

____________________________________________________________________________________________________

Strategic Services

IDP/PMS Unit

Enquiries:012716 1321 / 1433

nyakale.lale@moretele.gov.za

| Item | Topic | Page Number |
| --- | --- | --- |
| 1. | Mayor Foreword and Overview by Accounting Officer | 5 |
| 2. | SDBIP Approval | 7 |
| 3. | Key Performance Areas | 8 |
| 4. | SDBIP Contents | 9 |
|  | 4.1 Budget processes and related matters | 9 |
|  | 4.2 Components of the SDBIP | 10 |
| 5. | Municipal vision and Demographics | 11 |
|  | 5.1 Municipal Vision | 11 |
|  | 5.2 Demographics | 12 |
| 6. | Municipal Mandate, Powers, and Functions | 21 |
|  | 6.1 Municipal Mandate | 21 |
|  | 6.2 Powers and Functions | 22 |
| 7. | Financial Plan | 23 |
| 8 | Service Delivery, Indicators and Targets | 56 |
|  | 8.1 Budget and Treasury | 58 |
|  | 8.2 Community Development Services | 61 |

|  | 8.3 Human Resources | 64 |
| --- | --- | --- |
|  | 8.4 Infrastructure Development Services | 68 |
|  | 8.5Local Economic Development | 71 |
|  | 8.6 Good Governance | 75 |
| 9 | Consolidated Planned Indicators | 94 |
| 10 | Implementing, Monitoring and Reporting of the 2025-2026 SDBIP | 94 |
| 11 | Projections of each month of revenue to be collected by source. Operational and Capital expenditure by Vote (Attached as Annexure A) | 95 |

- Mayor Foreword and Overview by the Accounting Officer

  - Overview by the Accounting officer

- Final SDBIP Approval

3. Key Performance Areas

| Key Performance Area | Directorates / Units | Strategic Objective |
| --- | --- | --- |
| Basic Services and Infrastructure Development | Infrastructure Development Services | To ensure access to sustainable services and infrastructure to all households |
|  | Community Development Services | To ensure access to public amenities and to promote community safety, development and sustainable livelihoods |
| Financial Management and Viability | Budget and Treasury Office | To promote and ensure prudent financial management to enhance institutional viability and access to basic services |
| Institutional Development and Transformation | Human Resources and Corporate Services | To promote and enhance professional institutional development and transformation through improved human resources systems and technology |
| Local Economic Development | Local Economic Development and Planning | To promote and enhance economic development, growth and economic access |
| Good Governance and Public Participation | Strategic Services and Governance - Internal Audit - Communications - IDP/PMS - Special Projects - Public Participation - MPAC | - To promote and enhance effective governance systems for improved service delivery - To enhance and promote effective governance through credible communication systems - To promote and enhance integrated municipal planning - To promote Institutional development, transformation and good governance |

- SDBIP Context

The Municipal Finance Management Act (MFMA) No. 56 of 2003 defines the “service delivery and budget implementation plan” as the detailed plan approved by the mayor of the municipality in terms of Section 53 (1) (c) (ii) for implementing the municipality’s delivery of municipal services and its annual budget and which must include the following: -

a) Projections of each month of-

      - revenue to be collected, by source; and

      - operational and capital expenditure, by vote.

    - Service delivery targets and performance indicators for each quarter; and

    - Any other matters that may be prescribed and includes any revisions of such plan by the mayor in terms of section 54(1)(c).

In terms of Section 53 (i) (c)(ii) of the MFMA, the SDBIP must be approved by the mayor of a municipality within 28 days of the approval of the budget

  - Budget processes and related matters

Section 53 (4) requires that the mayor of a municipality must—

    - provide general political guidance over the budget process and the priorities that must guide the preparation of a budget.

    - co-ordinate the annual revision of the integrated development plan in terms of section 34 of the Municipal Systems Act and the preparation of the annual budget, and determine how the integrated development plan is to be considered or revised for the purposes of the budget; and (c) take all reasonable steps to ensure—

      - that the municipality approves its annual budget before the start of the budget year.

      - that the municipality’s service delivery and budget implementation plan is approved by the mayor within 28 days after the approval of the budget: and

      - that the annual performance agreements as required in terms of section 57(1)(b) of the Municipal Systems Act for the municipal manager and all senior managers-

(aa) comply with this Act to promote sound financial management.

(bb)are linked to the measurable performance objectives approved with the budget and to the service delivery and budget implementation plan; and

(cc) are concluded in accordance with section 57(2) of the Municipal Systems Act

  - Components of the SDBIP

Municipal Finance Management Act Circular 13 provides that the Service Delivery and Budget Implementation Plan should comprise of the following:

Component Description

| Monthly Projections of Revenue to be Collected for each Source | o | The Municipality must institute measures to achieve its monthly revenue targets for each source These measures will enable the Municipality to assess its cash flow monthly with a view to undertaking contingency plans should there be a cash flow shortage or other challenges and positives |
| --- | --- | --- |
| Monthly Projections of Expenditure and Revenue for each Vote | o | The monthly projection of revenue and expenditure per vote relate to the cash paid and reconciles with the cash flow statement adopted with the budget |
|  | o | The focus under this component is a monthly projection per vote in addition to projections by source |
| Quarterly Projections of Service Delivery Targets and Performance Indicators for each Vote | o o o | This component of the SDBIP requires non-financial measurable performance objectives in the form of service delivery targets and other indicators of performance The focus is on outputs rather than inputs Service delivery targets relate to the level and standard of service being provided to the community and include the addressing of backlogs in basic services |

- Municipality’s Vision and Demographics

  - Municipal Vision

Vision

A Developing Moretele for Growth and Prosperity for All

Mission

To provide and enhance equitable, cost effective, efficient and quality

service delivery and exploit resources for sustainable development,

growth and prosperity for all

Values

Service to stakeholders

Excellence

Transparency

Responsiveness

Value for diversity

Value for partnerships

Ethical standards

  - Demographics (Summary)

Population

South African Population as at census 2022 is at 62,027,503 and Northwest population is at 3,804,548 , Bojanala is at 1,624,428 and Moretele at 186 499.

| Male | Female |
| --- | --- |
| 85353 | 101146 |
| Total | 186499 |

| Local | age | Male | Female | Male(%) | Female(%) |
| --- | --- | --- | --- | --- | --- |
| NW371 : Moretele | 0-4 | 8266 | 8686 | -4.4% | 4.7% |
| NW371 : Moretele | 5-9 | 11035 | 11243 | -5.9% | 6.0% |
| NW371 : Moretele | 10-14 | 10492 | 9945 | -5.6% | 5.3% |
| NW371 : Moretele | 15-19 | 9939 | 9221 | -5.3% | 4.9% |
| NW371 : Moretele | 20-24 | 3767 | 5068 | -2.0% | 2.7% |
| NW371 : Moretele | 25-29 | 3994 | 6160 | -2.1% | 3.3% |
| NW371 : Moretele | 30-34 | 5763 | 7300 | -3.1% | 3.9% |
| NW371 : Moretele | 35-39 | 6581 | 7267 | -3.5% | 3.9% |
| NW371 : Moretele | 40-44 | 3945 | 5044 | -2.1% | 2.7% |
| NW371 : Moretele | 45-49 | 1789 | 3577 | -1.0% | 1.9% |
| NW371 : Moretele | 50-54 | 1770 | 4313 | -0.9% | 2.3% |
| NW371 : Moretele | 55-59 | 3141 | 5166 | -1.7% | 2.8% |
| NW371 : Moretele | 60-64 | 5048 | 4731 | -2.7% | 2.5% |
| NW371 : Moretele | 65-69 | 4034 | 4243 | -2.2% | 2.3% |
| NW371 : Moretele | 70-74 | 2868 | 3361 | -1.5% | 1.8% |
| NW371 : Moretele | 75+ | 2922 | 5823 | -1.6% | 3.1% |
|  | Total | 85353 | 101146 |  |  |
|  | Grand total |  | 186499 |  |  |

| Functional age groups | Number |
| --- | --- |
| 0-14 (children) | 59667 |
| 15 -34 (youth) | 51212 |
| 34-64 (adults) | 52371 |
| Elderly ( 65+) | 23250 |

| Coloured | 297 | 259 | 556 |
| --- | --- | --- | --- |
| Indian or Asian | 69 | 23 | 91 |
| White | 202 | 127 | 330 |
| Other | 169 | 39 | 208 |
| Unspecified | 6 | 3 | 9 |

| Table 2.3: Labour force characteristics by province and metro |  |
| --- | --- |
|  | Oct-Dec 2024 |
|  | Thousand |
| Northwest |  |
| Population 15-64 yrs | 2,817 |
| Labour Force | 1,593 |
| Employed | 935 |
| Unemployed | 658 |
| Not economically active | 1,224 |
| Discouraged work-seekers | 339 |
| Other | 885 |
| Rates (%) |  |
| Unemployment rate | 41.3 |
| Employed / population ratio (Absorption) | 33.2 |
| Labour force participation rate | 56.6 |

| Home/community play group | 1355 |  |  |
| --- | --- | --- | --- |
| Other (Specify) | 83 |  |  |
| None | 9344 |  |  |
| Space-Time Research |  |  |  |
| Census 2022 Version 1.1 |  |  |  |
| Table 1 |  |  |  |
| Highest level of education |  |  |  |
| for Person weight, 20 +, Moretele Local Municipality |  |  |  |
| No schooling | 8747 |  |  |
| Some primary | 12848 |  |  |
| Completed primary | 5216 |  |  |
| Some secondary | 43470 |  |  |
| Completed Grade 12/ Standard 10 | 49903 |  |  |
| Higher education | 5839 |  |  |
| Other | 742 |  |  |

| Formal dwelling | 88.4 |  |
| --- | --- | --- |
| Informal dwelling/ | 7.2 |  |
| Other | 0.4 |  |
| Not applicable | 3.5 |  |
| Caravan/tent | 0.0 |  |
| Traditional dwelling/hut/structure made of traditional materials | 0.4 |  |
| Total | 100.0 |  |

| Census 2022 |  |  |
| --- | --- | --- |
| Summation Options and Refuse or Rubbish |  |  |
| for Moretele Local Municipality |  |  |
|  | Percentage (%) |  |
| Own refuse dump | 46.0 |  |
| Removed by local authority/private company/community members at least once a week | 33.8 |  |
| Communal container/central collection point | 11.4 |  |
| Dump or leave rubbish anywhere (no rubbish disposal) | 4.9 |  |
| Removed by local authority/private company/community members less often | 1.9 |  |
| Communal refuse dump | 0.8 |  |
| Other | 1.1 |  |
| Total | 100.0 |  |

| Functional age groups | Number |
| --- | --- |
| 0-14 (children) | 59667 |
| 15 -34 (youth) | 51212 |
| 34-64 (adults) | 52371 |
| Elderly ( 65+) | 23250 |
| Sex ratio |  |
| 0.84 |  |

| Mid-year population estimates - 2024 |  |  |
| --- | --- | --- |
| Population by sex: |  |  |
| Male | Female |  |
| 85353 | 101146 |  |
| Total | 186499 |  |

Access to electricity lighting

Number of Households

Average household in size in a district

Internet Services

The figure below indicates 95% have no access to internet services.

Development Implications

The figure clearly points to the fact that there is a strong need for action to maximize internet access throughout the municipal area. The municipality should in partnership with other sectors explore available means of improving internet and cell phone network access.

Tenure Status

The figure below indicates that 72% of the households own and fully paid off and with about 23, 7% households occupied rent free. It should be noted that very few areas have been proclaimed and there is a larger percentage of households found in traditional council’s areas, which means that security of tenure is not guaranteed for 72% as indicated.

Census 2022

5.3. Economic Analysis

The spatial development framework of the municipality is shaped by the rich agricultural history characterizing large pieces of land in the area. It is against this backdrop that agriculture has become a focal point in all economic development prospects for the municipality constituency.

The municipality has vast tracts of land which can be used to harness economic development opportunities. It is believed that livestock farming is the main type of farming activity that is carried out in the local municipality. The tourism sector in the Moretele Local Municipality is not well established.

Trading Services are key economic drivers of the local economy. The district economy is largely driven by mining primarily around Rustenburg and Brits.  The weakness for the local economy is that there are no industries to boost the economy and create jobs to cushion poverty for the more than 25 000 people who are unemployed.

The real economic growth rate for the Northwest province in 2007 was 2.7% with the poverty gap standing at 8.8%. the contribution of Gauteng province into the South African Economy in 2011 was 34.5% whereas that of the Northwest Province at the same period was 6.5%, this implies that chances of finding employment in the province and the municipality in are very slim.

- Municipal Mandate and Powers and Functions

  - Mandate

Section 152 of the Constitution of the Republic Mandates local government to perform the following functions as depicted by the figure below:

To provide democratic and

accountable government for

local communities

To ensure the provision of services

to communities in a sustainable

manner

To promote social and economic

development

To promote safe and healthy environment

To encourage the involvement of

communities and community

organisations in the matters of

local government

  - Powers and Functions

The table below provides a list of allocated powers and functions of the municipality in accordance with Schedule 4 B and 5 B of the Constitution (1996) and Sections 83, 84, 85 and 86 of the Municipal Structures Act.

| Authorized Functions |  |  | Non-Authorized |  |
| --- | --- | --- | --- | --- |
| - Air Pollution | - Municipal Public Transport | - Childcare Facilities | - Electricity |
| - Local tourism | - Trading Regulations | - Municipal planning | - Fire fighting |
| - Municipal Airport | - Beaches and Amusement | - Pontoons and Ferries | - Municipal Health Services |
| - Storm Water | - Facilities | - Water (potable) |  |
| - Sanitation | - Cemeteries, Funeral | - Billboards and the |  |
| - Billboards and the Display of Advertisement in Public Places | - Parlours and Crematoria | - Display of |  |
| - Control of Public Nuisance | - Control of Undertaking that Sell Liquor to the public | - Advertisement in Public |  |
| - Fencing and Fences | - Licensing of dogs | - Places |  |
| - Local Amenities | - Markets | - Cleansing |  |
| - Local Sports Facilities | - Noise Pollution | - Facilities for the accommodation, care, and burial of animals Licensing of undertakings that sell food to the Public |  |
| - Municipal Parks and Recreation | - Refuse Removal, refuse Dumps and solid waste disposal | - Municipal Abattoirs Pounds |  |
| - Public Places | - Traffic and Parking | - Street Trading |  |
| - Street Lighting |  |  |  |
| - Building Regulation |  |  |  |
| - Municipal airport |  |  |  |

- Financial Plan

2025/2026 Adjusted Summary Budget

The application of sound financial management principles for the compilation of the Municipality’s financial plan is essential and critical to ensure that the Municipality remains financially viable and that municipal services are provided sustainably, economically, and equitably to all communities.

The Municipality’s business and service delivery priorities were reviewed as part of this year’s planning and budget process. Where appropriate, funds were transferred from low- to high priority programmes to maintain sound financial stewardship.

The Municipality is embarking on implementing a range of revenue collection strategies to optimize the collection of debt owed by consumers, mainly state owned. Some of these revenue collection strategies are through the new valuation roll which is implemented in the current FY 2025/2026 and is going to be valid until 2029.

Adjustment Budget 2025/2026

The main challenges experienced during the compilation of the Adjustment Budget 2025/2026 can be summarized as follows:

- The municipality aimed to avert an unfunded budget through application of;

- Low revenue collection and growing aging population.

- The ongoing difficulties in the national and local economy.

- Aging and poorly maintained roads and electricity infrastructure.

- The need to reprioritize projects and expenditure within the existing resource envelope given the cash flow realities and with also ensuring the non-declining cash position of the municipality.

- Affordability of capital projects – Allocation for MIG was R139.5 million in 2025/2026, and there were no adjustments. The municipality has prioritized water and sanitation on new projects and completion of MIG registered projects.

- The WSIG allocation for 2025/2026 was R42 million, and there were no adjustments. The grant is for the Municipal water Infrastructure Grant, the municipality uses this grant

mainly for sanitation projects and yard connections.

- Additional allocation for Municipal Response Grant of R15 million, the grant is allocated for the implementation of Thulare Bridge.

- Additional allocation for Municipal Recovery Grant of R20 million, the grant is allocated for the Carousel view storm water.

The following budget principles and guidelines directly informed the compilation of the adjustment Budget 2025/2026:

- Service delivery deliverables which were hindered by depleted funds, KPI’s which couldn’t not be attained in the mid-term performances which assess their reasonability and measurability to fund them accurately and reprioritized capital project as the DORA was adjusted.

The total original revenue budget for 2025/2026 was R646.9 million excluding capital revenue budget and there was an increase of R2.5 million, therefore the total revenue budget for 2025/2026 is R649.5 million.

Moretele Municipality is still dependent on grants as a major contributor of revenue. The Gazetted Division of Revenue Act has confirmed the following transfers to the municipality:

The original revenue grants were R673.3 million for 2025/2026 and it has been adjusted to R708.3 million funded by transfers from National Departments and as per the original allocation, the approved MIG budget was 139.5 million , Water Service Infrastructure Grant was R42 million, an additional  of R15 million for municipal disaster Response grant, additional allocation of R20 million for municipal Disaster Recovery Grant and Library grant original allocation was R1.2 million, it has been increased by R89 thousand, which then the adjusted amount is R1.28 million.

The 2025/2026 Financial Year (FY) original Revenue was R 822.3 million and it has been increased by R37.6 million, therefore the total Revenue amounted to R859.9 million, the operating expenditure was R706.2 million and it was increased by R19,3 million, the main adjustments were on contracted services, Debt impairment and operational costs. This has impacted on the performance to be on surplus of R 134.3 million capital revenue.

## Operating Revenue Framework

Moretele Local Municipality continues to improve the quality of services by ensuring it adheres to its constitutional mandate; it needs to generate the required revenue in order to have sufficient funds to be financially viable and be able to fund its project successfully. In these tough economic times strong revenue management is fundamental to the financial sustainability of every municipality. The reality is that we are facing serious financial difficulties because of not recovering the revenue we have billed for our consumers for the financial year, The municipality will be developing programmes which will assist the municipality to educate their consumers of the importance of paying bills and assisting with accurate readings. The other initiative that we are ready to embark on is developing revenue strategies to identify new revenue streams that the municipality can tap into to increase the current revenue streams we have as a municipality. The municipality is also funding local SMMEE’s to assist in the reduction of backlogs and poverty alleviations. The municipality continues to render service through contracted services who give the service of water tankering and waste management collection, this expenditure required to address these challenges will inevitably always exceed available funding; hence difficult choices must be made in prioritizing projects to be implemented and balancing expenditures against realistically anticipated revenues. The municipality grants reliance and seeks various methods to augment the financial incapacity.

Some of the mechanisms explored are the grant funds sought from different departments and the alignment of the municipality’s strategic objectives to the main conditions of the grants being provided by sister departments.

The Municipality’s expenditure framework for the 2025/2026 adjustment budget is informed by the funding of the budget over the medium-term as informed by Section 18 and 19 of the MFMA and should there be any operational gains and efficiencies will be directed to funding the capital budget and other core services.

Table 2 Summary of revenue classified by main revenue source.

In line with the formats prescribed by the Municipal Budget and Reporting Regulations, capital transfers and contributions are excluded from the operating statement, as inclusion of these revenue sources would distort the calculation of the operating surplus/deficit. Revenue generated from rates and services charges forms an insignificant percentage of the revenue basket for the Municipality, as the municipality is grant dependent. In the 2025/2026 financial year, revenue from rates and services charges totaled R93.1 million. The adjustments on which we have identified regarding revenue are as follows;

- Conditional Grants increased by R35.08 million,

- Other operational Revenue increased by R380 thousand

- Fines and penalties increased by R2 million

The total adjusted revenue amounted to R37.6 million therefore the adjustment budget revenue amounted to R857.9 million.

Table 3 Transfers and Grant Receipts

The original Capital grants allocated for 2025/2026 was R175.3 million and it was increased by R35 million, therefore Final Capital Grant allocation for 2025/2026 is R210.3 million. The operational grants allocation was R497.7 million, and it was increased by R89 thousand, therefore the Final Operational Grant allocation amounts to R498 million for 2025/2026.

## Operating Expenditure Framework

The following table is a high-level summary of the 2025/2026 budget Adjustment (classified per main type of operating expenditure):

Table 4 Summary of operating expenditure by standard classification item

EMPLOYEES’ COSTS

The original budget allocation for employee-related costs (Staff & Managers) for the 2025/2026 financial year was R188 million and there were no adjustments , as per the budgeted amount the employee related ratio is sitting at 26%, the norm is between 25% and 40%, This is reflecting a normal performance, As part of the Municipality’s cost reprioritization and cash management strategy vacancies and only key positions will be appointed.

COUNCILLORS REMUNERATION

The original budget allocation for Councillors remuneration for the 2025/2026 financial year was R24.6 million and there was no adjustment.

INVENTORY CONSUMED

Inventory consists of bulk purchases and materials. The bulk purchases and inventory original budget for 2025/2026 was R60.2 million and no adjustment was made for bulk purchases, material was reduced by R1 million, therefore the final budget amounts to R59.2 million.

CONTRACTED SERVICES

The original budget allocation for 2025/2026 was R205.1 million, it has been adjusted by R11.2 million therefore the adjustment budget amount increased to R216.3 million, the increase is due to the contracts that where expired and the appointments were higher than the initial estimates.

OPERATIONAL COSTS

The original budget allocation for 2025/2026 was R83.2 million, it has been adjusted by R1.1 million therefore the operational costs budget amounts to R85.1 million.

DEBT IMPAIRMENT

The original budget for 2025/2026 was R75.8 million, it was adjusted by R7.9 million therefore final budget is R83.7 million.

REPAIRS AND MAINTENANCE

Table 5 BS 18C

The repairs and maintenance budget are supposed to be aligned to the needs required to preserve and maintain the Municipality’s current infrastructure. In terms of the Municipal Budget and Reporting Regulations, operational repairs and maintenance are not considered a direct expenditure driver but an outcome of certain other expenditures, such as remuneration, purchases of materials and contracted services. During the compilation of the 2025/2026 original budget for repairs and maintenance it was R26.6 million, and it has been reduced by R170 thousand, therefore the final budget for repairs and maintenance is R26.4 million for 2025/2026 FY.

# ADJUSTMENT BUDGET TABLES

## Table 6 Explanatory notes to MBRR Table B1 - Budget Summary

- Table B1 is a budget summary and provides a concise overview of the Municipality’s budget from all the major financial perspectives (operating, capital expenditure, financial position, cash flow, and MFMA funding compliance).

- The table provides an overview of the amounts approved by the Council for operating performance, resources deployed to capital expenditure, financial position, cash, and funding compliance, as well as the municipality’s commitment to eliminating basic service delivery backlogs.

- Financial management reforms emphases the importance of the municipal budget being funded. This requires a simultaneous assessment of the Financial Performance, Financial Position and Cash Flow Budgets, along with the Capital Budget. The Budget Summary provides the key information in this regard:

- The operating surplus/deficit (after Total Expenditure)

- Capital expenditure is balanced by capital funding sources, of which

- Transfers recognized are reflected in the Financial Performance Budget.

- Internally generated funds are financed from a combination of the current generating surplus and accumulated cash-backed surpluses from previous years. The amount is incorporated in the Net cash from investing on the Cash Flow Budget. The fact that the municipality’s cash flow remains positive and is improving indicates that the necessary cash resources are available to fund the Capital Budget.

## Table 7 MBRR Table B2 - Budgeted Financial Performance (revenue and expenditure by standard classification)

- Table B2 is a view of the budgeted financial performance in relation to revenue and expenditure per standard classification. The modified GFS standard classification divides the municipal services into 15 functional areas. Municipal revenue, operating expenditure and capital expenditure are then classified in terms of each of these functional areas which enables the National Treasury to compile ‘whole of government’ reports.

- Note the Total Revenue on this table includes capital revenues (Transfers recognized – capital) and so does not balance to the operating revenue shown on Table B4. 3. Note that as a general principle the revenues for the Trading Services should exceed their expenditure, however it isn’t the case. The primary goal of the municipality is to be able to collect at least the flat rate currently and the municipality is still struggling to do that, achieving the total

cost of a service is still far-fetched.

## Table 8 MBRR Table B3 - Budgeted Financial Performance (revenue and expenditure by MUNICIPAL VOTE)

## EXPLANATORY notes to MBRR Table B3B - Budgeted Financial Performance (revenue and expenditure by municipal vote)

Table B3B is a view of the budgeted financial performance in relation to the revenue and expenditure per municipal vote. This table facilitates the view of the budgeted operating performance in relation to the organizational structure of the Municipality. This means it is possible to present the operating surplus or deficit of a vote.

Table 9 MBRR Table B4 - Budgeted Financial Performance (revenue and expenditure)

ADJUSTMENTS WERE MADE AGAINST THE FOLLOWING LINE ITEMS AND IMPACTS THEREOF ARE HEREIN EXPLAINED.

- Transfers recognized – operational transfers include the local government equitable shares and other operating grants from national and provincial government was R649.9 million and it was increased by R519 thousand, and the capital transfer was R175.3 million and it was increased by R35 million.

- Bulk purchases (Inventory Water) for 2025/2026 budget were R52.5 million and there were no adjustments.

- The original budgeted allocation for employee related costs including Councillors for the 2025/2026 financial year was R212.6 million and there was no adjustment, which equals 26 per cent of the total operating expenditure.

- Contracted services- Budget for contracted services for 2025/2026 was R205.1 million and it was increased by R11.2 million, the final budget for Contracted Services is R216.3 million.

- Repairs and maintenance- The budget for 2025/2026 was R26.6 million and it was reduced to R170 thousand, which indicates a decrease of R26.4 million.

## Table 10 MBRR Table B5 - Budgeted Capital Expenditure by vote, standard classification and funding source

Table B5 is a breakdown of the capital projects in relation to capital expenditure by municipal vote (multi-year and single-year appropriations); capital expenditure by standard classification; and the funding sources necessary to fund the capital budget, including information on capital transfers from national and provincial departments.

The original budget allocation for 2025/2026 was R196.4 million, there was an increase of R31 million during the adjustment, the total Capital budget is R227.4 million for 2025/2026 FY.

## TABLE 11 B6 Statement of Financial Position

Table 14 B9 Assets Management

## Adjustment to Budget Assumptions

REVENUE BUDGET

- maintain cost reflective tariffs which will increases at levels that reflect an appropriate balance between the affordability to poorer households and other customers while ensuring the financial sustainability of the municipality-

- pay careful attention to the differential incidence of tariff increases across all consumer groups.

Collection rate for revenue services

The base assumption is that tariff and rating should not increase beyond the CPI. Therefore, the increase has been curbed to the recommendations as per circular 129.

The performance of arrear collections is considered as a source of additional cash in-flow once the performance has been carefully monitored.

Impact of national, provincial and local policies

Integration of service delivery between national, provincial and local government is critical to ensure focussed service delivery and, in this regard, various measures were implemented to align IDPs, provincial and national strategies around priority spatial interventions.  In this regard, the following national priorities form the basis of all integration initiatives:

- Creating jobs;

- Enhancing education and skill development.

- Improving Health services;

- Rural development and agriculture; and

- Fighting crime and corruption.

To achieve these priorities integration mechanisms are in place to ensure integrated planning and execution of various development programs.  The focus will be to strengthen the link between policy priorities and expenditure thereby ensuring the achievement of the national, provincial and local objectives.

Ability of the municipality to spend and deliver on the programmes

It is estimated that a spending rate of at least 97 percent is achieved on operating expenditure and 98 percent on the capital programme for the 2025/2026 MTREF of which performance has been factored into the cash flow budget.

## ADJUSTMENT BUDGET FUNDING

a) Where there were no material adjustments to the budget funding which could impact:

- The funding of operating and Capital expenditure

- Financial plans

- Reserves

- The financial sustainability of the municipality

b) There were no adjustments to the collection levels estimated.

c) There were no adjustments to the municipality’s monetary investments

d) there were no adjustments to contributions and donations in cash or in-kind

e) there were no adjustments related to proceeds from the sale of Assets

f) there were no adjustments related to proceeds from lease of assets

g) there were no adjustments related to the planned use of previous cash backed accumulated surplus.

h) there were no adjustments relating to allocations in grants to the municipality

i) Refer to table B1for the reconciliation between the operating and capital expends

# Adjustment to Councillors allowance and Employee benefits

EMPLOYEE COSTS

The original budget for employee related costs (Staff & Managers) for the 2025/2026 financial year was R188 million and the was no adjustment. Based on the three-year collective SALGBC agreement. As part of the Municipality’s cost reprioritization and cash management strategy, only key positions will be appointed.

COUNCILLORS COSTS

The original budgeted allocation for councillors costs for the 2025/2026 financial year was R24.6 million the was no adjustemnt.

## Adjustment to Service delivery and budget implementation plan

Background

In term of Section 24(1) of the Municipal Finance Management Act (MFMA) No. 56 of 2003, the council of the municipality must for each year approve an annual budget for the municipality before the start of the financial year. Section 16(1) of MFMA states that, the council of a municipality must for each financial year approve an annual budget. Section 16(2) for a municipality to comply with subsection (1), the mayor of the municipality must table the annual budget at a council meeting at least 30 days before the start of the budget year.

The application of sound financial management principles for the compilation of the Municipality’s financial plan is essential and critical to ensure that the Municipality remains financially viable and that municipal services are provided sustainably, economically, and equitably to all communities.

The Municipality’s business and service delivery priorities were reviewed as part of this year’s planning and budget process. Where appropriate, funds were transferred from low- to high priority programmes to maintain sound financial stewardship.

CAPITAL EXPENDITURE

The original budget allocation for 2025/2026 was R196.4 million. There was an increase of R31 million during the adjustment, the total Capital budget is R227.4 million for 2025/2026 FY.

The capital projects are funded from National capital and provincial grants and transfers and internally generated funds from current year surpluses. These funding sources are further discussed in detail in Overview of Budget Funding

### IDP and Service Delivery and Budget Implementation Plan

The Council’s IDP is its principal strategic planning instrument, which directly guides and informs its planning, budget, management, and development actions.  This framework is rolled out into objectives, key performance indicators and targets for implementation which directly inform the Service Delivery and Budget Implementation Plan.  The Process Plan applicable to this cycle included the following key IDP processes and deliverables:

- Registration of community needs;

- Compilation of departmental business plans including key performance indicators and targets;

- Financial planning and budgeting process;

- Public participation process;

- Compilation of the SDBIP, and

The IDP has been taken into a business and financial planning process leading up to the 2025/2026 MTREF, Mid-year Review and adjustments budget.  The business planning process has subsequently been refined in the light of current economic circumstances and the resulting revenue projections.

With the compilation of the 2025/2026 MTREF, each department/function had to review the business planning process, including the setting of priorities and targets after reviewing the mid-year and third quarter performance against the 2025/2026 Departmental Service Delivery and Budget Implementation Plan.  Business planning links back to priority needs and master planning, and essentially informed the detail operating budget appropriations and three-year capital programme.

Financial Modelling and Key Planning Drivers

As part of the compilation of the 2025/2026 MTREF, extensive financial modelling was undertaken to ensure affordability and long-term financial sustainability.  The following key factors and planning strategies have informed the compilation of the 2025/2026 MTREF:

- Council’s growth

- Policy priorities and strategic objectives

- Asset maintenance

- Economic climate and trends (i.e. inflation, Eskom increases, and household debt)

- Performance trends

- Cash Flow Management

- Debtor payment levels

- The need for tariff increases versus the ability of the community to pay for services

- Improved and sustainable service delivery

In addition to the above, the strategic guidance given in National Treasury’s MFMA Circulars 128 has been taken into consideration in the planning and prioritisation process.

Submissions received during the community consultation process and additional information regarding revenue and expenditure and individual capital projects were addressed, and where relevant considered as part of the finalisation of the 2025/2026 MTREF.

The following are some of the issues and concerns raised as well as comments received during the consultation process:

- Several complaints were received regarding poor delivery service, especially the waste removal backlogs and the state of road infrastructure;

- Poor performance of contractors relating to infrastructure development and maintenance, especially in the areas of road construction and maintenance were raised;

- In sufficient budget for roads and high mast lights

- During the community consultation process large sections of the community made it clear that they are not in favor of any further tariff increases to fund additional budget requests.  They indicated that the municipality must do more to ensure efficiencies and value for money.

# OVERVIEW OF ALIGNMENT OF ANNUAL BUDGET WITH IDP

The Constitution mandates local government with the responsibility to exercise local developmental and cooperative governance.  The eradication of imbalances in South African society can only be realized through a credible integrated developmental planning process.

Municipalities in South Africa need to utilise integrated development planning as a method to plan future development in their areas and so find the best solutions to achieve sound long-term development goals.  A municipal IDP provides a five-year strategic programme of action aimed at setting short, medium, and long term strategic and budget priorities to create a development platform, which correlates with the term of office of the political incumbents.  The plan aligns the resources and the capacity of a municipality to its overall development aims and guides the municipal budget.  An IDP is therefore a key instrument which municipalities use to provide vision, leadership, and direction to all those that have a role to play in the development of a municipal area.  The IDP enables municipalities to make the best use of scarce resources and speed up service delivery.

Integrated developmental planning in the South African context is amongst others, an approach to planning aimed at involving the municipality and the community to jointly find the best solutions towards sustainable development.  Furthermore, integrated development planning provides a strategic environment for managing and guiding all planning, development and decision making in the municipality.

It is important that the IDP developed by municipalities correlate with National and Provincial intent. It must aim to co-ordinate the work of local and other spheres of government in a coherent plan to improve the quality of life for all the people living in that area. Applied to Moretele, issues of national and provincial importance should be reflected in the IDP of the municipality.  A clear understanding of such intent is therefore imperative to ensure that the municipality strategically complies with the key national and provincial priorities.

The aim of this revision cycle was to develop and coordinate a coherent plan to improve the quality of life for all the people living in the area, also reflecting issues of national and provincial importance.  One of the key objectives is therefore to ensure that there exists alignment between national and provincial priorities, policies and strategies and the municipality’s response to these requirements.

The national and provincial priorities, policies and strategies of importance include amongst others:

- Green Paper on National Strategic Planning of 2009.

- Government Programme of Action;

- Development Facilitation Act of 1995;

- Provincial Growth and Development Strategy (GGDS);

- National and Provincial spatial development perspectives;

- Relevant sector plans such as transportation, legislation and policy;

- National Key Performance Indicators (NKPIs);

- Accelerated and Shared Growth Initiative (ASGISA);

- National 2014 Vision;

- National Spatial Development Perspective (NSDP) and

- The National Priority Outcomes.

The Constitution requires local government to relate its management, budgeting and planning functions to its objectives.  This gives a clear indication of the intended purposes of municipal integrated development planning.  Legislation stipulates clearly that a municipality must not only give effect to its IDP but must also conduct its affairs in a manner which is consistent with its IDP.  The following table highlights the IDP’s five strategic objectives for the 2025/2026 MTREF and further planning refinements that have directly informed the compilation of the budget.

8. Service Delivery Objectives, Indicators and Targets

Municipal objectives by Directorate

Infrastructure Development Services

>

To ensure access to sustainable services and infrastructure to all households

Community Development Services

>

To ensure access to public amenities and to promote community safety, development and sustainable livelihoods

Budget and Treasury Office

>

To promote and ensure prudent financial management to enhance institutional viability and access to basic services

Human Resources and Corporate Services

>

To promote and enhance professional institutional development and transformation through improved human resources systems and

technology

Local Economic Development and Planning

>

To promote and enhance economic development, growth and economic access

Strategic Services and Governance

>

To promote and enhance effective governance systems for improved service delivery

>

To enhance and promote effective governance through credible communication systems

>

To promote and enhance integrated municipal planning

>

To promote Institutional development and transformation and good governance

Moretele Local Municipality

_____________________________________________________

2025/2026

Adjusted SDBIP

BTO

| National Outcome |  |  | National Outcome Responsive, Accountable, Effective And Efficient Local Government System |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NDP Chapters |  |  | Chapter 4: Economic Infrastructure Chapter 8: Human Settlements Chapter 12: Building Safer Communities Chapter 13: Building a capable state Chapter 14: Promoting accountability and fighting corruption |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Municipal Strategic Objectives |  |  | To promote and enhance effective governance systems for improved service delivery, To enhance and promote effective governance through credible communication systems, To promote and enhance integrated municipal planning, To promote Institutional development and transformation and good governance |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Goals |  |  | SG BTO: Ensuring Prudent Financial Management through improved sustainable revenue generation measures |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Key Performance Area |  |  | Financial Management and Viability |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 7. Prudent Financial Management through improved sustainable revenue generation measures ensured |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 7.1 | Output | 7.1 Enhanced municipal budgeting and budget implementation | Percentage of Total annual expenditure against total annual budget by June 2026 | Annual Financial Statement | Target | Percentage |  | 100 | 100 | 0 | 0 | 0 | Budget and Treasury Office | Chief Financial Officer |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 7.10 | Output | 7.10 Improved audit opinion | Number of submitted Financial Statements by June 2026 | 1.Acknowledgement letter from AG(SA), 2, Signed of Set of AFS | Target | Number | 4 | 1 | 1 | 1 | 1 | 1 | Budget and Treasury Office | Chief Financial Officer |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 3000000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 7.11 | Output | 7.11 Improved audit opinion | Number of audit issues resolved as per the Audit Report by June 2026 | Post audit action plan progress on issues relating to Financial statement. | Target | Number | 4 | 4 | 1 | 1 | 1 | 1 | Budget and Treasury Office | Chief Financial Officer |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 8000000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 7.2 | Output | 7.2 Improved financial sustainability and liability management | Percentage change in cash backed reserves reconciliation. Formula Cash backed reserves (current year) - Cash backed reserves (previous year)/ cash backed reserves (previous year) by June 2026 | Annual Financial Statement | Target | Percentage | 100 |  | 100 | 0 | 0 | 0 | Budget and Treasury Office | Chief Financial Officer |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 7.3 | Output | 7.3 Improved liquidity management | Percentage change in cash and cash equivalent (short term). Formula Cash and cash equivalent (Current year) - cash and cash equivalent (Previous year)) / cash and cash equivalent (previous year) by June 2026 | Annual Financial Statement | Target | Percentage | 80 | 80 | 80 | 0 | 0 | 0 | Budget and Treasury Office | Chief Financial Officer |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 7.4 | Output | 7.4 Improved expenditure management | Percentage of total operating expenditure on remuneration Formula Remuneration (Employee Related Costs + Councilors; Remuneration) / Total Operating Expenditure by June 2026 | Section 52 Report and Annual financial statement (AFS) | Target | Percentage | 30 | 30 | 7.5 | 7.5 | 7.5 | 7.5 | Budget and Treasury Office | Chief Financial Officer |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 7.5 | Output | 7.5 Improved expenditure management | Percentage of total operating expenditure on contracted services Formula Contracted Services / Total Operating Expenditure by June 2026 | Section 52 report | Target | Percentage | 5 | 5 | 1.2 | 1.2 | 1.2 | 1.2 | Budget and Treasury Office | Chief Financial Officer |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 7.6 | Output | 7.6 Improved asset management | Percentage change of repairs and maintenance of existing infrastructure Formula Repairs and maintenance expenditure (current year) - Repairs and maintenance expenditure (previous year)) / Repairs and maintenance expenditure by June 2026 | Audited AFS 4th quarter sec 52 report | Target | Percentage | 8 | 8 | 2 | 2 | 2 | 2 | Budget and Treasury Office | Chief Financial Officer |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 7.7 | Output | 7.7 Improved supply chain management | Percentage change in the amount of irregular expenditure a result of SCM transgressions Formula Irregular Expenditure (previous year) - Irregular Expenditure (current year)/ (Irregular Expenditure (previous year) by June 2026 | 1)Irregular Expenditure report (2)Audited AFS of the previous year | Target | Percentage | 100 | 100 | 0 | 0 | 0 | 100 | Budget and Treasury Office | Chief Financial Officer |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 7.8 | Output | 7.8 Improved revenue and debtors€™ management | Percentage change in Gross Consumer Debtors€™ (Current and Non-current) Formula: Gross Debtors - Bad Debt Provision) / Billed Revenue) &; Number of days in the reporting period year to date by June 2026 | Age debtors€™ analysis of current and previous year | Target | Percentage | 100 | 100 | 0 | 0 | 0 | 100 | Budget and Treasury Office | Chief Financial Officer |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 7.9 | Output | 7.9 Improved supply chain management | Percentage change in the amount of irregular expenditure a result of SCM transgressions Formula Irregular Expenditure (previous year) - Irregular Expenditure (current year))/ (Irregular Expenditure (previous year) by June 2026 | (1) Irregular Expenditure report (2) Audited AFS of the previous year | Target | Percentage | 100 | 100 | 0 | 0 | 0 | 100 | Budget and Treasury Office | Chief Financial Officer |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |

Moretele Local Municipality

_____________________________________________________

2025/2026

Adjusted SDBIP

CDS

| National Outcome |  |  | National Outcome Responsive, Accountable, Effective And Efficient Local Government System |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NDP Chapters |  |  | Chapter 4: Economic Infrastructure Chapter 8: Human Settlements Chapter 12: Building Safer Communities Chapter 13: Building a capable state Chapter 14: Promoting accountability and fighting corruption |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Municipal Strategic Objectives |  |  | To ensure access to public amenities and to promote community safety, development and sustainable livelihoods |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Goals |  |  | SG CDS: To ensure access to safe and habitable public facilities, To promote and maximize participation in sports, To promote and maximize participation in sports and recreation |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Key Performance Area |  |  | Basic Services and Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 5. Access to safe and habitable public facilities (CDS) |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 5.10 | Output | 5.10 Community Resilience promoted through effective disaster management activities | Percentage implementation of planned disaster management activities conducted by June 2026 | Q1-Q4: Attendance Register | Target | Percentage | 100 | 100 | 25 | 50 | 75 | 100 | Community Development Services | Community Development Services Director |  |  |
|  |  |  |  |  | Capital | N/A |  | 500000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 5.11 | Output | 5.11 Health Awareness programs designed and implemented in collaboration with other Dept of Health and health agencies | Number of community health awareness campaigns held by June 2026 | Programs & Attendance Registers | Target | Number | 12 | 8 | 2 | 2 | 2 | 2 | Community Development Services | Community Development Services Director |  |  |
|  |  |  |  |  | Capital | N/A |  | 200000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 5.2 | Output | 5.2 To provide accessible and adequate cemeteries and protect from damage | Number of cemeteries fenced in W2, W7 by June 2026 | Completion certificate for cemetery fencing signed by 30 Jun 2026 | Target | Number | 2 | 2 | 0 | 1 | 0 | 1 | Community Development Services | Community Development Services Director |  |  |
|  |  |  |  |  | Capital | N/A |  | 650000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 5.3 | Output | 5.3 To improve access to safe and habitable public facilities through upgrading and maintaining community facilities | Number of Municipal Public facilities developed and maintained at Municipal DLTC Offices , Moss Mary, Ward 17 Office-Makapanstad Mogogelo hall by June 2026 | Completion certificate and delivery note signed off by 30 Jun 2026 | Target | Number | 2 | 4 | 1 | 1 | 0 | 2 | Community Development Services | Community Development Services Director |  |  |
|  |  |  |  |  | Capital | N/A |  | 2000000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 5.4 | Output | 5.4 Development of disaster management plan | Number of disaster management Plan developed by June 2026 | Final copy Disaster Management Plan | Target | Number | 1 | 1 | 0 | 1 | 0 | 0 | Community Development Services | Community Development Services Director |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 5.5 | Output | Community support for victims of disaster provided through various relief Materials | Percentage cumulative of Disaster Relief Materials for disaster victims by June 2026 | Proof of Purchase materials and Delivery notes | Target | Percentage | 100 | 100 | 25 | 50 | 75 | 100 | Community Development Services | Community Development Services Director |  |  |
|  |  |  |  |  | Capital | N/A |  | 500000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 5.6 | Output | 5.6 To create an environment focused on lifting the vulnerable society through social sector meetings and awareness programs | Number of Social Sector Meeting and Awareness Programs {Disability Forum, Woman, Children, Older Person, LDAC & NPOs Forums) by June 2026 | Attendance Registers and Programmes | Target | Number | 14 | 20 | 5 | 5 | 5 | 5 | Community Development Services | Community Development Services Director |  |  |
|  |  |  |  |  | Capital | N/A |  | 300000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 5.7 | Output | 5.7 Improvement of sports facilities | Number of Sports Complex Grandstand installed in Lebotloane Sports Complex by 30 June 2026 | Completion certificate and delivery note signed off by 30 Jun 2026 | Target | Number | 1 | 1 | 0 | 0 | 0 | 1 | Community Development Services | Community Development Services Director |  |  |
|  |  |  |  |  | Capital | N/A |  | 900000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 5.8 | Output | 5.8 Revitalization of community libraries to encourage a culture of learning | Percentages of Community libraries revitalized and maintained by June 2026 | Quarterly reports on library grant spending | Target | Percentage | 100 | 100 | 25 | 50 | 75 | 100 | Community Development Services | Community Development Services Director |  |  |
|  |  |  |  |  | Capital | N/A |  | 1200000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 5.9 | Output | 5.9 Community Safety programs designed and implemented in collaboration with other security cluster agencies | Number of security cluster initiatives to fight crime implemented by June 2026 | Attendance Registers and Programs | Target | Number | 7 | 12 | 2 | 6 | 3 | 1 | Community Development Services | Community Development Services Director |  |  |
|  |  |  |  |  | Capital | N/A |  | 500000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Outcome |  |  | 6. Participation in sports and recreation maximized |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 6.1 | Output | 6.1: Sports and Recreational activities undertaken by June 2026 | Percentage of quarterly of Sports and; Recreational activities undertaken by June 2026 | Attendance Register and Programs | Target | Percentage | 100 | 100 | 25 | 50 | 75 | 100 | Community Development Services | Community Development Services Director |  |  |
|  |  |  |  |  | Capital | N/A |  | 1000000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |

Moretele Local Municipality

_____________________________________________________

2025/2026

Adjusted SDBIP

HR

| National Outcome |  |  | National Outcome Responsive, Accountable, Effective And Efficient Local Government System |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NDP Chapters |  |  | Chapter 4: Economic Infrastructure Chapter 8: Human Settlements Chapter 12: Building Safer Communities Chapter 13: Building a capable state Chapter 14: Promoting accountability and fighting corruption |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Municipal Strategic Objectives |  |  | To promote and enhance professional institutional development and transformation through improved human resources systems and technology |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Goals |  |  | SG HR & CS: To promote and enhance professional institutional development and transformation through improved human resources systems and technology |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Key Performance Area |  |  | Institutional Development and Transformation |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 14. Professional institutional development and transformation through improved human resources systems and technology promoted and enhanced |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.1 | Output | 14.1 Approval of HR Policies and Unit based policies | Percentage of HR related Policies policies developed, reviewed and approved by June 2026 | Q2-Q4: Council Resolution on Approved Policies | Target | Percentage |  | 100 | 0 | 100 | 100 | 100 | Human Resources and Corporate Services | Director Human Resource and Corporate Services |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.10 | Output | 14.10 Service and governance systems improved through the implementation of Information and communication technology and manage legal activities | Percentage implementation of planned information and communication technology initiatives and legal activities by June 2026 | Q1-Q4: Compliance Certificates or copies of reports | Target | Percentage | 100 | 100 | 100 | 100 | 100 | 100 | Human Resources and Corporate Services | Director Human Resource and Corporate Services |  |  |
|  |  |  |  |  | Capital | N/A |  | 16.8 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.11 | Output | 14.11 Employee Wellness initiatives Promoted | Percentage of Employee Wellness/Campaigns initiatives held June 2026 | Q1-Q4 Attendance Register and Reports | Target | Percentage | 4 | 100 | 100 | 100 | 0 | 100 | Human Resources and Corporate Services | Director Human Resource and Corporate Services |  |  |
|  |  |  |  |  | Capital | N/A |  | 62000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.12 | Output | 14.12 Good records keeping and access to information promoted for a better Audit Opinion through the implementation of Records Management legislative compliant systems | Percentage implementation of planned records keeping and access to information initiatives (Records Management legislative compliant systems by June 2026 | Q1 - Q4 Reports | Target | Percentage | 100 | 100 | 100 | 100 | 100 | 100 | Human Resources and Corporate Services | Director Human Resource and Corporate Services |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.13 | Output | 14.13 Institutionalization of Risk Management | 100% of Risk Treatment Plans resolved by June 2026 | Q1-Q4: Risk Reports | Target | Percentage | 100 | 100 | 100 | 100 | 100 | 100 | Human Resources and Corporate Services | Director Human Resource and Corporate Services |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.14 | Output | 14.14 Post Audit Action Plan to address all the audit findings of AGSA and Internal Audit implemented | 100% of Findings resolved by June 2026 | Q3-Q4: Post Audit Action Plan | Target | Percentage | 100 | 100 | 0 | 0 | 100 | 100 | Human Resources and Corporate Services | Director Human Resource and Corporate Services |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.15 | Output | 14.15 Harmonious Employer Employee Relations | Number of LLF Meetings held by June 2026 | Q1-Q4: Attendance Register | Target | Number | 4 | 4 | 1 | 1 | 1 | 1 | Human Resources and Corporate Services | Director Human Resource and Corporate Services |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.16 | Output | 14.16 Submission of the Annual Employment Equity Report to Department of Employment & Labour | Number of EE Report submitted to Department of Employment &amp; Labour by June 2026 | Q3: Submission/Acknowledgement Letter | Target | Number | 1 | 1 | 0 | 0 | 1 | 0 | Human Resources and Corporate Services | Director Human Resource and Corporate Services |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.17 | Output | 14.17 Promote conducive working environment | Percentage of over grown grass cutting and reconciliation of overtime claims and the work output by June 2026 | Pictures and consolidated overtime claim reports | Target | Percentage |  | 100 | 100 | 100 | 100 | 100 | Human Resources and Corporate Services | Director Human Resource and Corporate Services |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.18 | Output | 14.18 Promote and support the maintenance and repairs of municipal fleet by June 2026 | Percentage of maintenance and repairs of municipal fleet by June 2026 | Maintenance and repairs reports | Target | Percentage | 100 | 100 | 100 | 100 | 100 | 100 | Human Resources and Corporate Services | Director Human Resource and Corporate Services |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.2 | Output | 14.2 Review Staff Establishment | Number of Reviewed and Approved Staff Establishment by June 2026 | Q4: Signed Copy of Approved Reviewed Staff Establishment | Target | Number | 1 | 1 | 0 | 0 | 0 | 1 | Human Resources and Corporate Services | Director Human Resource and Corporate Services |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.3 | Output | 14.3 Filling of Critical Vacant Senior Managers Position | Number of Senior Managers appointed by June 2026 | Q4: Council Resolution on Appointment of Senior Managers | Target | Number | 5 | 2 | 0 | 0 | 0 | 2 | Human Resources and Corporate Services | Director Human Resource and Corporate Services |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.4 | Output | 14.4 Staff Appointments | Percentage of staff Appointments byJune 2026 | Q2- Q4: Signed Recruitment Files & Appointment Letters | Target | Percentage | 100 | 100 | 0 | 50 | 0 | 50 | Human Resources and Corporate Services | Director Human Resource and Corporate Services |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.5 | Output | 14.5 Enhanced measures and systems that create safe working conditions as prescribed for in OHSA/COIDA | Number of implementation of planned OHSA/COIDA-related initiatives by June 2026 | Q2 and Q4: Risk Assessment 0r Site Inspection or Medical Surveillance reports | Target | Number | 2 | 2 | 0 | 1 | 0 | 1 | Human Resources and Corporate Services | Director Human Resource and Corporate Services |  |  |
|  |  |  |  |  | Capital | N/A |  | 250000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.6 | Output | 14.6 Workplace Skills Plan implemented to promote employee development and professional growth | Percentage implementation of Workplace Skills Plan initiatives by June 2026 | Q1-Q4: Attendance registers or results or academic records or Proof of payments | Target | Percentage |  | 100 | 100 | 100 | 100 | 100 | Human Resources and Corporate Services | Director Human Resource and Corporate Services |  |  |
|  |  |  |  |  | Capital | N/A |  | 2.6 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.8 | Output | 14.8 Communication of Council Resolutions to Senior Managers | Percentage of Council Resolution Register updated and circulated to Senior Managers by June 2026 | Q1-Q4: Signed Updated Council Resolution Register Acknowledgment of Receipt | Target | Percentage | 100 | 100 | 0 | 0 | 0 | 100 | Human Resources and Corporate Services | Director Human Resource and Corporate Services |  |  |
|  |  |  |  |  | Capital | N/A |  | 2000000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.9 | Output | 14.9 Security and access control | Percentage (100%) provision of security and access control services by June 2026 | Q1-Q4: Quarterly security, assessment reports and monthly OB entries | Target | Percentage | 100 | 100 | 100 | 100 | 100 | 100 | Human Resources and Corporate Services | Director Human Resource and Corporate Services |  |  |
|  |  |  |  |  | Capital | N/A |  | 35.6 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |

Moretele Local Municipality

_____________________________________________________

2025/2026

Adjusted SDBIP

IDS

| National Outcome |  |  | National Outcome Responsive, Accountable, Effective And Efficient Local Government System |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NDP Chapters |  |  | Chapter 4: Economic Infrastructure Chapter 8: Human Settlements Chapter 12: Building Safer Communities Chapter 13: Building a capable state Chapter 14: Promoting accountability and fighting corruption |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Municipal Strategic Objectives |  |  | To ensure access to sustainable services and infrastructure to all households |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Goals |  |  | SG IDS: To optimise access to water services, To enhance human dignity through adequate sanitation, To promote and to ensure integrated and safe road networks, To ensure access to safe and habitable public facilities |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Key Performance Area |  |  | Basic Services and Infrastructure Development |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 1. Optimised access to water services |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 1.1 | Output | 1.1 Water supply to Moeka, (Ga Motle, Ratsiepane, Kromkuil, Mmakaunyane, Norokie) with reticulation and yard connections Schedule C | Number of households provided with basic water in Motle,Moeka Ratsiepane, Kromkuil, Mmakaunyane, Norokie by September 2025 | Q1: Progress reports & Completion certificate | Target | Number | 41856 | 620 | 620 | 0 | 0 | 0 | Infrastructure Development Services | Infrastructure Development Services Director |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 11.2 | Output | Water supply to Moeka, (Ga Motle, Ratsiepane, Kromkuil, Mmakaunyane, Norokie) with reticulation and yard connections Schedule C | Number of Yard connections in Motle,Moeka Ratsiepane, Kromkuil, Mmakaunyane, Norokie by September 2025 | Q1: Progress reports & Completion certificate | Target | Number | 41856 | 620 | 620 | 0 | 0 | 0 | Infrastructure Development Services | Infrastructure Development Services Director |  |  |
|  |  |  |  |  | Capital | N/A |  | 21 467 118,92 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 1.3 | Output | 1.2 Ruigtesloot Village Water Reticulation and Yard Connections | Number of households provided with basic water in (Ruigtesloot) Ward 1 by June 2026 | Q4: Completion certificates | Target | KM | 41856 | 288 | 0 | 0 | 0 | 288 | Infrastructure Development Services | Infrastructure Development Services Director |  |  |
|  |  |  |  |  | Capital | 18 731 930,00 |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Outcome |  |  | 19. Community facilities constructed for improved public cohesion and interactions |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 19.1 | Output | 19.1 Completion of Community Hall in Ward 15 by June 2026 | Percentage completion of Community Hall in Ward 15 completed by June 2026 | Progress report and completion certificate | Target | Percentage | 6 | 100 | 0 | 0 | 0 | 100 | Infrastructure Development Services | Infrastructure Development Services Director |  |  |
|  |  |  |  |  | Capital | N/A |  | 10000000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Outcome |  |  | 2. Human dignity enhanced through adequate sanitation |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 2.1 | Output | 2.1 Construction of Ablution facilities in various wards | Number of households provided with basic sanitation services in Ward 4 by March 2026 | Progress report and completion certificate | Target | Number | 43571 | 400 | 0 | 400 | 0 | 0 | Infrastructure Development Services | Infrastructure Development Services Director |  |  |
|  |  |  |  |  | Capital | N/A |  | 11 200 000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 2.2 | Output | 2.2 Construction of Ablution facilities in various wards | Number of households provided with basic sanitation in Ward 7 by March 2026 | Progress report and completion certificate | Target | Number | 43571 | 450 | 0 | 450 | 0 | 0 | Infrastructure Development Services | Infrastructure Development Services Director |  |  |
|  |  |  |  |  | Capital | N/A |  | 12 631 070,00 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 2.3 | Output | 2.3 Construction of Ablution facilities in various wards | Number of household provided with basic sanitation in Ward 26 by March 2026 | Progress report and completion certificate | Target | Number | 43571 | 214 | 0 | 0 | 214 | 0 | Infrastructure Development Services | Infrastructure Development Services Director |  |  |
|  |  |  |  |  | Capital | N/A |  | 7 100 000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Outcome |  |  | 3. Integrated and safe road networks promoted and ensured |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 3.1 | Output | 3.1: Paved roads & stormwater drainage constructed in ward 11 (Mogogelo) | Km of road paved with storm water by June 2026 in ward 11 | Progress Report, Completion Certificate | Target | KM | 105 | 1 | 0 | 0 | 0 | 1 | Infrastructure Development Services | Infrastructure Development Services Director |  |  |
|  |  |  |  |  | Capital | N/A |  | 10 750 000 ,00 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 3.2 | Output | 3.2 Paved roads & stormwater drainage constructed in ward 18 | km of road paved with storm water by June 2026 in ward 18 | Progress report and completion certificate | Target | KM | 105 | 1 | 0 | 0 | 0 | 1 | Infrastructure Development Services | Infrastructure Development Services Director |  |  |
|  |  |  |  |  | Capital | N/A |  | 9 856 974 ,65 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 3.3 | Output | 3.3 Paved roads & stormwater drainage constructed in ward 17 | Km of road paved with storm water by June 2026 in ward 17 | Progress report and completion certificate | Target | KM | 105 | 1 | 0 | 0 | 0 | 1 | Infrastructure Development Services | Infrastructure Development Services Director |  |  |
|  |  |  |  |  | Capital | N/A |  | 10 000000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 3.4 | Output | 3.4 Paved roads & stormwater drainage constructed in ward 22 | Km of road paved with stormwater by June 2026 in Ward 22 | Progress report and completion certificate | Target | KM | 105 | 1 | 0 | 0 | 0 | 1 | Infrastructure Development Services | Infrastructure Development Services Director |  |  |
|  |  |  |  |  | Capital | N/A |  | 9 103 490 ,87 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 3.7 | Output | Stormwater drainage constructed in ward 13 | Km of stormwater pipeline constructed in ward June 2026 ( multiyear project) | Progress report | Target | KM | 105 | 1km | 0 | 0 | 0 | 1km | Infrastructure Development Services | Infrastructure Development Services Director |  |  |
|  |  |  |  |  | Capital | 20 000000 |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 0 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 3.5 | Output | Development of Lebotlwane, Thulare Bridge in Ward 4 | Percentage developed of Lebotlwane Thulare Bridge in Ward 4 | Progress Reports | Target | Percentage | 2 | 80 | 0 | 0 | 0 | 80 | Infrastructure Development Services | Infrastructure Development Services Director |  |  |
|  |  |  |  |  | Capital | 15 000 000 |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 3.6 | Output | Implementation of Lebotlwane, Thulare paved in Ward 4 | Meters of paved road in Ward 4 ( multiyear project) by June 2026 | Progress Reports | Target | M | 2 | 400 | 0 | 0 | 0 | 400m | Infrastructure Development Services | Infrastructure Development Services Director |  |  |
|  |  |  |  |  | Capital | N/A |  | 15 000 000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Outcome |  |  | 4. Public safety enhanced through sustainable public lighting |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 4.1 | Output | 4.1 Community lighting erected for improved public safety in ward 8 | Number of high mast-lights erected by June 2026 in Ward 8 | Progress report and completion certificate | Target | Number | 335 | 8 | 0 | 0 | 0 | 8 | Infrastructure Development Services | Infrastructure Development Services Director |  |  |
|  |  |  |  |  | Capital | N/A |  | 5500000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |

Moretele Local Municipality

_____________________________________________________

2025/2026

Adjusted SDBIP

LED

| National Outcome |  |  | National Outcome Responsive, Accountable, Effective And Efficient Local Government System |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NDP Chapters |  |  | Chapter 4: Economic Infrastructure Chapter 8: Human Settlements Chapter 12: Building Safer Communities Chapter 13: Building a capable state Chapter 14: Promoting accountability and fighting corruption |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Municipal Strategic Objectives |  |  | To promote and enhance economic development, growth and economic access |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Goals |  |  | SG LED: To maximise the economic potential and growth of the local economy through innovation and improved economic performance, To Maximise the economic potential and growth of Agriculture as a critical economic anchor in the local economy, To minimize the environmental damage through maximizing compliance to address the environmental issues that have a direct and indirect impacts on the natural environment, To maximise (should be minimise) environmental damage through temporary job creation, To maximise the economic potential development of Tourism in the area, Compliance with Town Planning Legislations/policies/regulations |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Key Performance Area |  |  | Local Economic Development |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 10. The economic potential development of Tourism in the area maximized |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 10.1 | Output | 10.1 Tourism Development and supported | Number of Tourism projects supported by June 2026 | Completion certificate, delivery notes, and acknowledgement of beneficiaries | Target | Number | 3 | 3 | 1 | 1 | 1 | 0 | Local Economic Development and Planning | Director Local Economic Development |  |  |
|  |  |  |  |  | Capital | N/A |  | 709.71 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Outcome |  |  | 11. Compliance with Town Planning Legislations/policies/regulations |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 11.1 | Output | 11.1 Land use survey initiatives | Number of milestones to be achieved for land use survey by June 2026 | Draft land use survey report | Target | Number | 0 | 4 | 1 | 3 | 0 | 0 | Local Economic Development and Planning | Director Local Economic Development |  |  |
|  |  |  |  |  | Capital | N/A |  | 32500 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 11.2 | Output | 11.2 Feasibility study on all MLM incomplete land tenure upgrading Project closure by June 2026 | Number of Feasibility study on all MLM incomplete land tenure upgrading Project closure by June 2026 | Final feasibility study report with cost estimations | Target | Number | 0 | 2 | 1 | 1 | 0 | 0 | Local Economic Development and Planning | Director Local Economic Development |  |  |
|  |  |  |  |  | Capital | N/A |  | 480000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 11.3 | Output | 11.3 Delivery, supply, installation and commissioning of GIS by June 2026 | Number of milestone for delivery, supply, installation and commissioning of GIS by June 2026 | Training session attendance register, training report, Report of Database maintenance and Database management | Target | Number | 0 | 5 | 2 | 1 | 1 | 1 | Local Economic Development and Planning | Director Local Economic Development |  |  |
|  |  |  |  |  | Capital | N/A |  | 1031000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 11.4 | Output | 11.4 Demarcation of sites by June 2026 | Number of milestone for sites demarcation by June 2026 | Proof of application submission, acknowledgement letter of application from the Municipality Newspaper notice, and proof of public participation | Target | Number | 11 | 11 | 0 | 0 | 0 | 11 | Local Economic Development and Planning | Director Local Economic Development |  |  |
|  |  |  |  |  | Capital | N/A |  | 1270000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 11.5 | Output | 11.5 Land use and land development awareness workshops | Number of land use awareness workshops conducted by June 2026 | Attendance registers and minutes | Target | Number | 4 | 4 | 1 | 1 | 1 | 1 | Local Economic Development and Planning | Director Local Economic Development |  |  |
|  |  |  |  |  | Capital | N/A |  | 7308000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Capital | N/A |  | 835200 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Outcome |  |  | 12. Minimise environmental damage through temporary job creation |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 12.1 | Output | 12.1 Minimize the unemployment rate in Moretele through the EPWP initiatives | Number of jobs created through Phepafatsa Moretele Project by June 2026 | Monthly reports and attendance registers | Target | Number | 390 | 390 | 390 | 0 | 0 | 0 | Local Economic Development and Planning | Director Local Economic Development |  |  |
|  |  |  |  |  | Capital | N/A |  | 10764026.26 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 12.2 | Output | 12.2 Minimize the unemployment rate in Moretele through the EPWP initiatives | Number of PPE procured for the In-house EPW Programme by June 2026 | Delivery notes and pictures | Target | Number |  | 150 | 0 | 0 | 0 | 150 | Local Economic Development and Planning | Director Local Economic Development |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Outcome |  |  | 13. Minimize the environmental damage through maximizing compliance to address the environmental issues that have a direct and indirect impact on the natural environment |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 13.1 | Output | 13.1 Acquire the license for Makapanstad Landfill site | Number of landfill site license acquired from DEDECT by June 2026 | Proof of submission of application | Target | Number |  | 1 | 0 | 0 | 1 | 0 | Local Economic Development and Planning | Director Local Economic Development |  |  |
|  |  |  |  |  | Capital | N/A |  | 5000000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 13.2 | Output | 13.2 Cleaning of illegal dump hotspots | Number of Wards with weekly cleaning of illegal dump hotspots by June 2026 | Monthly signed cleaning of illegal dumps reports, including pictures by service, Councillors, and the Environmental Officer | Target | Number | 26 | 26 | 26 | 26 | 26 | 26 | Local Economic Development and Planning | Director Local Economic Development |  |  |
|  |  |  |  |  | Capital | N/A |  | 8769.6 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 13.3 | Output | 13.3 Wards with access to weekly waste removal services | Number of wards with access to weekly waste removal services by June 2026 | Monthly signed waste collection reports, including pictures by service, Councillors, and the Environmental Officer | Target | Number | 26 | 26 | 26 | 26 | 26 | 26 | Local Economic Development and Planning | Director Local Economic Development |  |  |
|  |  |  |  |  | Capital | N/A |  | 31000000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 13.4 | Output | 13.4 Wards with weekly skip bins maintenance | Number of Wards with weekly skip-bins maintenance by June 2026 | Monthly signed skip bins maintenance reports, including pictures by service, Councillors, and the Environmental Officer | Target | Number | 26 | 26 | 26 | 26 | 26 | 26 | Local Economic Development and Planning | Director Local Economic Development |  |  |
|  |  |  |  |  | Capital | N/A |  | 6614784 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 13.5 | Output | 13.5 Closure and rehabilitation of Ga motla dumpsite | Number of Closure and rehabilitation of Ga-motla dumpsite by June 2026 | Final Closure and Rehabilitation Plan and proof of submission | Target | Number | 1 | 1 | 0 | 0 | 0 | 1 | Local Economic Development and Planning | Director Local Economic Development |  |  |
|  |  |  |  |  | Capital | N/A |  | 5000000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Outcome |  |  | 8. The economic potential and growth of the local economy through innovation and improved economic performance maximised |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 8.1 | Output | 8.1 LED awareness workshops and campaigns | Number of LED awareness workshops and campaigns conducted by June 2026 | Attendance registers and minutes | Target | Number | 4 | 4 | 1 | 1 | 1 | 1 | Local Economic Development and Planning | Director Local Economic Development |  |  |
|  |  |  |  |  | Capital | N/A |  | 203630.11 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 8.2 | Output | 8.2 LED Strategy reviewed | Number of LED Strategy reviewed by June 2026 | Reviewed LED Strategy | Target | Number | 1 | 1 | 0 | 1 | 0 | 0 | Local Economic Development and Planning | Director Local Economic Development |  |  |
|  |  |  |  |  | Capital | N/A |  | 200000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 8.3 | Output | 8.3 Developing Business by law | Number of by-laws promulgated and gazetting business by-laws by June 2026 business by-law by June 2026 | Copy of the gazette business by-law | Target | Number | 1 | 1 | 0 | 0 | 0 | 1 | Local Economic Development and Planning | Director Local Economic Development |  |  |
|  |  |  |  |  | Capital | N/A |  | 312782.4 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 8.4 | Output | 8.4 SMME Development and support | Number of SMME’s projects developed and supported by June 2026 | Appointment letter and completion certificates | Target | Number | 3 | 5 | 1 | 1 | 2 | 1 | Local Economic Development and Planning | Director Local Economic Development |  |  |
|  |  |  |  |  | Capital | N/A |  | 751.89 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Outcome |  |  | 9. The economic potential and growth of Agriculture as a critical economic anchor in the local economy maximised |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 9.1 | Output | 9.1 Agriculture Development and support | Number of Agricultural Projects developed and supported by June 2026 | Appointment letter and completion certificate. | Target | Number | 5 | 7 | 2 | 1 | 2 | 2 | Local Economic Development and Planning | Director Local Economic Development |  |  |
|  |  |  |  |  | Capital | N/A |  | 1585.78 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |

|  | Local Economic Development and PlanningMORETELLOCAMUNICIPALITY SDBIP Annual Plan: 2025/2026 Page ofLocal Economic Development anPlanniMORETELOCAMUNICIPALISDBIAnnuaPlan2025/2026Page 1 of |
| --- | --- |

Moretele Local Municipality

_____________________________________________________

2025/2026

Adjusted SDBIP

OFFICE OF THE MAYOR

| National Outcome |  |  | National Outcome Responsive, Accountable, Effective And Efficient Local Government System |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NDP Chapters |  |  | Chapter 4: Economic Infrastructure Chapter 8: Human Settlements Chapter 12: Building Safer Communities Chapter 13: Building a capable state Chapter 14: Promoting accountability and fighting corruption |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Municipal Strategic Objectives |  |  | To promote and enhance effective governance systems for improved service delivery, To enhance and promote effective governance through credible communication systems, To promote and enhance integrated municipal planning, To promote Institutional development and transformation and good governance |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Goals |  |  | SG Governance: Efficient and effective Audit Management functions provided, Efficient and effective Risk Management functions provided, To ensure credible planning for improved outcomes,Achieve improved in institutional development, transformation, and good governance outcomes through implementation of Performance Management, Promote participatory development and local democracy through effective oversight |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Key Performance Area |  |  | Good Governance and Public Participation |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 15. Improved institutional development, transformation, and good governance outcomes through implementation of Performance Management |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 16. Efficient and effective Audit Management functions provided |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 17. Efficient and effective Risk Management functions provided |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 18. Promote participatory development and local democracy through effective oversight |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.11 | Output | 18.11 Promotion of Active Involvement, Good Governance and Public Participation | Percentage of good government and Public participation initiative held by June 2026 | Attendance Registers, Reports & Pictures | Target | Percentage | 100 | 100 | 100 | 100 | 100 | 100 | Office of the Mayor | Manager- Office of Mayor |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.11.1 | Activity | 18.11.1Promotion of Active Involvement, Good Governance and Public Participation | Number of (4) Imbizo Held by June 2026 | Attendance Register & Pictures | Target | Number | 4 | 2 | 0 | 0 | 1 | 1 | Office of the Mayor | Manager- Office of Mayor |  |  |
|  |  |  |  |  | Capital | N/A |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 1.2 |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.11.2 | Activity | 18.11.2 Conduct Mayor Oversight visits by June 2026 | Number (4) of Mayors Oversights visits and Service Delivery Accelerated Programs (Netefatso Program) by June 2026 | Attendance Registers, Reports & Pictures | Target | Number | 4 | 4 | 1 | 1 | 1 | 1 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 100 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.11.3 | Activity | 18.11.3 Promotion of the rights of Senior Citizen by June 2025 | Number (2) of Senior Citizens support Programs by June 2026 | Attendance Registers, Reports & Pictures | Target | Number | 2 | 2 | 0 | 1 | 0 | 1 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 200 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.11.4 | Activity | 18.11.4 Prepare consolidated quarterly Call Center Reports by June 2026 | Number (12) of quarterly Call Center Reports consolidated and submitted by June 2026 | Q1-Q4: Copies of monthly reports | Target | Number | 12 | 12 | 3 | 3 | 3 | 3 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.11.5 | Activity | 18.11.5 Provide vulnerable families with food parcels by June 2026 | Number (1040) of vulnerable households supported with food parcels by June 2026 | Beneficiary list per ward Q1-Q4 | Target | Number | 260 | 1040 | 260 | 260 | 260 | 260 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 2200000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.11.6 | Activity | 18.11.6 Promotion and support of destitute 02 families by June 2026 | Percentage (100) promotion and support of selected destitute 02 families by June 2026 | Pictures and confirmation of receipt by beneficiaries | Target | Percentage | 100 | 100 | 0 | 0 | 100 | 100 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 300 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.11.7 | Activity | 18.11.7 Hosting of local IGR Forums by June 2026 | Number (2) of Local IGR Forums held by June 2026 | Attendance Registers, Reports & Pictures | Target | Number | 2 | 2 | 0 | 1 | 0 | 1 | Office of the Mayor | Protocol & IGR Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 100 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.11.8 | Activity | 18.11.8 Promotion of National Calendar Events | Number (5) of Calendar Events held (Mandela day ,Youth Day , Prayer Day, Human Rights Day, 1 Pre-Easter by June 2026 | Attendance Registers, Reports & Pictures | Target | Number | 2 | 5 | 1 | 1 | 1 | 2 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.5 | Output | 18.5 Implementation of IGR & Protocol Initiatives | Percentage Implementation of IGR and Protocol Initiatives by June 2025 | attendance registers or Pictures | Target | Percentage | 100 | 100 | 100 | 100 | 100 | 100 | Office of the Mayor | Protocol & IGR Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.5.1 | Activity | 18.5.1 Promotion of social cohesion and good governance by June 2026 | Number (3) Mayoral and Stakeholders Outreach Engagements session held by June 2026 | Attendance Registers & Pictures | Target | Number | 3 | 3 | 0 | 1 | 1 | 1 | Office of the Mayor | Protocol & IGR Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 400000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.5.2 | Activity | 18.5.2 Strengthening the relationship between the Municipality and Magosi | Number (2) of Engagement Sessions and 1 training of Magosi and Traditional Council held by June 2026 | Attendance Registers & Pictures and acceptance letter | Target | Number | 3 | 3 | 0 | 1 | 1 | 1 | Office of the Mayor | Protocol & IGR Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 400000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.6 | Output | 18.6 Promotion and empowerment of Women by June 2026 | Percentage of Women empowerment initiatives by June 2026 | Q1-Q4 Reports | Target | Percentage | 100 | 100 | 100 | 100 | 100 | 100 | Office of the Mayor | Manager- Office of Mayor |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.6.1 | Activity | 18.6.1 Hold Womenâ€™s Day Celebration by June 2026 | Number (1) Women Seminar held by June 2026 | Attendance registers and pictures | Target | Number | 1 | 1 | 1 | 0 | 0 | 0 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 200000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 400000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 150000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.7 | Output | 18.7 Promotion and support of people living with disability BY June 2026 | Percentage of support of people living with disabilities by June 2026 | Q1,Q3 Reports, Attendance register and Pictures | Target | Percentage | 100 | 100 | 100 | 0 | 200 | 100 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.7.1 | Activity | 18.7.1 Provide Disability Projects Support by June 2026 | Number (1) of Casual Day Celebration | Pictures and Attendance Register | Target | Number | 1 | 1 | 1 | 0 | 0 | 0 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 125000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.7.2 | Activity | 18.7.2 Engagement with People with Disability | Number (2) Disability Forum Meetings and Programs by June 2026 | Attendance registers and pictures | Target | Number | 1 | 2 | 0 | 1 | 0 | 1 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 125000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.7.3 | Activity | 18.7.3 Provide People with Disability Projects Support by June 2026 | Number (1) of Disability Projects Supported by June 2026 | Profile of projects, acknowledgement of receipt | Target | Number | 1 | 1 | 0 | 0 | 1 | 0 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 100000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.8 | Output | 18.8 Promotion of Social Cohesion through celebrating National Days by June 2026 | Percentage of Social Cohesion through celebrating National Days initiatives implemented by June 2026 | Attendance registers and pictures | Target | Percentage | 100 | 100 | 100 | 100 | 100 | 100 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.8.1 | Activity | 18.8.1 Promotion of Social Cohesion through celebrating National Days by September 2025 | Number (1) of Heritage Day Celebration September 2025 | Attendance registers and pictures | Target | Number | 1 | 1 | 1 | 0 | 0 | 0 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 200000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.8.2 | Activity | 18.8.2 Promotion of Social Cohesion through celebrating National Days by June 2026 | Number (1) of Women's Month Commemoration by June 2026 | Attendance registers and pictures | Target | Number | 1 | 1 | 1 | 0 | 0 | 0 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | Capex |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 200000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.8.3 | Activity | 18.8.3 Promotion of Social Cohesion through celebrating National Days by June 2026 | Number (1) of World Aids Days celebrated by July 2026 | Attendance registers and pictures | Target | Number | 1 | 1 | 0 | 1 | 0 | 0 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 15000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.8.4 | Activity | 18.8.4 Promotion of Social Cohesion through celebrating National Days by June 2026 | Number (1) of 16 Days of Activism of Abuse Against Women and Child Abuse celebrated by December 2025 | Attendance registers and pictures | Target | Number | 1 | 1 | 0 | 1 | 0 | 0 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.9 | Output | 18.9 Promotion and empowerment of the Youth by June 2026 | Percentage of Youth empowerment initiatives by June 2026 | Q1-Q4 Reports | Target | Percentage | 100 | 100 | 100 | 100 | 100 | 100 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 750000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.9.2 | Activity | 18.9.2 Youth Council Engagement Session by June 2026 | Host (1) Youth Council Engagement by June 2026 | Attendance register, report and pictures | Target | Percentage | 100 | 100 | 100 | 100 | 100 | 100 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 100000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.9.4 | Activity | 18.9.3 Host Career Development Program by June 2026 | Number (1) Career Exhibition in partnership with Dept of Education) by June 2026 | Attendance registers and pictures | Target | Number | 1 | 1 | 0 | 0 | 0 | 1 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 200000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 400000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.9.5 | Activity | 18.9.5 Conduct Back to School Campaign in partnership with Dept of Education by March 2026 | Number (1) of Back-to-School Campaigns conducted in partnership with Dept of Education (Distribution of 200 shoes, and 500 cares packs) by March 2026 | List of Schools and Pictures | Target | Number | 1 | 1 | 0 | 0 | 1 | 0 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 200000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.9.6 | Activity | 18.9.6 Issuing, submission and capturing of 2026 academic year Bursary applications by June 2026 | Percentage (100) completion of issuing, submitting and capturing of 2026 academic bursaries for 30 Youth by June 2026 | Registration letters, Report | Target | Number | 100 | 100 | 0 | 100 | 100 | 100 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 1200000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.9.7 | Activity | 18.9.7 Selection and Payments of 2026 bursaries by June 2026 | Percentage (100) completion of selection and payments for 2026 academic bursaries for 30 Youth by June 2026 | Registration letters, Report | Target | Percentage | 100 | 100 | 0 | 0 | 100 | 100 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.9.9 | Activity | 18.9.9 Hold Youth Month Commemoration Program by June 2026 | Number (1) of Cluster Program held by June 2026 | Attendance registers and pictures | Target | Number | 1 | 1 | 0 | 0 | 0 | 1 | Office of the Mayor | Special Projects Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |

Moretele Local Municipality

_____________________________________________________

2025/2026

Adjusted SDBIP

OFFICE OF THE MUNICIPAL MANAGER

| National Outcome |  |  | National Outcome Responsive, Accountable, Effective And Efficient Local Government System |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NDP Chapters |  |  | Chapter 4: Economic Infrastructure Chapter 8: Human Settlements Chapter 12: Building Safer Communities Chapter 13: Building a capable state Chapter 14: Promoting accountability and fighting corruption |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Municipal Strategic Objectives |  |  | To promote and enhance effective governance systems for improved service delivery, To enhance and promote effective governance through credible communication systems, To promote and enhance integrated municipal planning, To promote Institutional development and transformation and good governance |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Goals |  |  | SG Governance: Efficient and effective Audit Management functions provided, Efficient and effective Risk Management functions provided, To ensure credible planning for improved outcomes,Achieve improved in institutional development, transformation, and good governance outcomes through implementation of Performance Management, Promote participatory development and local democracy through effective oversight |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Key Performance Area |  |  | Good Governance and Public Participation |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 15. Improved institutional development, transformation, and good governance outcomes through implementation of Performance Management |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 15.1 | Output | 15.1 Annual Report consistent with Circular 63 (National Treasury) prepared | Number of 2024/2025 Annual Report approved by January 2026 | Q1-Q4: Report | Target | Number | 1 | 1 | 0 | 0 | 1 | 0 | Office of the Municipal Manager | PMS Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 15.1.1 | Activity | 15.1.1 2025 /2026 Performance agreements finalised and signed by Senior Managers | Number (6) of signed performance agreements for Senior Managers by September 2025 | Q1: Copies of signed Performance Agreements | Target | Number | 6 | 6 | 6 | 0 | 0 | 0 | Office of the Municipal Manager | PMS Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 15.1.10 | Activity | 15.1.10 PMS Strategic session | Number (1) of IDP Strategic sessions held by March 2026 | Q3 A attendance register | Target | Number | 1 | 1 | 0 | 0 | 1 | 0 | Office of the Municipal Manager | PMS Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 15.1.2 | Activity | 15.1.2 Preparation and approval of the Annual Report | Percentage (100) completion of the preparation and approval of 2024/2025 Annual Report approved by January 2026 | Q3: Copy of Annual Report | Target | Percentage | 100 | 100 | 0 | 0 | 100 | 0 | Office of the Municipal Manager | PMS Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 15.1.3 | Activity | 15.1.3 Implement initiatives performance management organisational wide through Performance Management System | Percentage (100) of Individual performance management cascading initiatives through performance management System implemented by June 2026 | Q3: Quarterly Reports | Target | Percentage | 100 | 100 | 0 | 0 | 100 | 0 | Office of the Municipal Manager | PMS Manager |  |  |
|  |  |  |  |  | Capital | N/A |  | 2.2 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 15.1.4 | Activity | 15.1.4 Conduct quarterly performance reviews for all section 56/57 employees | Number (2) of individual (section 54/56 managers) performance reviews conducted by June 2025 | Q3&Q4: Performance Review Report | Target | Number | 4 | 2 | 0 | 0 | 1 | 1 | Office of the Municipal Manager | PMS Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 15.1.5 | Activity | 15.1.5 Conduct PMS policy review | Percentage (100) completion of PMS policy review and approval by June 2026 | Q4: Council Approved Copy of the policy | Target | Percentage | 100 | 100 | 0 | 0 | 0 | 100 | Office of the Municipal Manager | PMS Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 15.1.6 | Activity | 15.1.6 Preparation and approval of the SDBIP | Percentage (100) completion of the preparation and approval of the 2025/2026 signed by the Mayor by June 2026 | Q4: Copy of the SDBIP | Target | Percentage | 100 | 100 | 0 | 0 | 0 | 100 | Office of the Municipal Manager | PMS Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 15.1.7 | Activity | 15.1.7 Prepare consolidated quarterly performance report | Number (4) of quarterly performance reports tabled and approved by June 2026 | Q1-Q4: Council Resolutions | Target | Number | 4 | 4 | 1 | 1 | 1 | 1 | Office of the Municipal Manager | PMS Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 15.1.8 | Activity | 15.1.8 IDP REP Forum Capacity Building | Number (1) of IDP Capacity Building by December 2025 | Q2 Attendance register | Target | Number | 1 | 1 | 0 | 1 | 0 | 0 | Office of the Municipal Manager | PMS Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 15.1.9 | Activity | 15.1.9 IDP/PMS Operations equipment procured | Number (1) Projector and Sound system procured by July 2025 | Q1 Delivery note | Target | Number | 1 | 1 | 1 | 0 | 0 | 0 | Office of the Municipal Manager | PMS Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Outcome |  |  | 16. Efficient and effective Audit Management functions provided |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 16.1 | Output | 16.1 Risk based internal Audit Plan developed | Number of Internal Audit Plans approved by September 2025 | Q4: Approved Internal Audit Plan by Audit Committee Q1: minutes of the audit committee | Target | Number | 1 | 1 | 1 | 0 | 0 | 0 | Office of the Municipal Manager | Internal Audit Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 16.1.1 | Activity | 16.1.1 Preparation of the Internal Audit Plan | Percentage (100) completion of the preparation of the Internal Audit Plans September 2025 | Q1 Approved Internal Audit Plan by Audit Committee | Target | Percentage | 100 | 100 | 100 | 0 | 0 | 0 | Office of the Municipal Manager | Internal Audit Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 16.1.2 | Activity | 16.1.2 Approval of the Internal Audit Plan | Number of Internal Audit Plans approved by September 2025 | Q4: Approved Internal Audit Plan by Audit Committee Q1: minutes of the audit committee and the approved audit plan | Target | Number | 1 | 1 | 1 | 0 | 0 | 0 | Office of the Municipal Manager | Internal Audit Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 16.2 | Output | 16.2 Work and Audit Committee recommendations accounted to council | Number (4) of Audit Committee reports submitted to Council by June 2025 | Q1-Q4: Council resolutions | Target | Number | 4 | 4 | 1 | 1 | 1 | 1 | Office of the Municipal Manager | Internal Audit Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 16.2.1 | Activity | 16.2.1 Submission of Audit Committee Report | Number (4) audit committee reports submitted to council by June 2026 | Q1-Q4: Council resolutions | Target | Number | 4 | 4 | 1 | 1 | 1 | 1 | Office of the Municipal Manager | Internal Audit Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Outcome |  |  | 17. Efficient and effective Risk Management functions provided |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 17.1 | Output | 17.1 Fraud Management Plan developed and approved | Number of Fraud Management Plan developed by September 2025 | Approved Fraud Management Plan | Target | Number | 1 | 1 | 1 | 0 | 0 | 0 | Office of the Municipal Manager | Risk Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 17.1.1 | Activity | 17.1.1 Hold Anti-fraud and Corruption Awareness Training and Workshop | Number (1) of Anti-fraud and Corruption Awareness Training and Workshops held by December2025 | Presentations and attendance register | Target | Number | 1 | 1 | 0 | 1 | 0 | 0 | Office of the Municipal Manager | Risk Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 17.2 | Output | 17.2 Risk Management Plan developed and approved | Number of Risk Management Plan developed by September 2025 | Approved Risk Management Plan | Target | Number | 1 | 1 | 1 | 0 | 0 | 0 | Office of the Municipal Manager | Risk Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 17.2.1 | Activity | 17.2.1 Hold Risk Management Committee meetings | Number (4) of Risk Management Committee meetings held by June 2026 | Minutes of the RMC meeting and attendance register | Target | Number | 4 | 4 | 1 | 1 | 1 | 1 | Office of the Municipal Manager | Risk Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Outcome |  |  | 18. Promote participatory development and local democracy through effective oversight |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.1 | Output | 18.1 IDP reviewed in accordance with approved Process Plan | Percentage of 2026/2027 IDP Reviewed and approved by June 2026 | Q4: Copy of 2026/2027 IDP | Target | Percentage | 100 | 100 | 0 | 0 | 0 | 100 | Office of the Municipal Manager | IDP Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.1.1 | Activity | 18.1.1 Develop a credible IDP Process plan | Number (1) of 2026-2027 credible IDP Process plans developed by September 2026 | Copy of a 2026-2027 process plan | Target | Number | 1 | 1 | 1 | 0 | 0 | 0 | Office of the Municipal Manager | IDP Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.1.2 | Activity | 18.1.2 Hold 2026/2027 IDP Ward based consultations | Number (26) of 2026-2027 IDP Ward based consultations held by December 2026 | 2026-2027 Ward Based consultation report | Target | Number | 26 | 26 | 0 | 26 | 0 | 0 | Office of the Municipal Manager | IDP Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | Opex |  | 520000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.1.3 | Activity | 18.1.3 Hold IDP REP Forum meetings | Number (4) of IDP REP Forum meetings held by June 2026 | Minutes and attendance register | Target | Number | 4 | 4 | 1 | 1 | 1 | 1 | Office of the Municipal Manager | IDP Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | Opex |  | 100000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.1.4 | Activity | 18.1.4 Capacitate IDP REP Forums | Number (1) of IDP REP Forums capacitated by December 2025 | Report and Attendance register | Target | Number | 1 | 1 | 0 | 1 | 0 | 0 | Office of the Municipal Manager | IDP Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | Opex |  | 200000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.2 | Output | 18.2 Communication Strategy developed and implemented | Number of Communication Strategy developed and implemented to improve communication and its credibility by June 2026 | Copy of communication strategy | Target | Number |  | 1 | 0 | 0 | 1 | 0 | Office of the Municipal Manager | Communications Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 100000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.2.1 | Activity | 18.2.1 Hold Communication strategy Workshop | Number (1) of Communication strategy Workshops held by December 2025 | Attendance register | Target | Number |  | 1 | 0 | 1 | 0 | 0 | Office of the Municipal Manager | Communications Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | Opex |  | 50000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.2.2 | Activity | 18.2.2 Develop Cooperate Identity Manuals | Number (1) of Cooperate Identity Manuals developed by December 2025 | Cooperate identity manual | Target | Percentage |  | 1 | 0 | 1 | 0 | 0 | Office of the Municipal Manager | Communications Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | Opex |  | 200000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.2.3 | Activity | 18.2.3 Develop Communications and Social Media Policies | Number (3) of Communications and Social Media Policies developed by June 2026 | Copies of media, communications, and social media policies | Target | Number |  | 3 | 0 | 1 | 1 | 1 | Office of the Municipal Manager | Communications Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.2.4 | Activity | 18.2.4 Procure Diaries, Promotion Materials and Calendars | Number (3) of Diaries, Promotion Materials and Calendars procured by June 2026 | Prove of purchase | Target | Number |  | 3 | 0 | 2 | 1 | 0 | Office of the Municipal Manager | Communications Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | Opex |  | 250000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.2.5 | Activity | 18.2.5 Hold Media Communications and Coverage Promotions | Number (4) of Media Communications and Coverage Promotions held by June 2026 | Attendance register | Target | Number |  | 4 | 1 | 1 | 1 | 1 | Office of the Municipal Manager | Communications Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | Opex |  | 100000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.4 | Output | 18.4 Communities and interested stakeholders engaged on the 2024/2025 Annual Report | Percentage of 2024/2025 Annual Oversight Report approved by June 2026 | Q4: Council resolution | Target | Percentage | 100 | 100 | 0 | 0 | 0 | 100 | Office of the Municipal Manager | MPAC Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.4.1 | Activity | 18.4.1 Workshop for all the members of MPAC on the role and responsibilities of MPAC. | Number (1) Workshop for all members of MPAC on the roles and responsibilities of MPAC by June 2026 | Q:3 Invitation, Attendance registers. | Target | Number | 1 | 1 | 0 | 0 | 1 | 0 | Office of the Municipal Manager | MPAC Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 150000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.4.2 | Activity | 18.4.2 Consolidation of the draft 2024/2025 Oversight Report by MPAC committee by end of March 2026 | Percentage (100) completion of the consolidation of the draft 2024/2025 Oversight Report by MPAC committee by March 2026 | Invitations, Attendance registers and draft oversight report. | Target | Percentage | 100 | 100 | 0 | 0 | 100 | 0 | Office of the Municipal Manager | MPAC Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 120000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.4.3 | Activity | 18.4.3 Printing of the 2024/2025 Annual Oversight Report | Percentage (100) completion of the Printing of the 2024/2025 Annual Oversight Report by March 2026 | Final Oversight report adopted by council. | Target | Percentage | 100 | 100 | 0 | 0 | 100 | 0 | Office of the Municipal Manager | MPAC Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 381049.25 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.4.4 | Activity | 18.4.4 Engagement on the 2024/2025 Annual Report with community members by end of March 2026 | Number (4) of engagements on the 2024/2025 Annual Report with community members by end of March 2026 | Invitations, Minutes and attendance register | Target | Number | 4 | 4 | 0 | 0 | 4 | 0 | Office of the Municipal Manager | MPAC Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 150000 | 0 | 0 | 0 | 0 |  |  |  |  |

| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.10.5 | Activity | 14.10.5 Professional institutional development and transformation through provision of legal advice and guidance to the Municipality | Percentage (100) implementation of legal advice and guidance provided by June 2025 | Q3-Q4: Reports | Target | Percentage |  | 100 | 0 | 0 | 100 | 100 | Office of the Municipal Manager | Legal Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.10.6 | Activity | 14.10.6 Professional institutional development and transformation through conducting of legal research to identify potential risk associated with Municipality | Percentage (100) of legal research conducted by June 2026 | Q3-Q4: reports | Target | Percentage |  | 100 | 0 | 0 | 100 | 100 | Office of the Municipal Manager | Legal Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.10.7 | Activity | 14.10.7 Professional institutional development and transformation through engagement with stakeholders to develop strategies and policies to ensure compliance with law | Percentage (100 engagement with stakeholders by June 2026 | Q3-Q4 Reports | Target | Percentage |  | 100 | 0 | 0 | 100 | 100 | Office of the Municipal Manager | Legal Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.10.8 | Activity | 14.10.8 Professional institutional development and transformation through effective management of litigation cases | Percentage (100 of litigation cases managed by June 2026 | Q3-Q4 Report | Target | Percentage |  | 100 | 0 | 0 | 100 | 100 | Office of the Municipal Manager | Legal Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 14.10.9 | Activity | 14.10.9 Professional institutional development and transformation through working with internal departments to develop measures that align business practices with legal requirements | Percentage (100) of engagements with internal departments by June 2026 | Q3-Q4 Reports | Target | Percentage |  | 100 | 0 | 0 | 100 | 100 | Office of the Municipal Manager | Legal Manager |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |

Moretele Local Municipality

_____________________________________________________

2025/2026

Adjusted SDBIP

OFFICE OF THE CHIEFWHIP

| National Outcome |  |  | National Outcome Responsive, Accountable, Effective And Efficient Local Government System |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NDP Chapters |  |  | Chapter 4: Economic Infrastructure Chapter 8: Human Settlements Chapter 12: Building Safer Communities Chapter 13: Building a capable state Chapter 14: Promoting accountability and fighting corruption |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Municipal Strategic Objectives |  |  | To promote and enhance effective governance systems for improved service delivery, To enhance and promote effective governance through credible communication systems, To promote and enhance integrated municipal planning, To promote Institutional development and transformation and good governance |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Goals |  |  | SG Governance: Efficient and effective Audit Management functions provided, Efficient and effective Risk Management functions provided, To ensure credible planning for improved outcomes,Achieve improved in institutional development, transformation, and good governance outcomes through implementation of Performance Management, Promote participatory development and local democracy through effective oversight |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Key Performance Area |  |  | Good Governance and Public Participation |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 15. Improved institutional development, transformation, and good governance outcomes through implementation of Performance Management |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 16. Efficient and effective Audit Management functions provided |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 17. Efficient and effective Risk Management functions provided |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 18. Promote participatory development and local democracy through effective oversight |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.10 | Output | 18.10 Implementation of Whipery Initiatives | Percentage Implementation of Whipery Initiatives by June 2026 | Report | Target | Percentage | 100 | 100 | 100 | 100 | 100 | 100 | Office of the Single Whip | Manager - Office of the Single Whip |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.10.1 | Activity | 18.10.1 Hold Information Sharing Session between Whips of all political affiliates and portfolio whips. | Number (4) of Whipery Forum held and 04 Portfolio Whip by June 2026 | Attendance Register and Minutes | Target | Percentage | 3 | 4 | 1 | 1 | 1 | 1 | Office of the Single Whip | Manager - Office of the Single Whip |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 30000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.10.2 | Activity | 18.10.2 Hold Direct Engagements with Stakeholders concerning good governance and service delivery issues | Number (4) of Governance Forum held by June 2026 | Attendance Register and Reports | Target | Number | 4 | 4 | 1 | 1 | 1 | 1 | Office of the Single Whip | Manager - Office of the Single Whip |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 250000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.10.3 | Activity | 18.10.3 Hold Political engagements in order to make our institution politically stable and avoid unnecessary tension within our institution. | Number (4) of Political Caucus Management (Multi-Party Caucus) held by June 2026 | Attendance Register and Reports | Target | Number | 4 | 4 | 1 | 1 | 1 | 1 | Office of the Single Whip | Manager - Office of the Single Whip |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 30000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.10.4 | Activity | 18.10.4 Capacitate Councilors as Custodian of the society in the implementation of service delivery. | Number (4) of Council Caucuses held by June 2026 | Attendance Register and Reports | Target | Number | 4 | 4 | 1 | 1 | 1 | 1 | Office of the Single Whip | Manager - Office of the Single Whip |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 40000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.10.5 | Activity | 18.10.5 Voter registration drives, hosting candidate forums or debates, and conducting outreach efforts to inform and mobilize the electorate Organized | Number (4) of Letsema Programmes by June 2026 | Programmes and Attendance Register | Target | Number | 4 | 4 | 1 | 1 | 1 | 1 | Office of the Single Whip | Manager - Office of the Single Whip |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 220000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 3000000 | 0 | 0 | 0 | 0 |  |  |  |  |

Moretele Local Municipality

_____________________________________________________

2025/2026

Adjusted SDBIP

OFFICE OF THE SPEAKER

| National Outcome |  |  | National Outcome Responsive, Accountable, Effective And Efficient Local Government System |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| NDP Chapters |  |  | Chapter 4: Economic Infrastructure Chapter 8: Human Settlements Chapter 12: Building Safer Communities Chapter 13: Building a capable state Chapter 14: Promoting accountability and fighting corruption |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Municipal Strategic Objectives |  |  | To promote and enhance effective governance systems for improved service delivery, To enhance and promote effective governance through credible communication systems, To promote and enhance integrated municipal planning, To promote Institutional development and transformation and good governance |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Strategic Goals |  |  | SG Governance: Efficient and effective Audit Management functions provided, Efficient and effective Risk Management functions provided, To ensure credible planning for improved outcomes,Achieve improved in institutional development, transformation, and good governance outcomes through implementation of Performance Management, Promote participatory development and local democracy through effective oversight |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Key Performance Area |  |  | Good Governance and Public Participation |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 15. Improved institutional development, transformation, and good governance outcomes through implementation of Performance Management |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 16. Efficient and effective Audit Management functions provided |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 17. Efficient and effective Risk Management functions provided |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Outcome |  |  | 18. Promote participatory development and local democracy through effective oversight |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.3 | Output | 18.3 Participatory development and local democracy promoted through effective ward committee system | Percentage of promotions in participatory development and effective award system | Q1-Q4: Copies of Ward Committee meeting attendance registers | Target | Percentage | 100 | 100 | 100 | 100 | 100 | 100 | Office of the Speaker | Manager- Office of the Speaker |  |  |
|  |  |  |  |  | Capital | Capex |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 150000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.3.1 | Activity | 18.3.1 Conduct Ward Committee meetings | Number (20) of Ward Committee meetings held by June 2026 | Q1-Q4: Copies of Ward Committee meeting attendance registers | Target | Number | 20 | 20 | 5 | 5 | 5 | 5 | Office of the Speaker | Manager- Office of the Speaker |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 4149600 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.3.2 | Activity | 18.3.2 Award Councillor's Bursary | Number (1) of Councillor's Bursary Awarded by March 2026 | Q1; list of Registered Councilor's | Target | Number | 1 | 1 | 0 | 0 | 1 | 0 | Office of the Speaker | Manager- Office of the Speaker |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 500000 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.3.3 | Activity | 18.3.3 Purchase Ward Committee Uniforms and Identifications | Number (260) of Ward Committee Uniforms and Identifications purchased by March 2025 | Q2: Invoices and Receipts | Target | Number | 260 | 260 | 0 | 0 | 260 | 0 | Office of the Speaker | Manager- Office of the Speaker |  |  |
|  |  |  |  |  | Capital | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  | 230800 | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.3.4 | Activity | 18.3.4 Hold Ward Councilors and Secretaries Forum | Number (4) of Ward Councilors and Secretaries Forum held by June 2026 | Q1-Q4: Copy of Attendance Registers | Target | Number | 4 | 4 | 1 | 1 | 1 | 1 | Office of the Speaker | Manager- Office of the Speaker |  |  |
|  |  |  |  |  | Capital | N/A |  | 50000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |
| Sdbip ref. | Planning Level | Measurable Objective | Key Performance Indicator | Evidence | Type | UOM | Baseline | Annual Target | Q1 | Q2 | Q3 | Q4 | Accountability |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  | Department | Person |  |  |
| 18.3.5 | Activity | 18.3.5 Hold Ordinary Council meetings | Number (4) of Ordinary Council meetings held by June 2026 | Q1-Q4: Copy of Attendance Registers and Invites | Target | Number | 4 | 4 | 1 | 1 | 1 | 1 | Office of the Speaker | Manager- Office of the Speaker |  |  |
|  |  |  |  |  | Capital | N/A |  | 250000 | 0 | 0 | 0 | 0 |  |  |  |  |
|  |  |  |  |  | Operating | N/A |  |  | 0 | 0 | 0 | 0 |  |  |  |  |

| 9.Consolidated planned Indicators | 9.Consolidated planned Indicators |
| --- | --- |

Adjustments 2025/2026

| Key performance Area | Key performance indicator | Component | Original | Adjustment |
| --- | --- | --- | --- | --- |
|  | Number (1) of By Law promulgated and gazzeted by June 2026 | Target | 3rd Quarter | 4th Quarter |
|  | Number (6) of SMME projects developed and supported by June 2026 | Target | Number 6 | Number 5 |
|  | Number (5) of Agricultural Projects developed and supported by June 2026 | Target | Number 5 | Number 7 |
|  | Number of Landfill sites licence acquired from DEDECT by June 2026 | POE | License and business plan | Proof of submission of application |
|  | Number (1) Closure and rehabilitation of Ga-motla dumpsite by June 2026 | POE | Final Closure and Rehabilitation Plan, Closure license | Final closure and rehabilitation plan and proof of submission |
|  | Number (6)of SMME’s projects developed and supported by June 2026 | POE | Application form, approval letter, completion certificates, delivery notes and reports | Application letter and completion certificate |
|  | Number 05 0f Agricultural Projects developed and supported by June 2026 | POE | Appointment letter, pictures, completion certificates and acknowledgement letters from beneficiaries. | Appointment letter and completion certificate |
| Community Development Services | Number of Sports Complex (2) Grandstand installed in Lebotloane and Motla Sports Complex by 30 June 2026 | Target | Quarter 2 | Quarter 4 |
|  | Number (3) of cemeteries fenced in W2, W7,W11 by June 2026 | Target | Number 3 | Number 2 |

9.Consolidated planned Indicators

| Directorate / Unit | Planned Annual indicators |
| --- | --- |
| Infrastructure Development Services | 12 |
| Community Development services | 12 |
| Budget and Treasury Office | 11 |
| Human Resources and Corporate Services | 16 |
| LED and Planning | 18 |
| Strategic Services |  |
| - IDP/PMS | 2 |
| - Communications | 1 |
| - Speaker’s Office | 5 |
| - Special Projects (Mayor’s Office) | 7 |
| - Internal Audit | 2 |
| - Risk | 2 |
| - Chief Whip | 6 |
| - MPAC | 1 |
| Totals | 94 |

10. Implementation, Monitoring and Reporting of the 2025/2026 SDBIP

- Directors are to submit monthly reports to the Municipal Manager by Directors, the Municipal Manager submits to the mayor in accordance with section 71 (g) (ii) of the MFMA

- The Mayor or the Budget and Treasury Chairperson as delegated convenes quarterly Budget Steering Committee

- The mayor submits quarterly reports to Council in accordance with section 52 (d) of MFMA indicating progress in the implementation of the SDBIP

- The revision of the SDBIP may be done as per section 54 (1) (c) of the MFMA as part of the adjustment budget.

- Section 121 of the MFMA requires a municipality to account in a form of an assessment of performance against the measurable objectives set in the IDP and SDBIP.

| Directorate: | Office of the Municipal Manager |
| --- | --- |
| Municipal Manager: | Name: S.Ngwenya |

11. Projections of each month of revenue to be collected by source. Operational and Capital expenditure by Vote (Attached as Annexure A)