Moretele Local Municipality

2025/2026

Mid Term Report

December 2025

___________________________________________________________________________________________________________

Revision Control 10.1

Mid-term Report 2025/2026

December 2025

____________________________________________________________________________________________________________

Strategic Services

IDP/PMS Unit

Enquiries:

012 716 1433

nyakale.lale@moretele.gov.za

____________________________________________________________________________________________________________

Table of contents

| ITEM | TITLE | PAGE NUMBER |
| --- | --- | --- |
| 1 | Purpose | 4 |
| 2 | Context | 4 |
| 3 | Reporting requirements | 5 |
| 4 | Financial reporting | 6 |
| 5.1 | Mandate | 11 |
| 5.2 | Powers and Function | 12 |
| 5.3 | Key Development Objectives | 13 |
| 5.4 | Performance and rating by KPA | 15 |
| 6 | Reporting fundamentals | 129 |
| 7 | Reporting Regime | 130 |
| 8 | Signing Off | 131 |

Part A

1. Purpose

To provide a comprehensive account of municipal performance for the Mid term performance for the 2025/2026 financial year in accordance with section 52 of the Municipal Finance Management Act (2003).

2. Context

The Municipal Finance Management Act (MFMA) of 2003 requires that municipalities prepare a Service Delivery and Budget Implementation Plan (SDBIP) as an implementation and management tool to ensure that budgetary decisions that are adopted by municipalities for the financial year are aligned with their Integrated Development Plan (IDP).

Section 1 of the Municipal Finance Management Act defines the “service delivery and budget implementation plan” as the detailed plan approved by the mayor of the municipality in terms of Section 53 (1) (c) (ii) for implementing the municipality’s delivery of municipal services and its annual budget and which must include the following –

a) projections of each month of-

(i) revenue to be collected, by source; and

(ii) operational and capital expenditure, by vote;

b) service delivery targets and performance indicators for each quarter; and

c) any other matters that may be prescribed, and includes any revisions of such plan by the mayor in terms of section 54(1)(c”).

In terms of Section 53 (i)(c)(ii) of the MFMA, the SDBIP must be approved by the Mayor of a municipality within 28 days of the approval of the budget and be made public within 14 days after the approval of the SDBIP (Section 53 (3) (a). The report is therefore intended to report on the performance against the 2025/2026 SDBIP in respect of the Mid-term performance of the 2025/2026 financial year.

3. Reporting Requirements

| Statutory Reporting as required by the Municipal Finance Management Act (2003) |  |  |  |
| --- | --- | --- | --- |
| Section 71 | Section 52 | Section 72 | Section 121 |
| Section 71 of the MFMA stipulates that reporting on actual revenue targets and spending against the budget should occur on a monthly basis. This reporting must be conducted by the accounting officer of a municipality no later than 10 working days, after the end of each month. Reporting must include the following: - actual revenue, per source - actual borrowings - actual expenditure, per vote - actual capital expenditure, per vote - the amount of any allocations received | Section 52 (d) of the MFMA compels the Mayor to submit a report to the council on the implementation of the budget and the financial state of affairs of the municipality within 30 days of the end of each quarter. | Section 72 (1) (a) of the MFMA outlines the requirements for mid-year reporting. The accounting officer is required by the 25th January of each year to assess the performance of the municipality during the first half of the year taking into account – - the monthly statements referred to in section 71 of the first half of the year - the municipalities service delivery performance during the first half of the financial year, and the service delivery targets and performance indicators set in the service delivery and budget implementation plan - the past year’s annual report, and progress on resolving problems identified in the annual report; and - the performance of every municipal entity under the sole or shared control of the municipality, taking into account reports in terms of section 88 from any such entities. Based on the outcomes of the mid-year budget and performance assessment report, an adjustments budget may be tabled if actual revenue or expenditure amounts are materially different from the projections contained in the budget or the SDBIP. | Section 121 of the Municipal Finance Management Act stipulates that every municipality and every municipal entity must for each financial year prepare an annual report. The council of a municipality must within nine months after the end of a financial year deal with the annual report of municipal entity under the municipality’s sole or shared control in accordance with section 129. The purpose of an annual report is— - to provide a record of the activities of the municipality or municipal entity during the financial year to which the report relates - to provide a report on performance against the budget of the municipality or municipal entity for that financial year - to promote accountability to the local community for the decisions made throughout the year by the municipality or municipal entity. |

Part B

4. Financial Reporting

Summary of the past year’s (2023/24) Annual Report and Progress on resolving problems identified.

| No. | Identified problem | Status and Progress |
| --- | --- | --- |
| 1. | Consequence management not implemented for the Unauthorized, Irregular and Fruitless and Wasteful Expenditure raised in the prior years. | Not yet started |
| 2. | Differences between the Annual Performance Report (APR) and the supporting registers. | Not yet started |
| 3. | Internal control deficiency - Inaccurate presentation of key performance indicator in the SDBIP | Done |
| 4. | Duplicate Assets – Overstatement of the fixed assets register | Done |
| 5. | Consequence management not implemented for the Unauthorized, Irregular and Fruitless and Wasteful Expenditure raised in the prior years. | Not yet started |
| 6. | Consequence management not implemented for the Unauthorized, Irregular and Fruitless and Wasteful Expenditure raised in the prior years. | Not yet started |

    - Summary of progress on resolving problems identified in the previous year’s audit report.

| No. | Audit findings | Status and Progress |
| --- | --- | --- |
| 1. | Consequence management not implemented for the Unauthorized, Irregular and Fruitless and Wasteful Expenditure raised in the prior years. | Not yet started |
| 2. | Differences between the Annual Performance Report (APR) and the supporting registers. | Not yet started |
| 3. | Internal control deficiency - Inaccurate presentation of key performance indicator in the SDBIP | Not yet started |
| 4. | Duplicate Assets – Overstatement of the fixed assets register | Not yet started |
| 5. | Consequence management not implemented for the Unauthorized, Irregular and Fruitless and Wasteful Expenditure raised in the prior years. | Not yet started |

The annual regulatory audit for the 2024/25 financial year has been concluded in which regard the municipality received an unqualified audit opinion. We have started to update the Post Audit Action Plan which will be table in council together with the new annual report for the 2024/25 financial year.

Overall Financial Performance to date.

| No. | Indicator | Comments |
| --- | --- | --- |
|  | Is the budget implementation in line with the implementation of the Service Delivery and Budget Implementation Plan and any service delivery agreements with municipal entities? | The financial performance of the municipality is on par and in line with the SDBIP. Note the municipality does not have any municipal entities. |
|  | Total aggregated Operating Revenue. | Total actual year-to-date Operating Revenue exceeded the year-to-date budget. Is above par at 41% more than the year-to-date budget. The average collection rate is 12.3%. |
|  | Total aggregated Operating Expenditure. | Is on par at 21% below the year-to-date budget due to outstanding depreciation and impairments. |
|  | Total aggregated Capital Expenditure. | Total actual year-to-date Capital Expenditure exceeded the year-to-date budget and is on par at 4% above the year-to-date budget. |
|  | Total Cash from Operations and Cash and Cash Equivalents at the end of the reporting period. | Total cash from operations was positive with a positive closing balance in respect of investments. Total Net Cash Flow was also positive. The total Cash and Cash Equivalents balance on 31 December 2025 was R536,31 mil. |
|  | Total Outstanding Debtors. | The total older than 1 year requires attention. |
|  | Total Outstanding Creditors. | The total older than 1 year requires attention. |
|  | The overall liquidity and equity of the municipality. | Is on par with Total Net Equity of R2.03 billion. |

The overall financial performance of the municipality is on par. We are aware of the long outstanding creditors and debtors which requires further attention and processing.

Summary of financial problems and or risks facing the municipality or municipal entity.

| No. | Indicator | Status | Impact |
| --- | --- | --- | --- |
|  | Total overdue debtors | Revenue collection remains a challenge | Old historic billings not collectable. Affects cash collections. |
|  | Total overdue creditors | Older than 1 year) are being attended to. | Requires detailed reconciliations. Affects the audit opinion. |

Summary: Potential impact of the National and or Provincial Adjustments Budget.

The impact of the provincial and national government adjustment processes as follows:

| No. | Indicator | Status | Impact |
| --- | --- | --- | --- |
|  | Any additional allocations | Yes | Additional total of R15 million was received for Municipal Disaster grant and it was recorded during the special adjustment. |
|  | Any loss of grant-funding during roll-overs and reallocations process. | No | n/a |
|  | Any changes in the provincial allocations. | No | n/a |

Recommendation for an adjustments budget for the 2025/26 financial year.

- Based on the overall mid-year performance and the impact of the provincial and national adjustment budget process; The municipality will prepare an adjustments budget to be tabled in council by 28 February 2026.

- Changes will also be processed to the Service Delivery Budget Implementation Plan of the municipality.

# EXECUTIVE SUMMARY

This is the mid-year report of the municipality as per Section 72 of the Municipal Finance Management Act and Part 5 of the Municipal Budgeting and Reporting Regulations; for the month that ended 31 December 2025, which represents the 6th reporting period of the financial year.

The total Actual Year-to-Date Operating Revenue for the period under review amounted to R450,72 million whilst the total Actual Year-to-Date Operating Expenditure amounted to R280,37 million, resulting in a total Net Actual Operating Surplus of R170,34 million.

The municipality budgeted for a total Year-to-Date Operating Deficit of R33,83 million indicating and over-achievement of more than R204 million.

The financial performance of the municipality: Capital Expenditure

The total Actual Year-to-Date Capital Expenditure of R108,38 million is R4,48 million more than the Year-to-Date Budget of R103,90 million, an over achievement of R4,48 million.

The financial performance of the municipality: Financial Position

The total liabilities of R251,81 million (243,57 mil + 8,23 mil) is significantly less the total assets of R2,28 billion (507,80 mil + 1780,91 mil). Total assets are about 9 times the value of the total liabilities, confirming the positive liquidity position and Equity of R2,03 billion.

The financial performance of the municipality: Cash Flows

The municipality closed the reporting period with a positive closing bank balance of R536,31 million which is R279,87 million more than the projected total of R256,43 million. The total ‘Cash Flows from Operations’ was positive at R417,00 million.

The financial performance of the municipality: Outstanding Debtors and Creditors

The municipality recorded total actual Outstanding Debtors of R836,36 million and total actual Outstanding Creditors of R1,86 million.

The financial performance of the municipality: Material Variances and Explanations

The report is in respect of the first six months of the financial year. The reasons for the variances on the performance in terms of the main financial indicators had been recorded and will be monitored by management during the next reporting periods to ensure that remedial actions are implemented.

In year Budget Statements

Operating Revenue

Property Rates: The actual year-to-date revenue of R9,06 million significantly exceeded the year-to-date budget of R6,52 million with a positive variance of R2,54 million.

Service Charges: The actual year-to-date revenue of R46,61 million exceeded the year-to-date budget of R37,06 million with a positive variance of R9,54 million.

Investment Revenue: The actual year-to-date revenue of R10,07 million is below the year-to-date budget of R15,37 million with a negative variance of R5,30 million.

Transfers and Subsidies - Operational: The actual year-to-date revenue of R370,45 million exceeded the year-to-date budget of R248,95 million with a positive variance of R121,49 million.

Other Own Revenue: The actual year-to-date revenue of R14,51 million exceeded the year-to-date budget of R11,05 million with a positive variance of R3,46 million.

Total Operating Revenue: The actual year-to-date revenue of R450,72 million exceeded the year-to-date budget of R318,98 million with a positive variance of R131,73 million.

Operating Expenditure

Employee Costs: The actual expenditure of R77,07 million is below the year-to-date budget of R84,27 million with a variance of R7,19 million.

Remuneration of Councillors: The actual expenditure of R12,77 million is below the year-to-date budget of R17,57 million with a variance of R4,80 million.

Depreciation and Amortisation: We did not record any (zero) actual expenditure against the year-to-date budget of R34,17 million.

Inventory consumed and Bulk Purchases: The actual expenditure of R32,79 million is higher than the year-to-date budget of R30,06 million with a variance of R2,72 million.

Transfers and Subsidies: Not budgeted for and no actual expenditure recorded to date.

Other Expenditure: The actual expenditure of R157,73 million is below the year-to-date budget of R186,71 million with a variance of R28,98 million.

Total Operating Expenditure: The actual expenditure of R280,37 million is below the year-to-date budget of R352,81 million with a variance of R72,43 million.

Capital expenditure & funds sources

The Total Actual Year-to-Date Capital Expenditure is higher than projections at R108,38 million against the Total Year-to-Date Budget of R103,90 million.

The Total Actual Year-to-Date capital expenditure of R106,05 million against grants and subsidies (capital transfers) are also higher than the year-to-date budget of R95,19 million whilst those projects funded by internally generated funds are running behind due to the acceleration of the MIG funded projects.

Financial Position

The Total Liabilities of R251,81 million is significantly less than the Total Assets of R2,14 billion which is the reason for the positive ‘Equity’ of R1,89 billion.

The municipality holds fixed assets to the value of R1,78 billion with very long-term loans or borrowings to the amount of R8,23 million.

Budget Statement Summary: Total Cash Flows

The ‘Total Actual Year-to-Date Net cash flows from Operating Activities’ of R417,00 million was positive and significantly better than ‘Total Year-to-Date Budget’ of R107,24 million. The ‘Total Actual Year-to-Date Net cash flows from Investing Activities’, was R133,78 million and in respect of expenditure on capital projects. It was also higher than the ‘Total Year-to-Date Budget’ of R103,90 million.

We did not have any financing activities (mainly borrowings) during the period under review.

The municipality closed the end of the reporting with a positive bank balance of R536,31 million which was better than the projection of R256,43 million.

Budget Statement Summary: Debtors Age Analysis

The municipality recorded total actual outstanding debtors of R836,36 million of which a total of R716,86 million is outstanding for more than a year.

Budget Statement Summary: Creditors Age Analysis

The total actual outstanding creditors amounted to R1,86 million with about R658 thousand (35%) in current (0 - 30 days) and a total of R1,20 million (65%), outstanding for longer than a year.

Budget Statement - Financial Performance (revenue and expenditure by municipal vote)

Note the total operating performance had been covered in the Executive Summary as well as per the discussions under Table C1 and C2. The performance at municipal vote level indicates that ‘Vote 2: Finance and Administration’ recorded an exceptional performance in terms of exceeding the year-to-date revenue projections and keeping expenditure well below the allocated budget.

It is noted that ‘Vote 4: Community and Social Services’ is the only vote that recorded a notable under-achievement of R1,93 million against projected revenues and ‘Vote 1: Executive and Council’ is the only vote that recorded a notable overspending of R3,32 million against the year to-date budget of R40,76 million.

Budget Statement - Financial Performance (revenue and expenditure)

| No. | Item | Performance | Comments |
| --- | --- | --- | --- |
| 1. | Service charges - Electricity | n/a | n/a |
| 2. | Service charges - Water | R30,40 mil against budget of R21,54 mil. | Exceeded budget. Positive variance of R11,86 mil. |
| 3. | Service charges - Waste Water Management | n/a | n/a |
| 4. | Service charges - Waste management | R13,21 mil against budget of R15,52 mil. | Below budget. Negative variance of R2,31 mil. |
| 5. | Agency services | n/a | n/a |
| 6. | Property rates | R9,06 mil against budget of R6,52 mil. | Exceeded budget. Positive variance of R2,54 mil. |
| 7. | Transfers and subsidies - Operational | R370,45 mil against budget of R248,95 mil. | Exceeded budget. Positive variance of R121,49 mil. |
| 8. | Total Operating Revenue | R450,72 mil against budget of R318,98 mil. | Exceeded budget. Positive variance of R131,73 mil. |
| 9. | Employee related costs | R77,07 mil against budget of R84,27 mil. | Below budget. Variance of R7,19 mil. |
| 10. | Remuneration of councillors | R12,77 mil against budget of R17,57 mil. | Below budget. Variance of R4,80 mil. |
| 11. | Bulk purchases - electricity | n/a | n/a |
| 12. | Debt impairment | Zero against budget of R37,92 mil. | No expenditure to date. Variance of R37,92 mil. |
| 13. | Depreciation and amortisation | Zero against budget of R34,17 mil. | No expenditure to date. Variance of R34,17 mil. |
| 14. | Contracted services | R118,77 mil against budget of R105,08 mil. | Exceeded budget. Variance of R13,68 mil. |
| 15. | Operational costs | R38,92 mil against budget of R43,71 mil. | Below budget. Variance of R4,78 mil. |
| 16. | Total Expenditure | R280,37 mil against budget of R352,81 mil. | Below budget. Variance of R72,43 mil. |

In summary: the municipality exceeded the total projected operating revenue by R204,17 million and overall underspent against the year-to-date operating expenditure budget by an amount of R72,43 million. In terms of the Net Operating Results, the municipality projected to end the reporting period with an operating deficit of R33,83 million but exceeded this target and recorded an actual operating surplus of R170,34 million.

The underspending is informed by the zero actual expenditure to date against the budgets of Debt Impairment (R37,92 mil) and Depreciation (R34,17 mil).

Budget Statement - Cash Flow

Net Cash Flows from Operations, were positive with a total of R417,00 million at the end of the reporting period.

Net Cash Flows from Investing Activities, with a total of R133,78 million at the end of the reporting period, was in respect of capital expenditure.

Net Cash Flows from Financing Activities, was zero.

The municipality recorded a positive closing balance of R536,31 million in respect of Cash and Cash Equivalents at the end of the reporting period.

The Net movement in Cash was also positive with a total of R283,21 million for the period under review.

Councillor and Staff benefits

Councillors

The total Actual Year-to-Date expenditure of R12,77 million against the total Year-to-Date Budget of R17,57 million indicates an underspending of R4,80 million in respect of both the monthly salaries and benefits of councillors for the 6 months.

Material Variance: Yes Explanation: Underspending against the budget which may be due to outstanding upper limits of councillors.

Impact on performance agreements of senior management: None Explanation: Will be monitored after the processing of the upper limits during the next reporting periods.

Senior Managers

The total Actual Year-to-Date expenditure of R2,21 million against the total Year-to-Date Budget of R2,05 million indicates an underspending of R161 thousand in respect of both the monthly salaries and benefits of senior managers for the 6 months.

Material Variance: None Explanation: Performance is on par.

Impact on performance agreements of senior management: None Explanation: Performance is on par.

Other Municipal staff

The total Actual Year-to-Date expenditure of R74,86 million against the total Year-to-Date Budget of R82,22 million indicates an underspending of R7,36 million in respect of both the monthly salaries and benefits of the other municipal staff for the 6 months.

Material Variance: None Explanation: Performance is on par.

Impact on performance agreements of senior management: None Explanation: Performance is on par.

5. Powers and Functions and Performance against Pre-Determined Objectives (SDBIP)

5.1 Mandate

Section 152 of the Constitution of the Republic Mandates local government to perform the following functions –

5.2 Powers and Functions

The table below provides a list of allocated powers and functions of the municipality in accordance with Schedule 4 B and 5 B of the Constitution (1996) and Sections 83, 84, 85 and 86 of the Municipal Structures Act.

| Authorized Functions |  |  | Non Authorized |
| --- | --- | --- | --- |
| - Air Pollution - Local tourism - Municipal Airport - Storm Water - Sanitation - Billboards and the Display of Advertisement in Public Places - Control of Public Nuisance - Fencing and Fences - Local Amenities - Local Sports Facilities - Municipal Parks and Recreation - Public Places - Street Lighting | - Building Regulation - Municipal airport - Municipal Public Transport - Trading Regulations - Beaches and Amusement Facilities - Cemeteries, Funeral Parlours and Crematoria - Control of Undertaking that Sell Liquor to the public - Licensing of dogs - Markets - Noise Pollution - Refuse Removal, refuse Dumps and solid waste disposal - Traffic and Parking | - Child Care Facilities - Municipal planning - Pontoons and Ferries - Water (potable) - Billboards and the Display of Advertisement in Public Places - Cleansing - Facilities for the accommodation, care and burial of animals - Licensing of undertakings that sell food to the Public - Municipal Abattoirs - Pounds - Street Trading | - Electricity - Fire fighting - Municipal Health Services |

5.3 Key Development Objectives

| Key Performance Area | Directorate |
| --- | --- |
| - Good Governance and Public Participation - Institutional Development and Transformation | - Strategic Services - IDP and PMS - Internal Audit - Risk Management - Public Participation - Municipal Public Accounts (Admin Unit) - Communications - Governance - Council Support - Special Projects |
| - Municipal Financial Viability and Management | - Budget and Treasury - Budget and Expenditure Management - Revenue management - Assets management - Supply Chain Management |
| - Basic services and Infrastructure Development | - Infrastructure Development and Services - Water and sanitation - Roads - PMU |
| - Institutional Development and Transformation | - Human Resources and Corporate Services - Human Resources - Administration - Human Resources and Development - Legal Services - ICT - Records Management - Fleet Management - Employee Assistance and Wellness (OHS) |
| - Local Economic Development | - Local Economic Development, Planning, Rural Development and Traditional Affairs - Agriculture, Tourism and Environment - SMME Development And Job-creation - Planning - Rural Development - Traditional Services |
| - Basic services and Infrastructure Development - Local Economic Development | - Community Development Services - Education, Sports, Arts, Culture and Libraries - Disaster Management - Health Services - Social Services - Facilities Management and Thusong Services - Transport and Public Safety |

5.4 Performance Assessment and Rating by KPA and Business Unit

1st Quarter (July– September 2025)

Moretele Local Municipality 2025/2026 Q1 Planned vs Planned Achieved vs Not Achieved by Outcome ¦ Included Regional Lines. Organisational Unit; Q1. Planned; Achieved; Not Achieved; % Achieved. Office of the Municipal Manager; 17; 17; 0; 100%. Human Resources and Corporate Services; 31; 31; 0; 100%. Community Development Services; 26; 26; 0; 100%. Infrastructure Development Services; 4; 4; 0; 100%. Budget and Treasury Office; 26; 26; 0; 100%. Local Economic Development and Planning; 30; 30; 0; 100%. Office of the Mayor; 15; 15; 0; 100%. Office of the Speaker; 8; 8; 0; 100%. Office of the Single Whip; 6; 6; 0; 100%. Plan vs Achieved vs not Achieved; 163; 163; 0; 100%.

Consolidated 1st Quarter Performance

Second Quarter (October– December 2025)

| Moretele Local Municipality 2025/2026 Mid-term Planned vs Planned Achieved vs Not Achieved by Outcome |  |  |  |  |
| --- | --- | --- | --- | --- |
| Organisational Unit | Planned Targets | Planned Achieved | Not Achieved | Percentage Achieved |
| Office of the Municipal Manager | 22 | 22 | 0 | 100% |
| Human Resources and Corporate Services | 44 | 44 | 0 | 100% |
| Community Development Services | 33 | 33 | 0 | 100% |
| Infrastructure Development Services | 11 | 11 | 0 | 100% |
| Budget and Treasury Office | 26 | 26 | 0 | 100% |
| Local Economic Development and Planning | 45 | 45 | 0 | 100% |
| Office of the Mayor | 24 | 24 | 0 | 100% |
| Office of the Speaker | 4 | 4 | 0 | 100% |
| Office of the Single Whip | 7 | 7 | 0 | 100.00% |
| Total | 216 | 216 | 0 | 100% |
| Information Dated: Jan 14, 2026 1:24:00 PM |  |  |  |  |

Consolidated 2nd Quarter Performance

Mid term performance ( July- December)

| Moretele Local Municipality 2025/2026 Mid-term Planned vs Planned Achieved vs Not Achieved by Outcome |  |  |  |  |
| --- | --- | --- | --- | --- |
| Organisational Unit | Planned Targets | Planned Achieved | Not Achieved | Percentage Achieved |
| Office of the Municipal Manager | 22 | 22 | 0 | 100% |
| Human Resources and Corporate Services | 44 | 44 | 0 | 100.% |
| Community Development Services | 33 | 33 | 0 | 100% |
| Infrastructure Development Services | 11 | 11 | 0 | 100% |
| Budget and Treasury Office | 26 | 26 | 0 | 100% |
| Local Economic Development and Planning | 45 | 45 | 0 | 100% |
| Office of the Mayor | 24 | 24 | 0 | 100% |
| Office of the Speaker | 4 | 4 | 0 | 100% |
| Office of the Single Whip | 7 | 7 | 0 | 100.00% |
| Total | 216 | 210 | 6 | 100% |
| Information Dated: Jan 14, 2026 1:42:00 PM |  |  |  |  |

Consolidated Mid term performance

Moretele Local Municipality

_____________________________________________________

2025/2026

SDBIP and IDP Working Document

___________________________________

BTO

| Outcome | 7. Prudent Financial Management through improved sustainable revenue generation measures ensured |
| --- | --- |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 7.1; Output; 7.1 Enhanced municipal budgeting and budget implementation; Percentage of Total annual expenditure against total annual budget by June 2026; Annual Financial Statement; TARGET: Percentage; 100; 0; 0; 0; 0; Budget and Treasury Office; Chief Financial Officer. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 7.2; Output; 7.2 Improved financial sustainability and liability management; Percentage change in cash backed reserves reconciliation. Formula Cash backed reserves (current year) - Cash backed reserves (previous year))/ cash backed reserves (previous year) by June 2026; Annual Financial Statement; TARGET: Percentage; 0; 0; 0; 0; 0; Budget and Treasury Office; Chief Financial Officer. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 7.3; Output; 7.3 Improved liquidity management; Percentage change in cash and cash equivalent (short term). Formula Cash and cash equivalent (Current year) - cash and cash equivalent (Previous year)) / cash and cash equivalent (previous year) by June 2026; Annual Financial Statement; TARGET: Percentage; 80; 0; 0; 0; 0; Budget and Treasury Office; Chief Financial Officer. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 7.4; Output; 7.4 Improved expenditure management; Percentage of total operating expenditure on remuneration Formula Remuneration (Employee Related Costs + Councillors' Remuneration) / Total Operating Expenditure by June 2026; Section 52 Report and Annual financial statement (AFS); TARGET: Percentage; 30; 7.5; 7.5; 0; 100%; Budget and Treasury Office; Chief Financial Officer. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 7.5; Output; 7.5 Improved expenditure management; Percentage of total operating expenditure on contracted services Formula Contracted Services / Total Operating Expenditure by June 2026; Section 52 report; TARGET: Percentage; 5; 1.2; 1.2; 0; 100%; Budget and Treasury Office; Chief Financial Officer. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 7.6; Output; 7.6 Improved asset management; Percentage change of repairs and maintenance of existing infrastructure Formula Repairs and maintenance expenditure (current year) - Repairs and maintenance expenditure (previous year)) / Repairs and maintenance expenditure by June 2026; Audited AFS 4th quarter sec 52 report; TARGET: Percentage; 8; 2; 2; 0; 100%; Budget and Treasury Office; Chief Financial Officer. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 7.7; Output; 7.7 Improved supply chain management; Percentage change in the amount of irregular expenditure a result of SCM transgressions Formula Irregular Expenditure (previous year) - Irregular Expenditure (current year))/ (Irregular Expenditure (previous year) by June 2026; 1)Irregular Expenditure report (2)Audited AFS of the previous year; TARGET: Percentage; 100; 0; 0; 0; 0; Budget and Treasury Office; Chief Financial Officer. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 7.8; Output; 7.8 Improved revenue and debtors management; Percentage change in Gross Consumer Debtors (Current and Non-current) Formula: Gross Debtors - Bad Debt Provision) / Billed Revenue) Number of days in the reporting period year to date by June 2026; Age debtors analysis of current and previous year; TARGET: Percentage; 100; 0; 0; 0; 0; Budget and Treasury Office; Chief Financial Officer. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 7.9; Output; 7.9 Improved supply chain management; Percentage change in the amount of irregular expenditure a result of SCM transgressions Formula Irregular Expenditure (previous year) - Irregular Expenditure (current year))/ (Irregular Expenditure (previous year) by June 2026; (1) Irregular Expenditure report (2) Audited AFS of the previous year; TARGET: Percentage; 100; 0; 0; 0; 0; Budget and Treasury Office; Chief Financial Officer. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 7.10; Output; 7.10 Improved audit opinion; Number of submitted Financial Statements by June 2026; 1.Acknowledgement letter from AG(SA), 2, Signed of Set of AFS; TARGET: Number; 1; 1; 1; 0; 100%; Budget and Treasury Office; Chief Financial Officer. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 3000000; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 7.11; Output; 7.11 Improved audit opinion; Number of audit issues resolved as per the Audit Report by June 2026; Post audit action plan progress on issues relating to Financial statement.; TARGET: Number; 4; 1; 1; 0; 100%; Budget and Treasury Office; Chief Financial Officer. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 8000000; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |

Moretele Local Municipality

_____________________________________________________

2025/2026

SDBIP and IDP Working Document

___________________________________

CDS

| Outcome | 5. Access to safe and habitable public facilities (CDS) |
| --- | --- |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 5.2; Output; 5.2 To provide accessible and adequate cemeteries and protect from damage; Number (3) of cemeteries fenced in W2, W7 & W11 by June 2026; Completion certificate for cemetery fencing signed by 30 Jun 2026; TARGET: Number; 3; 1; 1; 0; 100%; Community Development Services; Community Development Services Director. CAPITAL: N/A; 1250000; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments; Contractor couldn't finished within the estimated time due to heavy rainfall. Contractor on site and the project is at 80% towards completion.. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 5.3; Output; 5.3 To improve access to safe and habitable public facilities through upgrading and maintaining community facilities; Number (4) Municipal Public facilities developed and maintained at Municipal DLTC Offices , Moss Mary, Ward 17 Office-Makapanstad Mogogelo and Community hall Lefatlheng by June 2026; Completion certificate and delivery note signed off by 30 June 2026; TARGET: Number; 4; 1; 1; 0; 100%; Community Development Services; Community Development Services Director. CAPITAL: N/A; 2000000; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 5.4; Output; 5.4 Development of disaster management plan; Number of (1) development of disaster management Plan by June 2026; Final copy Reviewed Disaster Management Plan; TARGET: Number; 1; 1; 1; 0; 100%; Community Development Services; Community Development Services Director. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 5.5; Output; 5.5 Community support for victims of disaster provided through various relief Materials; Percentage (100) cumulative of Disaster Relief Materials for disaster victims by June 2026; Proof of Purchase materials and Delivery notes; TARGET: Percentage; 100; 50; 50; 0; 100%; Community Development Services; Community Development Services Director. CAPITAL: N/A; 500000; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 5.6; Output; 5.6 To create an environment focused on lifting the vulnerable society through social sector meetings and awareness programs; Number of 20 Social Sector Meeting and Awareness Programs {Disability Forum, Woman & Children, Older Person, LDAC & NPO’s Forums} by June 2026; Attendance Registers and Programmes; TARGET: Number; 20; 5; 5; 0; 100%; Community Development Services; Community Development Services Director. CAPITAL: N/A; 300000; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 5.7; Output; 5.7 Improvement of sports facilities; Number of Sports Complex (2) Grandstand installed in Lebotloane and Motla Sports Complex by 30 June 2026; Completion certificate and delivery note signed off by 30 Jun 2026; TARGET: Number; 1; 0; 0; 0; 0; Community Development Services; Community Development Services Director. CAPITAL: N/A; 900000; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 5.8; Output; 5.8 Revitalization of community libraries to encourage a culture of learning; Percentages of Community libraries (100-cumulative) revitalized and maintained by June 2026; Quarterly reports on library grant spending; TARGET: Percentage; 100; 50; 50; 0; 100%; Community Development Services; Community Development Services Director. CAPITAL: N/A; 1200000; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 5.9; Output; 5.9 Community Safety programs designed and implemented in collaboration with other security cluster agencies; Number (12) of security cluster initiatives to fight crime implemented by June 2026; Attendance Registers and Programs; TARGET: Number; 12; 6; 6; 0; 100%; Community Development Services; Community Development Services Director. CAPITAL: N/A; 500000; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 5.10; Output; 5.10 Community Resilience promoted through effective disaster management activities; Percentage (100) implementation of planned disaster management activities conducted by June 2025; Q1-Q4: Attendance Register; TARGET: Percentage; 100; 50; 50; 0; 100%; Community Development Services; Community Development Services Director. CAPITAL: N/A; 500000; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 5.11; Output; 5.11 Health Awareness programs designed and implemented in collaboration with other Dept of Health and health agencies; Number of (08) community health awareness campaigns held by June 2026; Programs & Attendance Registers; TARGET: Number; 8; 2; 2; 0; 100%; Community Development Services; Community Development Services Director. CAPITAL: N/A; 200000; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Outcome | 6. Participation in sports and recreation maximized |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 6.1; Output; 6.1: Sports and Recreational activities undertaken by June 2026; Percentage (100), quarterly of Sports & Recreational activities undertaken by June 2026; Attendance Register and Programs; TARGET: Percentage; 100; 50; 50; 0; 100%; Community Development Services; Community Development Services Director. CAPITAL: N/A; 1000000; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |

Moretele Local Municipality

_____________________________________________________

2025/2026

SDBIP and IDP Working Document

___________________________________

HR

| Outcome | 14. Professional institutional development and transformation through improved human resources systems and technology promoted and enhanced |
| --- | --- |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 14.1; Output; 14.1 Approval of HR Policies and Unit based policies; Percentage (100) of HR related Policies and units based policies developed, reviewed and approved by June 2026; Q2-Q4: Council Resolution on Approved Policies; TARGET: Percentage; 100; 100; 100; 0; 100%; Human Resources and Corporate Services; Director Human Resource and Corporate Services. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Technical Indicator Description. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 14.2; Output; 14.2 Review Staff Establishment; Number (1) of Reviewed and Approved Staff Establishment by June 2026; Q4: Signed Copy of Approved Reviewed Staff Establishment; TARGET: Number; 1; 0; 0; 0; 0; Human Resources and Corporate Services; Director Human Resource and Corporate Services. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Technical Indicator Description. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 14.3; Output; 14.3 Filling of Critical Vacant Senior Managers Position; Number (2) of Senior Managers appointed by June 2026; Q4: Council Resolution on Appointment of Senior Managers; TARGET: Number; 2; 0; 0; 0; 0; Human Resources and Corporate Services; Director Human Resource and Corporate Services. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Technical Indicator Description. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 14.4; Output; 14.4 Staff Appointments; Percentage (100) of staff Appointments by June 2026; Q2- Q4: Signed Recruitment Files & Appointment Letters; TARGET: Percentage; 100; 50; 50; 0; 100%; Human Resources and Corporate Services; Director Human Resource and Corporate Services. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Technical Indicator Description. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 14.5; Output; 14.5 Enhanced measures and systems that create safe working conditions as prescribed for in OHSA/COIDA; Number (2) implementation of planned OHSA/COIDA-related initiatives by June 2026; Q2 and Q4: Risk Assessment or Site Inspection or Medical Surveillance reports; TARGET: Number; 2; 1; 1; 0; 100%; Human Resources and Corporate Services; Director Human Resource and Corporate Services. CAPITAL: N/A; 250000; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Technical Indicator Description. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 14.6; Output; 14.6 Workplace Skills Plan implemented to promote employee development and professional growth; Percentage (100) implementation of Workplace Skills Plan initiatives by June 2026; Q1-Q4: Attendance registers or results or academic records or Proof of payments; TARGET: Percentage; 100; 100; 100; 0; 100%; Human Resources and Corporate Services; Director Human Resource and Corporate Services. CAPITAL: N/A; 2.6; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Technical Indicator Description. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 14.8; Output; 14.8 Communication of Council Resolutions to Senior Managers; Percentage (100%) of Council Resolution Register updated and circulated to Senior Managers by June 2026; Q1-Q4: Signed Updated Council Resolution Register Acknowledgment of Receipt; TARGET: Percentage; 100; 0; 0; 0; 0; Human Resources and Corporate Services; Director Human Resource and Corporate Services. CAPITAL: N/A; 2000000; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Technical Indicator Description. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 14.9; Output; 14.9 Security and access control; Percentage (100%) provision of security and access control services by June 2026; Q1-Q4: Quarterly security, assessment reports and monthly OB entries; TARGET: Percentage; 100; 100; 100; 0; 100%; Human Resources and Corporate Services; Director Human Resource and Corporate Services. CAPITAL: N/A; 35.6; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Technical Indicator Description. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 14.10; Output; 14.10 Service and governance systems improved through the implementation of Information and communication technology and manage legal activities; Percentage (100) implementation of planned information and communication technology initiatives and legal activities by June 2026; Q1-Q4: Compliance Certificates or copies of reports; TARGET: Percentage; 100; 100; 100; 0; 100%; Human Resources and Corporate Services; Director Human Resource and Corporate Services. CAPITAL: N/A; 16.8; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Technical Indicator Description. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 14.11; Output; 14.11 Employee Wellness initiatives Promoted; Percentage (100) of Employee Wellness/Campaigns initiatives held June 2026; Q1-Q4 Attendance Register and Reports; TARGET: Percentage; 100; 100; 100; 0; 100%; Human Resources and Corporate Services; Director Human Resource and Corporate Services. CAPITAL: N/A; 62000; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Technical Indicator Description. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 14.12; Output; 14.12 Good records keeping and access to information promoted for a better Audit Opinion through the implementation of Records Management legislative compliant systems; Percentage (100) implementation of planned records keeping and access to information initiatives (Records Management legislative compliant systems by June 2026; Q1 - Q4 Reports; TARGET: Percentage; 100; 100; 100; 0; 100%; Human Resources and Corporate Services; Director Human Resource and Corporate Services. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Technical Indicator Description. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 14.13; Output; 14.13 Institutionalization of Risk Management; 100% of Risk Treatment Plans resolved by June 2026; Q1-Q4: Risk Reports; TARGET: Percentage; 100; 100; 100; 0; 100%; Human Resources and Corporate Services; Director Human Resource and Corporate Services. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Technical Indicator Description. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 14.14; Output; 14.14 Post Audit Action Plan to address all the audit findings of AGSA and Internal Audit implemented; 100% of Findings resolved by June 2026; Q3-Q4: Post Audit Action Plan; TARGET: Percentage; 100; 0; 0; 0; 0; Human Resources and Corporate Services; Director Human Resource and Corporate Services. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Technical Indicator Description. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 14.15; Output; 14.15 Harmonious Employer Employee Relations; Number (04) of LLF Meetings held by June 2026; Q1-Q4: Attendance Register; TARGET: Number; 4; 1; 1; 0; 100%; Human Resources and Corporate Services; Director Human Resource and Corporate Services. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Technical Indicator Description. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 14.16; Output; 14.16 Submission of the Annual Employment Equity Report to Department of Employment & Labour; Number(1) of EE Report submitted to Department of Employment & Labour by June 2026; Q3: Submission/Acknowledgement Letter; TARGET: Number; 1; 0; 0; 0; 0; Human Resources and Corporate Services; Director Human Resource and Corporate Services. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Technical Indicator Description. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 14.17; Output; 14.17 Promote conducive working environment; Percentage (100), of over grown grass cutting and reconciliation of overtime claims and the work output by June 2026; Pictures and consolidated overtime claim reports; TARGET: Percentage; 100; 100; 100; 0; 100%; Human Resources and Corporate Services; Director Human Resource and Corporate Services. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Technical Indicator Description. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 14.18; Output; 14.18 Promote and support the maintenance and repairs of municipal fleet by June 2026; Percentage (100) of maintenance and repairs of municipal fleet by June 2026; Maintenance and repairs reports; TARGET: Percentage; 100; 100; 100; 0; 100%; Human Resources and Corporate Services; Director Human Resource and Corporate Services. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Technical Indicator Description. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |

Moretele Local Municipality

_____________________________________________________

2025/2026

SDBIP and IDP Working Document

___________________________________

IDS

| Outcome | 1. Optimised access to water services |
| --- | --- |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 1.1; Output; 1.1 Water supply to Moeka, (Ga Motle, Ratsiepane, Kromkuil, Mmakaunyane, Norokie) with reticulation and yard connections Schedule C; Number (620) provision of water services with yard connections and reticulations to Moeka, (Ga-Motle, Ratsiepane, Kromkuil, Mmakaunyane, Norokie by September 2025; Progress reports & Completion certificate; TARGET: Number; 620; 0; 0; 0; 0; Infrastructure Development Services; Infrastructure Development Services Director. CAPITAL: N/A; 20000000; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments; The project was substantially completed in September 2025, with the identified snag list addressed and the completion certificate subsequently issued.. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 1.2; Output; Water supply to Moeka, (Ga Motle, Ratsiepane, Kromkuil, Mmakaunyane, Norokie) with reticulation and yard connections Schedule C; Number of Yard connections in Motle,Moeka Ratsiepane, Kromkuil, Mmakaunyane, Norokie by September 2025; Q4: Completion certificates; TARGET: Number; 620; 0; 0; 0; 0; Infrastructure Development Services; Infrastructure Development Services Director. CAPITAL: N/A; 21467118.92; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 1.3; Output; 1.3 Water Reticulation & Yard Connection: Drilling & equipping of 2 boreholes, Refurbishment of 254KL elevated steel tank 5km reticulation pipeline, 200 yard connections; Number (200) provision of basic water through yard connection in Ward 12 by June 2026; Progress reports and completion certificates; TARGET: Number; 200; 0; 0; 0; 0; Infrastructure Development Services; Infrastructure Development Services Director. CAPITAL: N/A; 1890856.51; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Outcome | 2. Human dignity enhanced through adequate sanitation |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 2.1; Output; 2.1 Construction of Ablution facilities in various wards; Number (400) provision of basic sanitation services in Ward 4 by March 2026; Progress report and completion certificate; TARGET: Number; 400; 400; 400; 0; 100%; Infrastructure Development Services; Infrastructure Development Services Director. CAPITAL: N/A; 31582143; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments; The project is complete. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 2.2; Output; 2.2 Construction of Ablution facilities in various wards; Number (450) provision of basic sanitation in Ward 7 by March 2026; Progress report and completion certificate; TARGET: Number; 450; 450; 450; 0; 100%; Infrastructure Development Services; Infrastructure Development Services Director. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments; The project is complete.. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 2.3; Output; 2.3 Construction of Ablution facilities in various wards; Number (214) provision of basic sanitation in Ward 26 constructed by March 2026; Progress report and completion certificate; TARGET: Number; 214; 0; 0; 0; 0; Infrastructure Development Services; Infrastructure Development Services Director. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments; None. Line Manager Comments. |
| Outcome | 3. Integrated and safe road networks promoted and ensured |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 3.1; Output; 3.1: Paved roads & stormwater drainage constructed in ward 11 (Mogogelo); Km (1) of road paved by June 2026 in ward 11; Progress Report, Completion Certificate; TARGET: KM; 1; 0; 0; 0; 0; Infrastructure Development Services; Infrastructure Development Services Director. CAPITAL: N/A; 9030700; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 3.2; Output; 3.2 Paved roads & stormwater drainage constructed in ward18; Km (1) of Pavement by June 2026 in ward ward 18; Progress report and completion certificate; TARGET: KM; 1; 0; 0; 0; 0; Infrastructure Development Services; Infrastructure Development Services Director. CAPITAL: N/A; 10000000; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments; None. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 3.3; Output; 3.3 Paved roads & stormwater drainage constructed in ward 17; Km (1) of road paved by June 2026 in ward 17; Progress report and completion certificate; TARGET: KM; 1; 0; 0; 0; 0; Infrastructure Development Services; Infrastructure Development Services Director. CAPITAL: N/A; 10000000; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments; None. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 3.4; Output; 3.4 Paved roads & stormwater drainage constructed in ward 22; Km (1) of road paved with stormwater by June 2026 in Ward 22; Progress report and completion certificate; TARGET: KM; 1; 0; 0; 0; 0; Infrastructure Development Services; Infrastructure Development Services Director. CAPITAL: N/A; 10000000; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments; None. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 3.5; Output; 3.5 Implementation of Lebotlwane, Thulare Bridge in Ward 4; Percentage (100) Implementation of Lebotlwane, Thulare Bridge in Ward 4 by June 2026; Progress Reports and Completion Certificate; TARGET: Percentage; 100; 0; 0; 0; 0; Infrastructure Development Services; Infrastructure Development Services Director. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Outcome | 4. Public safety enhanced through sustainable public lighting |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 4.1; Output; 4.1 Community lighting erected for improved public safety in ward 8; Number (8) of high mast-lights erected by June 2026 in Ward 8; Progress report and completion certificate; TARGET: Number; 8; 0; 0; 0; 0; Infrastructure Development Services; Infrastructure Development Services Director. CAPITAL: N/A; 5500000; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments; None. Line Manager Comments. |

Moretele Local Municipality

_____________________________________________________

2025/2026

SDBIP and IDP Working Document

___________________________________

LED

| Outcome | 10. The economic potential development of Tourism in the area maximised |
| --- | --- |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 10.1; Output; 10.1 Tourism Development and supported; Number 3 of Tourism projects supported by June 2026; Completion certificate, delivery notes, and acknowledgement of beneficiaries; TARGET: Number; 3; 1; 1; 0; 100%; Local Economic Development and Planning; Director Local Economic Development. CAPITAL: N/A; 709.71; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Outcome | 11. Compliance with Town Planning Legislations/policies/regulations |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 11.1; Output; 11.1 Land use survey initiatives; Number (4) of milestone to be achieved for land use survey by June 2026; Draft land use survey report; TARGET: Number; 4; 3; 3; 0; 100%; Local Economic Development and Planning; Director Local Economic Development. CAPITAL: N/A; 32500; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 11.2; Output; 11.2 Feasibility study on all MLM incomplete land tenure upgrading Project closure by June 2026; Number (2) Feasibility study on all MLM incomplete land tenure upgrading Project closure by June 2026; Final feasibility study report with cost estimations; TARGET: Number; 2; 1; 1; 0; 100%; Local Economic Development and Planning; Director Local Economic Development. CAPITAL: N/A; 480000; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments; None. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 11.3; Output; 11.3 Delivery, supply, installation and commissioning of GIS by June 2026; Number (5) of milestone for delivery, supply, installation and commissioning of GIS by June 2026; Training session attendance register, training report, Report of Database maintenance and Database management; TARGET: Number; 5; 1; 1; 0; 100%; Local Economic Development and Planning; Director Local Economic Development. CAPITAL: N/A; 1031000; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 11.4; Output; 11.4 Demarcation of sites by June 2026; Number (11) of milestone for sites demarcation by June 2026; Proof of application submission, acknowledgement letter from the Municipality, assessment report from the Municipality, Newspaper notice, final comments from sector departments (Dep of Agriculture, public works, mineral resources and energy, decision on application, Proof of submission of general plan to Surveyor Generalâ€™s Office and completion letter for pegging and closure report; TARGET: Number; 11; 0; 0; 0; 0; Local Economic Development and Planning; Director Local Economic Development. CAPITAL: N/A; 1270000; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 11.5; Output; 11.5 Land use and land development awareness workshops; Number (4) of land use awareness workshops conducted by June 2026; Attendance registers and minutes; TARGET: Number; 4; 1; 1; 0; 100%; Local Economic Development and Planning; Director Local Economic Development. CAPITAL: N/A; 7308000; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 11.6; Output; 11.6 Formalization of MLM incomplete land tenure projects; Number (6) settlements transferred after formalization processes by June 2026; Transfer of titles report; TARGET: Number; 6; 0; 0; 0; 0; Local Economic Development and Planning; Director Local Economic Development. CAPITAL: N/A; 835200; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons; Unplanned. Corrective Actions; None. Employee Comments; None. Line Manager Comments. |
| Outcome | 12. Minimise environmental damage through temporary job creation |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 12.1; Output; 12.1 Minimize the unemployment rate in Moretele through the EPWP initiatives; Number (390) of jobs created through Phepafatsa Moretele Project by June 2026; Monthly reports and attendance registers; TARGET: Number; 390; 0; 0; 0; 0; Local Economic Development and Planning; Director Local Economic Development. CAPITAL: N/A; 10764026.26; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons; Unplanned. Corrective Actions; None. Employee Comments; None. Line Manager Comments. |
| Outcome | 13. Minimize the environmental damage through maximizing compliance to address the environmental issues that have a direct and indirect impact on the natural environment |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 13.1; Output; 13.1 Acquire the license for Makapanstad Landfill site; Number (1) of landfill site license acquired from DEDECT by June 2026; License and business plan; TARGET: Number; 1; 0; 0; 0; 0; Local Economic Development and Planning; Director Local Economic Development. CAPITAL: N/A; 5000000; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons; Unplanned. Corrective Actions; None. Employee Comments; None. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 13.2; Output; 13.2 Cleaning of illegal dump hotspots; Number (26) Wards with weekly cleaning of illegal dump hotspots by June 2026; Monthly signed cleaning of illegal dumps reports, including pictures by service, Councillors, and the Environmental Officer; TARGET: Number; 26; 26; 26; 0; 100%; Local Economic Development and Planning; Director Local Economic Development. CAPITAL: N/A; 8769.6; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 13.3; Output; 13.3 Wards with access to weekly waste removal services; Number (26) wards with access to weekly waste removal services by June 2026; Monthly signed waste collection reports, including pictures by service, Councillors, and the Environmental Officer; TARGET: Number; 26; 26; 26; 0; 100%; Local Economic Development and Planning; Director Local Economic Development. CAPITAL: N/A; 31000000; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 13.4; Output; 13.4 Wards with weekly skip bins maintenance; Number (26) Wards with weekly skip-bins maintenance by June 2026; Monthly signed skip bins maintenance reports, including pictures by service, Councillors, and the Environmental Officer; TARGET: Number; 26; 26; 26; 0; 100%; Local Economic Development and Planning; Director Local Economic Development. CAPITAL: N/A; 6614784; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 13.5; Output; 13.5 Closure and rehabilitation of Ga motla dumpsite; Number (1) Closure and rehabilitation of Ga-motla dumpsite by June 2026; Final Closure and Rehabilitation Plan, Closure license; TARGET: Number; 1; 0; 0; 0; 0; Local Economic Development and Planning; Director Local Economic Development. CAPITAL: N/A; 5000000; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Outcome | 8. The economic potential and growth of the local economy through innovation and improved economic performance maximised |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 8.1; Output; 8.1 LED awareness workshops and campaigns; Number (4) of LED awareness workshops and campaigns conducted by June 2026; Attendance registers and minutes; TARGET: Number; 4; 1; 1; 0; 100%; Local Economic Development and Planning; Director Local Economic Development. CAPITAL: N/A; 203630.11; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions; None. Employee Comments; None. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 8.2; Output; 8.2 LED Strategy reviewed; Number (1) of LED Strategy reviewed by June 2026; Reviewed LED Strategy; TARGET: Number; 1; 1; 1; 0; 100%; Local Economic Development and Planning; Director Local Economic Development. CAPITAL: N/A; 200000; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions; None. Employee Comments; None. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 8.3; Output; 8.3 Developing Business by law; Number (1) of by-laws promulgated and gazetting business by-laws by June 2026; Copy of the gazette business by-law; TARGET: Number; 1; 0; 0; 0; 0; Local Economic Development and Planning; Director Local Economic Development. CAPITAL: N/A; 312782.4; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons; Unplanned. Corrective Actions; None. Employee Comments; None. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 8.4; Output; 8.4 SMME Development and support; Number (5) of SMME’s projects developed and supported by June 2026; Application form, approval letter, completion certificates, delivery notes and reports; TARGET: Number; 5; 1; 1; 0; 100%; Local Economic Development and Planning; Director Local Economic Development. CAPITAL: N/A; 751.89; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions; None. Employee Comments; None. Line Manager Comments. |
| Outcome | 9. The economic potential and growth of Agriculture as a critical economic anchor in the local economy maximised |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 9.1; Output; 9.1 Agriculture Development and support; Number 07 0f Agricultural Projects developed and supported by June 2026; Appointment letter, pictures, completion certificates and acknowledgement letters from beneficiaries.; TARGET: Number; 7; 1; 1; 0; 100%; Local Economic Development and Planning; Director Local Economic Development. CAPITAL: N/A; 1585.78; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions; None. Employee Comments; None. Line Manager Comments. |

Moretele Local Municipality

_____________________________________________________

2025/2026

SDBIP and IDP Working Document

___________________________________

OFFICE OF THE MAYOR

| Outcome | 18. Promote participatory development and local democracy through effective oversight |
| --- | --- |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.5; Output; 18.5 Implementation of IGR & Protocol Initiatives; Percentage (100) Implementation of IGR & Protocol Initiatives by June 2025; attendance registers or Pictures; TARGET: Percentage; 100; 100; 100; 0; 100%; Office of the Mayor; Protocol & IGR Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.6; Output; 18.6 Promotion and empowerment of Women by June 2026; Percentage (100) of Women empowerment initiatives by June 2026; Q1-Q4 Reports; TARGET: Percentage; 100; 100; 100; 0; 100%; Office of the Mayor; Manager- Office of Mayor. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.7; Output; 18.7 Promotion and support of people living with disability BY June 2026; Percentage (100) of support of people living with disabilities by June 2026; Q1-Q4 Reports; TARGET: Percentage; 100; 100; 100; 0; 100%; Office of the Mayor; Special Projects Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.8; Output; 18.8 Promotion of Social Cohesion through celebrating National Days by June 2025; Percentage of Social Cohesion through celebrating National Days initiatives implemented by June 2026; Attendance registers and pictures; TARGET: Percentage; 100; 100; 100; 0; 100%; Office of the Mayor; Special Projects Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.9; Output; 18.9 Promotion and empowerment of the Youth by June 2026; Percentage (100) of Youth empowerment initiatives by June 2026; Q1-Q4 Reports; TARGET: Percentage; 100; 100; 100; 0; 100%; Office of the Mayor; Special Projects Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.11; Output; 18.11 Promotion of Active Involvement, Good Governance and Public Participation; Percentage(100) of good government and Public participation initiative held by June 2026; Attendance Registers, Reports & Pictures; TARGET: Percentage; 100; 100; 100; 0; 100%; Office of the Mayor; Manager- Office of Mayor. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Output | 18.5 Implementation of IGR & Protocol Initiatives |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.5.1; Activity; 18.5.1 Promotion of social cohesion and good governance by June 2026; Number (3) Mayorâ€™s Stakeholders Outreach Engagements session held by June 2026; Attendance Registers & Pictures; TARGET: Number; 3; 1; 1; 0; 100%; Office of the Mayor; Protocol & IGR Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 400000; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.5.2; Activity; 18.5.2 Strengthening the relationship between the Municipality and Magosi; Number (3) of Engagement Session with Magosi and Traditional Council held by June 2026; Attendance Registers & Pictures; TARGET: Number; 3; 1; 1; 0; 100%; Office of the Mayor; Protocol & IGR Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 400000; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Output | 18.6 Promotion and empowerment of Women by June 2026 |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.6.1; Activity; 18.6.1 Hold Womenâ€™s Day Celebration by June 2026; Number (1) Women Seminar held by June 2026; Attendance registers and pictures; TARGET: Number; 0; 0; 0; 0; 0; Office of the Mayor; Special Projects Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 200000; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.6.2; Activity; 18.6.2 Provide Support to Women Projects by June 2026; Number (2) of Women Projects Supported by June 2026; Attendance registers and pictures; TARGET: Number; 2; 0; 0; 0; 0; Office of the Mayor; Special Projects Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 400000; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Output | 18.7 Promotion and support of people living with disability BY June 2026 |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.7.1; Activity; 18.7.1 Provide Disability Projects Support by June 2026; Number (1) of Casual Day Celebration; Pictures and Attendance Register; TARGET: Number; 1; 0; 0; 0; 0; Office of the Mayor; Special Projects Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 125000; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.7.2; Activity; 18.7.2 Engagement with People with Disability; Number (2) Disability Forum Meetings and Programs by June 2026; Attendance registers and pictures; TARGET: Number; 2; 1; 1; 0; 100%; Office of the Mayor; Special Projects Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 125000; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.7.3; Activity; 18.7.3 Provide People with Disability Projects Support by June 2026; Number (1) of Disability Projects Supported by June 2026; Profile of projects, acknowledgement of receipt; TARGET: Number; 1; 0; 0; 0; 0; Office of the Mayor; Special Projects Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 100000; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Output | 18.8 Promotion of Social Cohesion through celebrating National Days by June 2025 |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.8.1; Activity; 18.8.1 Promotion of Social Cohesion through celebrating National Days by September 2025; Number (1) of Heritage Day Celebration September 2025; Attendance registers and pictures; TARGET: Number; 1; 0; 0; 0; 0; Office of the Mayor; Special Projects Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 200000; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.8.2; Activity; 18.8.2 Promotion of Social Cohesion through celebrating National Days by June 2026; Number (1) of Women's Month Commemoration by June 2026; Attendance registers and pictures; TARGET: Number; 1; 0; 0; 0; 0; Office of the Mayor; Special Projects Manager. CAPITAL: Capex; 0; 0; 0; 0; 0. OPERATING: N/A; 200000; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.8.3; Activity; 18.8.3 Promotion of Social Cohesion through celebrating National Days by June 2026; Number (1) of World Aids Days celebrated by July 2026; Attendance registers and pictures; TARGET: Number; 1; 1; 1; 0; 100%; Office of the Mayor; Special Projects Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 15000; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.8.4; Activity; 18.8.4 Promotion of Social Cohesion through celebrating National Days by June 2026; Number (1) of 16 Days of Activism of Abuse Against Women and Child Abuse celebrated by December 2025; Attendance registers and pictures; TARGET: Number; 1; 1; 1; 0; 100%; Office of the Mayor; Special Projects Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Output | 18.9 Promotion and empowerment of the Youth by June 2026 |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.9.1; Activity; 18.9.1 Train Youth to be Artisans to create jobs by June 2026; Number (15) of Youth to be trained as artisans; Q2-Q4 Attendance register & Reports; TARGET: Number; 15; 15; 15; 0; 100%; Office of the Mayor; Special Projects Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 750000; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.9.2; Activity; 18.9.2 Youth Council Engagement Session by June 2026; Host (1) Youth Council Engagement by June 2026; Attendance register, report and pictures; TARGET: Percentage; 100; 100; 100; 0; 100%; Office of the Mayor; Special Projects Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 100000; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.9.3; Activity; 18.9.3 Host Career Development Program by June 2026; Number (1) Career Exhibition in partnership with Dept of Education) by June 2026; Attendance registers and pictures; TARGET: Number; 1; 0; 0; 0; 0; Office of the Mayor; Special Projects Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 200000; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.9.5; Activity; 18.9.5 Conduct Back to School Campaign in partnership with Dept of Education by March 2026; Number (1) of Back-to-School Campaigns conducted in partnership with Dept of Education (Distribution of 200 shoes, and 500 cares packs) by March 2026; List of Schools and Pictures; TARGET: Number; 1; 0; 0; 0; 0; Office of the Mayor; Special Projects Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 200000; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.9.6; Activity; 18.9.6 Issuing, submission and capturing of 2026 academic year Bursary applications by December 2025; Percentage (100) completion of issuing, submitting and capturing of 2026 academic bursaries for 30 Youth by December 2025; Registration letters, Report; TARGET: Number; 100; 100; 100; 0; 100%; Office of the Mayor; Special Projects Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 1200000; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments; Capturing is on-going as the closing date for submission is 16 January 2026. Attached is the acknowledgement of receipt form for prospective students. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.9.7; Activity; 18.9.7 Selection and Payments of 2026 bursaries by June 2026; Percentage (100) completion of selection and payments for 2026 academic bursaries for 30 Youth by June 2026; Registration letters, Report; TARGET: Percentage; 100; 0; 0; 0; 0; Office of the Mayor; Special Projects Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.9.9; Activity; 18.9.9 Hold Youth Month Commemoration Program by June 2026; Number (1) of Cluster Program held by June 2026; Attendance registers and pictures; TARGET: Number; 1; 0; 0; 0; 0; Office of the Mayor; Special Projects Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Output | 18.11 Promotion of Active Involvement, Good Governance and Public Participation |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.11.2; Activity; 18.11.2 Conduct Mayor Oversight visits by June 2026; Number (4) of Mayors Oversights visits and Service Delivery Accelerated Programs (Netefatso Program) by June 2026; Attendance Registers, Reports & Pictures; TARGET: Number; 4; 1; 1; 0; 100%; Office of the Mayor; Special Projects Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 100; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.11.3; Activity; 18.11.3 Promotion of the rights of Senior Citizen by June 2025; Number (2) of Senior Citizens support Programs by June 2026; Attendance Registers, Reports & Pictures; TARGET: Number; 2; 1; 1; 0; 100%; Office of the Mayor; Special Projects Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 200; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.11.4; Activity; 18.11.4 Prepare consolidated quarterly Call Center Reports by June 2026; Number (12) of quarterly Call Center Reports consolidated and submitted by June 2026; Q1-Q4: Copies of monthly reports; TARGET: Number; 12; 3; 3; 0; 100%; Office of the Mayor; Special Projects Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.11.5; Activity; 18.11.5 Provide vulnerable families with food parcels by June 2026; Number (1040) of vulnerable households supported with food parcels by June 2026; Beneficiary list per ward Q1-Q4; TARGET: Number; 0; 260; 260; 0; 100%; Office of the Mayor; Special Projects Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 2200000; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.11.6; Activity; 18.11.6 Promotion and support of destitute 02 families by June 2026; Percentage (100) promotion and support of selected destitute 02 families by June 2026; Pictures and confirmation of receipt by beneficiaries; TARGET: Percentage; 100; 0; 0; 0; 0; Office of the Mayor; Special Projects Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 300; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.11.7; Activity; 18.11.7 Hosting of local IGR Forums by June 2026; Number (2) of Local IGR Forums held by June 2026; Attendance Registers, Reports & Pictures; TARGET: Number; 2; 1; 1; 0; 100%; Office of the Mayor; Protocol & IGR Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 100; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.11.8; Activity; 18.11.8 Promotion of National Calendar Events; Number (5) of Calendar Events held (1 x Mandela day Project, Festive Prayer Day, Human Rights Day, 1 Pre-Easter by June 2026; Attendance Registers, Reports & Pictures; TARGET: Number; 5; 1; 1; 0; 100%; Office of the Mayor; Special Projects Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |

Moretele Local Municipality

_____________________________________________________

2025/2026

SDBIP and IDP Working Document

___________________________________

OFFICE OF THE MUNICIPAL MANAGER

| Output | 14.10 Service and governance systems improved through the implementation of Information and communication technology and manage legal activities |
| --- | --- |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 14.10.5; Activity; 14.10.5 Professional institutional development and transformation through provision of legal advice and guidance to the Municipality; Percentage (100) implementation of legal advice and guidance provided by June 2025; Q3-Q4: Reports; TARGET: Percentage; 100; 0; 0; 0; 0; Office of the Municipal Manager; Legal Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 14.10.6; Activity; 14.10.6 Professional institutional development and transformation through conducting of legal research to identify potential risk associated with Municipality; Percentage (100) of legal research conducted by June 2026; Q3-Q4: reports; TARGET: Percentage; 100; 0; 0; 0; 0; Office of the Municipal Manager; Legal Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 14.10.7; Activity; 14.10.7 Professional institutional development and transformation through engagement with stakeholders to develop strategies and policies to ensure compliance with law; Percentage (100 engagement with stakeholders by June 2026; Q3-Q4 Reports; TARGET: Percentage; 100; 0; 0; 0; 0; Office of the Municipal Manager; Legal Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 14.10.8; Activity; 14.10.8 Professional institutional development and transformation through effective management of litigation cases; Percentage (100 of litigation cases managed by June 2026; Q3-Q4 Report; TARGET: Percentage; 100; 0; 0; 0; 0; Office of the Municipal Manager; Legal Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 14.10.9; Activity; 14.10.9 Professional institutional development and transformation through working with internal departments to develop measures that align business practices with legal requirements; Percentage (100) of engagements with internal departments by June 2026; Q3-Q4 Reports; TARGET: Percentage; 100; 0; 0; 0; 0; Office of the Municipal Manager; Legal Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Outcome | 15. Improved institutional development, transformation, and good governance outcomes through implementation of Performance Management |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 15.1; Output; 15.1 Annual Report consistent with Circular 63 (National Treasury) prepared; Number (1) of 2024/2025 Annual Report approved by January 2026; Q1-Q4: Report; TARGET: Number; 1; 0; 0; 0; 0; Office of the Municipal Manager; PMS Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Outcome | 16. Efficient and effective Audit Management functions provided |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 16.1; Output; 16.1 Risk based internal Audit Plan developed; Number of Internal Audit Plans approved by September 2025; Q4: Approved Internal Audit Plan by Audit Committee Q1: minutes of the audit committee; TARGET: Number; 1; 0; 0; 0; 0; Office of the Municipal Manager; Internal Audit Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 16.2; Output; 16.2 Work and Audit Committee recommendations accounted to council; Number (4) of Audit Committee reports submitted to Council by June 2025; Q1-Q4: Council resolutions; TARGET: Number; 4; 1; 1; 0; 100%; Office of the Municipal Manager; Internal Audit Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Outcome | 17. Efficient and effective Risk Management functions provided |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 17.1; Output; 17.1 Fraud Management Plan developed and approved; Number (1) Fraud Management Plan developed by September 2025; Approved Fraud Management Plan; TARGET: Number; 1; 0; 0; 0; 0; Office of the Municipal Manager; Risk Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 17.2; Output; 17.2 Risk Management Plan developed and approved; Number (1) of Risk Management Plan developed by September 2025; Approved Risk Management Plan; TARGET: Number; 1; 0; 0; 0; 0; Office of the Municipal Manager; Risk Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Outcome | 18. Promote participatory development and local democracy through effective oversight |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.1; Output; 18.1 IDP reviewed in accordance with approved Process Plan; Percentage (100) of 2026/2027 IDP Reviewed and approved by June 2026; Q4: Copy of 2026/2027 IDP; TARGET: Percentage; 100; 0; 0; 0; 0; Office of the Municipal Manager; IDP Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.2; Output; 18.2 Communication Strategy developed and implemented; Number (1) of Communication Strategy developed and implemented to improve communication and its credibility by June 2026; Copy of communication strategy; TARGET: Number; 1; 0; 0; 0; 0; Office of the Municipal Manager; Communications Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 100000; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.4; Output; 18.4 Communities and interested stakeholders engaged on the 2024/2025 Annual Report; Percentage (100) of 2024/2025 Annual Oversight Report approved by June 2026; Q3: Council resolution; TARGET: Percentage; 100; 0; 0; 0; 0; Office of the Municipal Manager; MPAC Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Output | 15.1 Annual Report consistent with Circular 63 (National Treasury) prepared |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 15.1.1; Activity; 15.1.1 2025 /2026 Performance agreements finalised and signed by Senior Managers; Number (6) of signed performance agreements for Senior Managers by September 2025; Q1: Copies of signed Performance Agreements; TARGET: Number; 6; 0; 0; 0; 0; Office of the Municipal Manager; PMS Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 15.1.2; Activity; 15.1.2 Preparation and approval of the Annual Report; Percentage (100) completion of the preparation and approval of 2024/2025 Annual Report approved by January 2026; Q3: Copy of Annual Report; TARGET: Percentage; 100; 0; 0; 0; 0; Office of the Municipal Manager; PMS Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 15.1.3; Activity; 15.1.3 Implement initiatives performance management organisational wide through Performance Management System; Percentage (100) of Individual performance management cascading initiatives through performance management System implemented by June 2026; Q3: Quarterly Reports; TARGET: Percentage; 100; 0; 0; 0; 0; Office of the Municipal Manager; PMS Manager. CAPITAL: N/A; 2.2; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 15.1.4; Activity; 15.1.4 Conduct quarterly performance reviews for all section 56/57 employees; Number (2) of individual (section 54/56 managers) performance reviews conducted by June 2025; Q3&Q4: Performance Review Report; TARGET: Number; 2; 0; 0; 0; 0; Office of the Municipal Manager; PMS Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 15.1.5; Activity; 15.1.5 Conduct PMS policy review; Percentage (100) completion of PMS policy review and approval by June 2026; Q4: Council Approved Copy of the policy; TARGET: Percentage; 100; 0; 0; 0; 0; Office of the Municipal Manager; PMS Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 15.1.6; Activity; 15.1.6 Preparation and approval of the SDBIP; Percentage (100) completion of the preparation and approval of the 2025/2026 signed by the Mayor by June 2026; Q4: Copy of the SDBIP; TARGET: Percentage; 100; 0; 0; 0; 0; Office of the Municipal Manager; PMS Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 15.1.7; Activity; 15.1.7 Prepare consolidated quarterly performance report; Number (4) of quarterly performance reports tabled and approved by June 2026; Q1-Q4: Council Resolutions; TARGET: Number; 4; 1; 1; 0; 100%; Office of the Municipal Manager; PMS Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 15.1.8; Activity; 15.1.8 IDP REP Forum Capacity Building; Number (1) of IDP Capacity Building by December 2025; Q2 Attendance register; TARGET: Number; 1; 1; 1; 0; 100%; Office of the Municipal Manager; PMS Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 15.1.9; Activity; 15.1.9 IDP/PMS Operations equipment procured; Number (1) Projector and Sound system procured by July 2025; Q1 Delivery note; TARGET: Number; 1; 0; 0; 0; 0; Office of the Municipal Manager; PMS Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 15.1.10; Activity; 15.1.10 PMS Strategic session; Number (1) of IDP Strategic sessions held by March 2026; Q3 A attendance register; TARGET: Number; 1; 0; 0; 0; 0; Office of the Municipal Manager; PMS Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Output | 16.1 Risk based internal Audit Plan developed |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 16.1.1; Activity; 16.1.1 Preparation of the Internal Audit Plan; Percentage (100) completion of the preparation of the Internal Audit Plans September 2025; Q1 Approved Internal Audit Plan by Audit Committee; TARGET: Percentage; 100; 0; 0; 0; 0; Office of the Municipal Manager; Internal Audit Manager. CAPITAL: N/A; 1027193.08; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 16.1.2; Activity; 16.1.2 Approval of the Internal Audit Plan; Number of Internal Audit Plans approved by September 2025; Q4: Approved Internal Audit Plan by Audit Committee Q1: minutes of the audit committee and the approved audit plan; TARGET: Number; 1; 0; 0; 0; 0; Office of the Municipal Manager; Internal Audit Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Output | 16.2 Work and Audit Committee recommendations accounted to council |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 16.2.1; Activity; 16.2.1 Submission of Audit Committee Report; Number (4) audit committee reports submitted to council by June 2026; Q1-Q4: Council resolutions; TARGET: Number; 4; 1; 1; 0; 100%; Office of the Municipal Manager; Internal Audit Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Output | 17.1 Fraud Management Plan developed and approved |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 17.1.1; Activity; 17.1.1 Hold Anti-fraud and Corruption Awareness Training and Workshop; Number (1) of Anti-fraud and Corruption Awareness Training and Workshops held by December2025; Presentations and attendance register; TARGET: Number; 1; 1; 1; 0; 100%; Office of the Municipal Manager; Risk Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Output | 17.2 Risk Management Plan developed and approved |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 17.2.1; Activity; 17.2.1 Hold Risk Management Committee meetings; Number (4) of Risk Management Committee meetings held by June 2026; Minutes of the RMC meeting and attendance register; TARGET: Number; 4; 1; 1; 0; 100%; Office of the Municipal Manager; Risk Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Output | 18.1 IDP reviewed in accordance with approved Process Plan |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.1.1; Activity; 18.1.1 Develop a credible IDP Process plan; Number (1) of 2026-2027 credible IDP Process plans developed by September 2026; Copy of a 2026-2027 process plan; TARGET: Number; 1; 0; 0; 0; 0; Office of the Municipal Manager; IDP Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.1.2; Activity; 18.1.2 Hold 2026/2027 IDP Ward based consultations; Number (26) of 2026-2027 IDP Ward based consultations held by December 2026; 2026-2027 Ward Based consultation report; TARGET: Number; 26; 26; 26; 0; 100%; Office of the Municipal Manager; IDP Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: Opex; 520000; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.1.3; Activity; 18.1.3 Hold IDP REP Forum meetings; Number (4) of IDP REP Forum meetings held by June 2026; Minutes and attendance register; TARGET: Number; 4; 1; 1; 0; 100%; Office of the Municipal Manager; IDP Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: Opex; 100000; 0; 0; 0; 0. Calculations Applied; Cumulative Indicator. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.1.4; Activity; 18.1.4 Capacitate IDP REP Forums; Number (1) of IDP REP Forums capacitated.; Report and Attendance register; TARGET: Number; 1; 1; 1; 0; 100%; Office of the Municipal Manager; IDP Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: Opex; 200000; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Output | 18.2 Communication Strategy developed and implemented |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.2.1; Activity; 18.2.1 Hold Communication strategy Workshop; Number (1) of Communication strategy Workshops held by December 2025; Attendance register; TARGET: Number; 1; 1; 1; 0; 100%; Office of the Municipal Manager; Communications Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: Opex; 50000; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.2.2; Activity; 18.2.2 Develop Cooperate Identity Manuals; Number (1) of Cooperate Identity Manuals developed by December 2025; Cooperate identity manual; TARGET: Percentage; 1; 1; 1; 0; 100%; Office of the Municipal Manager; Communications Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: Opex; 200000; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.2.3; Activity; 18.2.3 Develop Communications and Social Media Policies; Number (3) of Communications and Social Media Policies developed by June 2026; Copies of media, communications, and social media policies; TARGET: Number; 3; 1; 1; 0; 100%; Office of the Municipal Manager; Communications Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.2.4; Activity; 18.2.4 Procure Diaries, Promotion Materials and Calendars; Number (3) of Diaries, Promotion Materials and Calendars procured by June 2026; Prove of purchase; TARGET: Number; 3; 2; 2; 0; 100%; Office of the Municipal Manager; Communications Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: Opex; 250000; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.2.5; Activity; 18.2.5 Hold Media Communications and Coverage Promotions; Number (4) of Media Communications and Coverage Promotions held by June 2026; Prove of purchase; TARGET: Number; 4; 1; 1; 0; 100%; Office of the Municipal Manager; Communications Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: Opex; 100000; 0; 0; 0; 0. Calculations Applied; Cumulative Indicator. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Output | 18.4 Communities and interested stakeholders engaged on the 2024/2025 Annual Report |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.4.1; Activity; 18.4.1 Workshop for all the members of MPAC on the role and responsibilities of MPAC.; Number (1) Workshop for all members of MPAC on the roles and responsibilities of MPAC by June 2026; Q:3 Invitation, Attendance registers.; TARGET: Number; 1; 0; 0; 0; 0; Office of the Municipal Manager; MPAC Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 150000; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.4.2; Activity; 18.4.2 Consolidation of the draft 2024/2025 Oversight Report by MPAC committee by end of March 2026; Percentage (100) completion of the consolidation of the draft 2024/2025 Oversight Report by MPAC committee by March 2026; Invitations, Attendance registers and draft oversight report.; TARGET: Percentage; 100; 0; 0; 0; 0; Office of the Municipal Manager; MPAC Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 120000; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.4.3; Activity; 18.4.3 Printing of the 2024/2025 Annual Oversight Report; Percentage (100) completion of the Printing of the 2024/2025 Annual Oversight Report by March 2026; Final Oversight report adopted by council.; TARGET: Percentage; 100; 0; 0; 0; 0; Office of the Municipal Manager; MPAC Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 381049.25; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.4.4; Activity; 18.4.4 Engagement on the 2024/2025 Annual Report with community members by end of March 2026; Number (4) of engagements on the 2024/2025 Annual Report with community members by end of March 2026; Invitations, Minutes and attendance register; TARGET: Number; 4; 0; 0; 0; 0; Office of the Municipal Manager; MPAC Manager. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 150000; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |

Moretele Local Municipality

_____________________________________________________

2025/2026

SDBIP and IDP Working Document

___________________________________

OFFICE OF THE CHIEF WHIP

| Outcome | 18. Promote participatory development and local democracy through effective oversight |
| --- | --- |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.10; Output; 18.10 Implementation of Whipery Initiatives; Percentage (100) Implementation of Whipery Initiatives by June 2026; Report; TARGET: Percentage; 100; 100; 100; 0; 100%; Office of the Single Whip; Manager - Office of the Single Whip. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Output | 18.10 Implementation of Whipery Initiatives |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.10.1; Activity; 18.10.1 Hold Information Sharing Session between Whips of all political affiliates and portfolio whips.; Number (4) of Whipery Forum held and 04 Portfolio Whip by June 2026; Attendance Register and Minutes; TARGET: Percentage; 4; 1; 1; 0; 100%; Office of the Single Whip; Manager - Office of the Single Whip. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 30000; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.10.2; Activity; 18.10.2 Hold Direct Engagements with Stakeholders concerning good governance and service delivery issues; Number (4) of Governance Forum held by June 2026; Attendance Register and Reports; TARGET: Number; 4; 1; 1; 0; 100%; Office of the Single Whip; Manager - Office of the Single Whip. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 250000; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.10.3; Activity; 18.10.3 Hold Political engagements in order to make our institution politically stable and avoid unnecessary tension within our institution.; Number (4) of Political Caucus Management (Multi-Party Caucus) held by June 2026; Attendance Register and Reports; TARGET: Number; 4; 1; 1; 0; 100%; Office of the Single Whip; Manager - Office of the Single Whip. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 30000; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.10.4; Activity; 18.10.4 Capacitate Councilors as Custodian of the society in the implementation of service delivery.; Number (4) of Council Caucuses held by June 2026; Attendance Register and Reports; TARGET: Number; 4; 1; 1; 0; 100%; Office of the Single Whip; Manager - Office of the Single Whip. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 40000; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.10.5; Activity; 18.10.5 Voter registration drives, hosting candidate forums or debates, and conducting outreach efforts to inform and mobilize the electorate Organized; Number (4) of Letsema Programmes by June 2026; Programmes and Attendance Register; TARGET: Number; 4; 1; 1; 0; 100%; Office of the Single Whip; Manager - Office of the Single Whip. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 220000; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |

Moretele Local Municipality

_____________________________________________________

2025/2026

SDBIP and IDP Working Document

___________________________________

OFFICE OF THE SPEAKER

| Outcome | 18. Promote participatory development and local democracy through effective oversight |
| --- | --- |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.3; Output; 18.3 Participatory development and local democracy promoted through effective ward committee system; Percentage (100) of promotions in participatory development and effective award system; Q1-Q4: Copies of Ward Committee meeting attendance registers; TARGET: Percentage; 100; 100; 100; 0; 100%; Office of the Speaker; Manager- Office of the Speaker. CAPITAL: Capex; 0; 0; 0; 0; 0. OPERATING: N/A; 150000; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Output | 18.3 Participatory development and local democracy promoted through effective ward committee system |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.3.1; Activity; 18.3.1 Conduct Ward Committee meetings; Number (20) of Ward Committee meetings held by June 2026; Q1-Q4: Copies of Ward Committee meeting attendance registers; TARGET: Number; 20; 5; 5; 0; 100%; Office of the Speaker; Manager- Office of the Speaker. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 4149600; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.3.2; Activity; 18.3.2 Award Councillor's Bursary; Number (1) of Councillor's Bursary Awarded by March 2026; Q1; list of Registered Councilor's; TARGET: Number; 1; 0; 0; 0; 0; Office of the Speaker; Manager- Office of the Speaker. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 500000; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.3.3; Activity; 18.3.3 Purchase Ward Committee Uniforms and Identifications; Number (260) of Ward Committee Uniforms and Identifications purchased by March 2025; Q2: Invoices and Receipts; TARGET: Number; 260; 0; 0; 0; 0; Office of the Speaker; Manager- Office of the Speaker. CAPITAL: N/A; 0; 0; 0; 0; 0. OPERATING: N/A; 230800; 0; 0; 0; 0. Calculations Applied; Override Autosum,. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.3.4; Activity; 18.3.4 Hold Ward Councilors and Secretaries Forum; Number (4) of Ward Councilors and Secretaries Forum held by June 2026; Q1-Q4: Copy of Attendance Registers; TARGET: Number; 4; 1; 1; 0; 100%; Office of the Speaker; Manager- Office of the Speaker. CAPITAL: N/A; 50000; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Cumulative Indicator. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |
| Reference No; Planning Level; Measurable Objective; Key Performance Indicator; Evidence; UOM; Annual Plan; Planned; Actual; Variance; % Performance Achieved; Dept; Responsible Person. 18.3.5; Activity; 18.3.5 Hold Ordinary Council meetings; Number (4) of Ordinary Council meetings held by June 2026; Q1-Q4: Copy of Attendance Registers and Invites; TARGET: Number; 4; 1; 1; 0; 100%; Office of the Speaker; Manager- Office of the Speaker. CAPITAL: N/A; 250000; 0; 0; 0; 0. OPERATING: N/A; 0; 0; 0; 0; 0. Calculations Applied; Cumulative Indicator. Variance Reasons. Corrective Actions. Employee Comments. Line Manager Comments. |

6. Reporting Fundamentals

- Reporting for 2025/2026, consistent with the approved PMS Policy, will be guided by the following fundamentals, that:

- In the absence of two signatures (administrative and political office bearers) authorising the report’s completeness and finality, the report will be considered as final and not submitted.

- That reporting by all directorates and or units will be within the reporting regime as depicted in the figure below.

- That all the reports are to be submitted in hard (signed) and soft copies inclusive with applicable Portfolio of Evidence (POE’s).

- Preferably POE’s are to be scanned and submitted with the report. Original files to be kept safely by reporting directorates / units.

- That reports are to follow the authorised reporting framework without any alterations.

7. Reporting Regime

Presentations / Engagement on the reports

_____________________________________________________________________________________________________________

8. Signing Off

Signed off by:

THE ACCOUNTING OFFICER

Name: Mr. Sipho Ngwenya

Date: 29. January 2025

Signature: